## TECH
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
Program Office | N.1.01.3.01.01 | WYATT, E JAY | 1.1147 | 0.03584 | 1.1147 |  |  |  | 7.661% | 14.5515
AMMOS DTN PILOT IMP | N.1.02.3.01.10 | CASTANO, REBECCA | 11.3231 | 0.42693 | 16.1666 | APL subcontract funding planned in October will be sent in November ($5K) |  | 2020-11-20 | 65.59% | 24.6498
Next Gen Plan & Seq | N.1.03.3.01.10 | CHIEN, DR. STEVE A | 3.0899 | 0.30616 | 3.0899 |  |  |  | 41.18% | 7.5037
Low-Thrust Opt | N.1.04.3.01.10 | CHIEN, STEVE | -7.4796 | -0.26553 | -7.4796 |  |  |  | -80.95% | 9.2397
Interactive Data Vis | N.1.04.3.02.10 | STUART, JEFFREY R | -16.3305 | -0.17324 | -32.8075 | Internships for Rohan Patel & Jimmy Moore, along with some early work for Sagan | Going into hiatus for a few months, will correct overrun | 2020-01-20 | -700.5% | 4.6836
DATA DRIVEN EXPLORER | N.1.05.3.01.10 | TAPELLA, ROBERT K | 0.029648 | 0.05439 | 0.029648 |  |  |  | 0.1974% | 15.02
Patch | N.1.05.3.02.10 | AYOUB, FRANCOIS | 5.1741 | 0.2112 | 5.1741 |  |  |  | 100% | 5.1741
AUTO ARCH & FLIGHT-GROUND INTE. | N.1.06.3.01.10 | TAPELLA, ROBERT K | -3.1782 | -0.0277 | -3.1782 |  |  |  | -26.07% | 12.1896
|  | TOTAL |  |  | -17.8904
-18

## MGMT
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
AMMOS PROG MGMT | A.1.01.0.01.01 | CUDA, DEBRA | 7.8057 | 0.14138 | 13.2957 | slight dip in labor; lower than budgeted chargebacks | none at this time | N/A | 14.58% | 91.1734
AMMOS PROG ADMIN | A.1.01.0.02.01 | CUDA, DEBRA | -4.5128 | -0.34989 | -4.5128 | labor above budgeted amount | none at this time | N/A | -10.2% | 44.2615
MISSION INT OFFICE | A.1.01.0.04.11 | ELLIOTT, ROBERT G | 33.5777 | 1.0121 | 33.5777 |  |  |  | 43.42% | 77.338
CUSTOMER DEVELOPMENT | A.1.01.0.05.11 | ELLIOTT, ROBERT G | 12.5214 | 0.41172 | 12.5214 |  |  |  | 96.53% | 12.9716
|  | TOTAL |  |  | 54.882

## BO
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
BUSINESS MGT | B.1.01.0.01.02 | DI PAOLO, RUSSELL M | 0.47397 | -0.03029 | 0.47397 |  |  |  | 1.666% | 28.4561
BUSINESS SPT | B.1.01.0.02.02 | DI PAOLO, RUSSELL M | 8.7233 | 0.33909 | 8.7233 |  |  |  | 18.71% | 46.6172
BUSINESS SCHED | B.1.01.0.04.02 | DI PAOLO, RUSSELL M | -2.5303 | -0.08437 | -2.5303 |  |  |  | -5.777% | 43.7995
|  | TOTAL |  |  | 6.667

## SPO
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MGSS IMP & PLNG | E.1.00.0.00.01 | GUNN, JOHANNA M | 17.2526 | 0.56321 | 17.2526 |  |  |  | 24.29% | 71.0273
|  | TOTAL |  |  | 17.2526

## RMO
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
RELAY SYS ENG | M.1.00.0.01.03 | CALL, JARED A | -10.268 | -0.46043 | -10.268 | Task is oversubscribed (first identified in Sept. MMR) with a lien currently under consideration. |  |  | -58.05% | 17.6896
RELAY I&T | M.1.00.0.01.06 | CALL, JARED A | -2.4033 | -0.41856 | -2.4033 | Task is oversubscribed (first identified in Sept. MMR) with a lien currently under consideration. |  |  | -8.15% | 29.4864
RELAY MAINT | M.1.00.0.01.07 | CALL, JARED A | -7.0896 | -0.31167 | -7.0896 | Task is oversubscribed (first identified in Sept. MMR) with a lien currently under consideration. |  |  | -58.31% | 12.159
|  | TOTAL |  |  | -19.7609

## SEO
| Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
REF MISSION SYSTEMS | C.2.10.1.01.03 | STRANGE, NATHAN J | -11.7184 | -0.18197 | 47.4067 |  |  |  | 42.1% | 112.5968
Sys Deployment Imp | C.2.10.1.12.03 | PAJEVSKI, MICHAEL J | 4.9728 | -0.06429 | 2.4364 |  |  |  | 6.744% | 36.1292
MGSS Sys Engr | C.2.10.2.01.03 | RADULESCU, COSTIN | -24.0642 | -0.70037 | -17.6656 |  |  |  | -41.68% | 42.3829
AMMOS CATALOG | C.2.10.2.02.03 | ELLIOTT, ROBERT G | 0.35085 | -0.13578 | 0.35085 |  |  |  | 9.504% | 3.6918
MM GDS ENG | C.2.10.2.10.03 | O'BRIEN, ROBIN A | 2.2257 | 0.03318 | 2.2257 |  |  |  | 6.116% | 36.3913
SYS ARCH & ENG | C.2.10.2.12.05 | PAJEVSKI, MICHAEL J | 18.0869 | 0.51741 | 19.8061 | More funding added in Oct than could be used by B. Taber. | B. Taber is expected to ramp up in Nov. | 2020-12-01 | 49.24% | 40.2226
SOFTWARE SYS ENG | C.2.10.2.13.03 | GIESELMAN, KENNETH G | -2.0769 | -0.01938 | -12.8048 | Charging at planned rate, but overhead is higher than expected. | None planned. | 2020-12-01 | -207.9% | 6.1585
COMPUTE PLATFORM ENG | C.2.10.2.19.03 | NGUYEN, VU H | 0.51052 | -0.07992 | 0.51052 |  |  |  | 1.474% | 34.6374
GDS Security | C.2.11.1.13.10 | PAJEVSKI, MICHAEL J | 8.1034 | -0.01177 | 18.473 | One subcontractor funding increment made in Nov instead of Oct. | Subcontractor funding was provided in Nov & will continue according to plan -- with exception for Oct. | 2020-12-20 | 48.11% | 38.4001
ASEC MAINT | C.2.11.2.05.07 | GIESELMAN, KENNETH G | -24.7306 | -0.87575 | -41.4941 | Developer and SE only charged the maintenance task in Oct. | Timecard correction (in progress) will correct some of the variance, the rest will be handled through adjusting task plans and potential cost transfers. | 2020-12-20 | -91.21% | 45.4949
SEO SECURITY | C.2.11.2.11.03 | PAJEVSKI, MICHAEL J | -1.368 | 0.01584 | -1.368 |  |  |  | -11.12% | 12.2981
MGSS Configuration M | C.2.12.2.01.04 | NGUYEN, SHAWN N | -3.4345 | -0.36774 | -3.4345 |  |  |  | -4.765% | 72.0815
Config MGMT Mainten | C.2.12.2.02.07 | NGUYEN, SHAWN N | 0.771 | 0.00198 | 0.19214 |  |  |  | 7.056% | 2.7232
I&T VALIDATION | C.2.13.2.04.06 | MARKHAM, SCOTT D | 17.0748 | 0.80224 | 17.0748 | One Cat-A Test Engineer was on vacation for a week and Raytheon Subcontract for Security Patch Testing does not begin until fiscal Novemebr | The start of the Raytheon subcontract for Security Patch Testing will begin to erase the under-run with reocvery expect in fiscal January. Our Cat-A test engineer will return to full-time. | 2020-01-21 | 15.45% | 110.5255
MGSS PORT CHARGES | C.2.13.2.08.09 | MARKHAM, SCOTT D | 5.4054 | 0 | 5.4054 | ITSD charging for ports affected by change in MGSS account numbers. After account number correction this account should be over-run in fiscal November | Port charges delayed by change in MGSS account numbers. After account number correction this account should be over-run in fiscal November correctig the under-run | 2020-11-20 | 64.68% | 8.3576
MM INT & TEST DEP SE | C.2.13.2.17.03 | MARKHAM, SCOTT D | 2.4318 | 0.05284 | 2.4318 |  |  |  | 6.512% | 37.3419
MM DEPLOYMENT ENG | C.2.13.2.18.03 | MARKHAM, SCOTT D | -2.1587 | -0.05886 | -2.1587 |  |  |  | -8.128% | 26.5581
MGSS - IMS | C.2.14.2.01.09 | MCCLEARY, JENNIFER M | 10.9351 | 0.33696 | 10.9351 | Underrun due some vacation time and due to the team having to wait for tester feedback & configuration changes from the EPDM team. | Manual migration of documents to the new system will ramp up labor charges. | 2020-12-20 | 40.56% | 26.9594
MM GDS SUPPORT | C.2.14.2.16.09 | O'BRIEN, ROBIN A | 31.101 | 1.1948 | -1.1465 |  |  |  | -1.804% | 63.5441
SEC PLAN-H/W-LIC | C.2.14.2.21.09 | O'BRIEN, ROBIN A | -5.2221 | -0.01218 | -5.2221 |  |  |  | -21.18% | 24.6594
SYS ENG SA | C.2.14.2.22.09 | O'BRIEN, ROBIN A | 51.5435 | 0 | 51.5435 |  |  |  | 100% | 51.5435
AMMOS Deployment in the Cloud | C.2.15.1.12.10 | RADULESCU, COSTIN | 17.7594 | 0.67759 | 17.7594 |  |  |  | 58.36% | 30.4307
ASEC Impl | C.2.15.1.15.10 | PAJEVSKI, MICHAEL J | 15.9564 | 0.49184 | 5.2285 | Developer and SE only charged the maintenance task in Oct. | Timecard correction (in progress) will correct some of the variance, the rest will be handled through adjusting task plans and potential cost transfers. | 2020-12-20 | 29.35% | 17.8169
Common Logging Svc Impl | C.2.15.1.16.10 | PAJEVSKI, MICHAEL J | 3.3844 | 0 | -6.7291 | Scheduling of subcontractor increments slightly different than plan. | None planned. | 2020-12-20 | -82.2% | 8.1866
DTN Network Monitor Configuration | C.2.15.1.17.10 | PAJEVSKI, MICHAEL J | 0 | 0 | 8.8139 | APL subcontract funding planned in October will be sent in November. |  | 2020-11-20 | 100% | 8.8139
ASIS | C.2.15.2.01.10 | GIESELMAN, KENNETH G | 7.132 | -0.06739 | -22.3019 | Scheduling of subcontractor increments slightly different than plan. | None planned. | 2020-12-20 | -43.16% | 51.6681
Common Logging Svc | C.2.15.2.06.10 | GIESELMAN, KENNETH G | 3.5227 | 0 | -6.7564 | Scheduling of subcontractor increments slightly different from plan. | None planned. | 2020-12-20 | -82.81% | 8.1593
CSE | C.2.15.2.07.10 | GIESELMAN, KENNETH G | 16.8777 | -0.1084 | 53.2415 | Cost for planned purchases have not come in yet. Planned labor rates shown (0.13) do not match submitted IBT (0.33). | Need to update planned labor rates to match submitted IBT. Planned purchases in progress. | 2020-11-20 | 59.15% | 90.0152
MGSS SQA Support | C.2.16.2.13.05 | BOKOR, EVA | -9.1926 | 1.3037 | -9.1926 | Labor charged as a service over planned amount | CAM will adjust charging going forward. | 2020-11-20 | -24.66% | 37.2749
|  | TOTAL |  |  | 133.5613

## MDN
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MDN MANAGEMENT | G.1.00.0.00.01 | BERRY, DAVID S | 12.6525 | 0.27461 | 12.6525 | The AEM had two other major tasks in October: (1) Preparations for CCSDS Fall Meetings, and (2) completing the MADCAP 3.1 release work. Both of these tasks have non-AMMOS accounts, so time was charged elsewhere. | The CCSDS Meetings will be over in November. The MADCAP task completed 11/2/2020. Recovery will be a little delayed since I will be taking some December vacation time. | 2021-01-31 | 41.9% | 30.2004
MDN SYS ENG | G.1.00.0.00.03 | GERASIMATOS, DIMITRIOS V | 12.1355 | 0.41115 | 12.1355 | The lead MDN System Engineer has some non-AMMOS tasks. We have individuals WAM'd to the account to work on some of the other tasks, but these didn't kick in immediately with the change of FY. | Individuals WAM'd to the account have commenced work on their assignments. | 2021-12-31 | 38.61% | 31.4303
MONTE/MASAR PDM | G.1.00.0.01.01 | EVANS, DR. SCOTT E | -1.386 | -0.03029 | -1.386 |  |  |  | -4.348% | 31.875
MDN SOFTWARE ADV-2 | G.2.01.1.06.10 | EVANS, DR. SCOTT E | -23.3924 | -0.81734 | -23.3924 | Resources have been immediately available to work on the scoped tasks for the next Monte release. | As the scoped tasks for the next Monte release are completed, and resources are needed related to other accounts, resources will be shifted. | 2021-01-31 | -71.1% | 32.902
Automated RMM Design & Implemntn | G.2.01.1.12.10 | EVANS, DR. SCOTT E | -3.6229 | -0.18993 | -3.6229 |  |  |  | -10.32% | 35.1186
MONTE MAINT | G.2.01.2.02.07 | EVANS, DR. SCOTT E | 20.4142 | 0.81237 | 20.4142 | There was a greater emphasis on new development in October than on maintenance. | As bugs are addressed in the Monte software, this account will recover. | 2021-01-31 | 38.27% | 53.3424
MONTE TRAIN & CUST SUPT | G.2.01.2.02.11 | EVANS, DR. SCOTT E | -0.66949 | -0.06314 | 8.7385 | We had two $10K subcontracts in the plan to obligate in October, but only one did. | The second subcontract should obligate in November, which should get us back on plan. | 2020-11-20 | 36.72% | 23.7949
NAV SW AUTOMA MAINT | G.2.01.2.03.07 | TABER, DR. WILLIAM L | -2.3858 | -0.11675 | -2.3858 | $2K is not a problem. There should be a minimum dollar amount for reporting a variance, perhaps $5K, especially at the beginning of the FY. | None | N/A | -26.27% | 9.0814
Monte/Masar "SparQ" 3D Viz Enh | G.3.01.1.03.10 | EVANS, DR. SCOTT E | 24.4365 | 0.84047 | 24.4365 | The primary resource who will be working on this task has some other assignments, so we haven't started work on this yet. We are also preparing the Task Implementation Plan (TIP) for the task. | Work may start in November. The TIP should be in DMS Review in November, perhaps even released. | 2021-01-31 | 100% | 24.4365
SPICE MAINT | G.4.01.2.01.07 | ACTON, CHARLES H JR. | 1.5756 | 0.04452 | 1.5756 | $2K is not a problem. There should be a minimum dollar amount for reporting a variance, perhaps $5K, especially at the beginning of the FY. The necessity for filing variance reports on such a small LoE account is PRECISELY the reason I did not want to accept this $20.5K account, but Andy mandated it. | None | N/A | 100% | 1.5756
PLANETARY EPHEMERIS | G.5.01.2.01.09 | PARK, DR. SANG H | 2.5681 | 0.15461 | 2.5681 |  |  |  | 4.636% | 55.3882
SATELLITE EPHEMERIS | G.5.02.2.01.09 | PARK, DR. SANG H | -12.2097 | -0.41868 | -12.2097 | Significant new releases on Jupiter moons for missions such as Juno, Europa Clipper, Europa Lander, and significant work on Neptunian moons in for the Trident mission. | Work on at least the Neptunian satellites has completed. Jupiter moon research will continue, but on "smaller picture" issues. | 2020-12-31 | -24.65% | 49.537
CMT/AST EPHEMERIS | G.5.03.2.01.09 | PARK, DR. SANG H | 6.0305 | -0.13362 | 6.0305 |  |  |  | 9.258% | 65.1412
GRAVITY MODELLING | G.5.04.2.01.09 | PARK, DR. SANG H | -4.571 | -0.2297 | -4.571 | I don't really think $5K is a problem given that we have just started a new fiscal year and there is plenty of time to recover. However, the overrun is likely due to development of an updated Mars gravity model and a scientific journal paper that accompanies it. | Resources will be reduced to recover the account. | 2020-12-27 | -22.8% | 20.0451
Lunar Conj Assessment | G.6.03.2.02.09 | BERRY, DAVID S | 1.2561 | 0.02548 | 1.2561 | $1K is not a problem. There should be a minimum dollar amount for reporting a variance, perhaps $5K, especially at the beginning of the FY. | None | N/A | 50.46% | 2.4893
Astrodynamics Tech Infusion | G.7.01.1.01.10 | EVANS, DR. SCOTT E | 3.1407 | 0.08738 | 3.1407 | $3K is not a problem. There should be a minimum dollar amount for reporting a variance, perhaps $5K, especially at the beginning of the FY. | None | N/A | 19.09% | 16.4541
|  | TOTAL |  |  | 45.3803

## MPSA
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MPSA MGMT | H.1.00.0.00.01 | CHAFIN, BRIAN G | 13.0276 | 0.30404 | 13.0276 |  |  |  | 32.92% | 39.5723
MGSS SEQ SE | H.1.00.0.00.03 | CHAFIN, BRIAN G | -15.7969 | -0.0278 | -19.4548 |  |  |  | -31.59% | 61.5915
SEQ SUBSYSTEM TEST | H.1.00.0.00.06 | CHAFIN, BRIAN G | 17.0802 | 0.44132 | 17.0802 |  |  |  | 24.62% | 69.3713
MPS MAINT NEW | H.1.00.0.00.07 | CHAFIN, BRIAN G | -11.1203 | -1.1262 | -11.1203 |  |  |  | -15.3% | 72.6843
Web Int for Plan Maint | H.1.00.2.02.07 | CHAFIN, BRIAN G | 2.3589 | 0.0848 | 2.3589 |  |  |  | 100% | 2.3589
SOA Rearchitecture | H.2.01.1.05.10 | CHAFIN, BRIAN G | -0.59751 | 0.00987 | -0.65386 |  |  |  | -2.67% | 24.4853
Aerie Adv MPS Seq | H.3.01.1.20.10 | CHAFIN, BRIAN G | 4.9445 | 0.18366 | 4.9445 |  |  |  | 5.231% | 94.5164
Spacecraft State Estimation | H.5.01.1.03.10 | CHEUNG, DR. KAR-MING | -0.96947 | -0.02531 | -0.96947 |  |  |  | #DIV/0! | 0
S/C Analysis Maint | H.5.01.2.01.07 | CHEUNG, DR. KAR-MING | 10.542 | 0.32193 | 10.542 |  |  |  | 43.48% | 24.2449
|  | TOTAL |  |  | 15.7548

## MMCS
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MCS MGT | J.1.00.0.00.01 | KHAZRA, MOOJAN | -1.2085 | -0.0917 | -1.2085 |  |  |  | -3.792% | 31.8708
MCS SYS ENG | J.1.00.0.00.03 | KHAZRA, MOOJAN | -0.37462 | -0.06207 | -0.37462 |  |  |  | -0.8983% | 41.7054
MCS TEST ENG | J.1.00.0.00.06 | SHAMILIAN, ARSHALUYS | -7.6857 | -0.38127 | -7.6857 |  |  |  | -14.41% | 53.3513
MCS SYS LVL MAINT | J.1.00.0.00.07 | KHAZRA, MOOJAN | 2.0639 | 0.00261 | 2.0639 |  |  |  | 3.069% | 67.2456
MMCS Support | J.1.00.0.00.11 | KHAZRA, MOOJAN | 4.1152 | 0.14776 | 4.1152 | Underrun in October is due to less support needed from Boris Borelly for transition of CogE responsibilites to Nicole Witeck | None | 2021-09-01 | 100% | 4.1152
Sys Admin & Dep SUPT | J.1.00.0.01.03 | KHAZRA, MOOJAN | 11.2288 | 0 | 11.2288 | Underrun in October is due to sick leave and less support needed from Nicholai Brooks for transition of SA responsibilities to John Riehl. | None | 2021-09-01 | 41.88% | 26.8133
Chill Mon Rep Dev Testing | J.1.00.1.05.10 | KHAZRA, MOOJAN | 6.6963 | 0.21524 | 6.6963 | Underrun in October is due to VISTA 4. code freeze is after October. | Testing effor will ramp up in Novemeber. | 2021-02-01 | 75.7% | 8.8453
VISTA Maintenance | J.1.00.2.05.07 | KHAZRA, MOOJAN | -0.10589 | 0 | -0.10589 |  |  |  | #DIV/0! | 0
Int Command Maint | J.2.02.2.01.07 | KHAZRA, MOOJAN | -1.0087 | -0.11572 | -1.0087 |  |  |  | -6.324% | 15.9514
Telemetry&Commanding Closed Loop Test Framework | J.2.07.1.17.10 | KHAZRA, MOOJAN | 0 | 0 | 24.9401 | APL subcontract funding planned in October will be sent in November. | None | 2020-11-20 | 100% | 24.9401
AMPCS Pass Automation | J.2.07.2.12.07 | KHAZRA, MOOJAN | 1.6938 | 0.07738 | 1.6938 | WA for this task has not been approved. | None | NA | 100% | 1.6938
TDAC - Maintenance | J.2.16.2.01.07 | KHAZRA, MOOJAN | 1.3893 | 0.05708 | 1.3893 |  |  |  | 9.427% | 14.737
DATA MGT MAINT | J.3.01.2.01.07 | KHAZRA, MOOJAN | 6.7652 | 0.16495 | 6.7652 | Underrun in October is due to late start of the tester than planned | Will ramp up efforts when SHIP/DOM is released in May | 2021-06-01 | 15.75% | 42.958
MDMS (DOM Replacement) | J.3.02.1.04.10 | KHAZRA, MOOJAN | 19.3889 | 0.69638 | 19.3889 | Underrun in October is due to family sick leave of staff | Will ramp up effirts when implementation starts in Feb | 2021-07-21 | 59.19% | 32.756
|  | TOTAL |  |  | 67.898

## IDS
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
IDS MGMT | K.1.00.0.01.01 | DAHL, LUKE B | -2.6368 | -0.14296 | -2.6368 |  |  |  | -6.747% | 39.0816
IDS SYS ENG | K.1.00.0.01.03 | TINIO, ADRIAN W | 11.1434 | 0.3858 | 11.1434 |  |  |  | 28.02% | 39.7692
IDS I&T | K.1.00.0.01.06 | LEE, PHAN | -19.0712 | -0.69971 | -19.0712 |  |  |  | -55.45% | 34.3908
SYS SW-HW INF M | K.1.00.0.02.07 | LEUNG, ALEX | 10.9235 | -0.06386 | 10.7336 |  |  |  | 25.61% | 41.9066
Sys SW Modernization | K.1.00.0.04.07 | LIU, JEFF Y | -2.4442 | -0.15698 | -139.4175 |  |  |  | -548.4% | 25.4236
SYNOPSIS | K.1.00.1.04.10 | LEUNG, ALEX | -2.18 | -0.07011 | -2.18 |  |  |  | -41.42% | 5.2632
AFIDS Auto Plan Image | K.1.00.1.08.10 | LOGAN, DR. THOMAS L | 6.1649 | 0.16628 | 6.1649 |  |  |  | 43.99% | 14.015
IDS EXP & TAC MAINT | K.1.00.2.01.07 | TINIO, ADRIAN W | 16.4572 | 0.74917 | 16.4572 |  |  |  | 30.81% | 53.4214
IOS/SDS Cloud Deployment | K.2.01.1.08.10 | TINIO, ADRIAN W | 23.4966 | 0.76092 | 23.4966 |  |  |  | 76.69% | 30.6382
USER CONSULTANT | K.2.04.2.02.11 | DAHL, LUKE B | 4.6751 | 0.16534 | 4.6751 |  |  |  | 79.28% | 5.8973
CARGO | K.3.02.1.02.10 | DAHL, LUKE B | 3.1774 | 0.08436 | 3.1774 |  |  |  | 24.14% | 13.1634
CCSDS Architecture Support | K.4.01.2.01.03 | DAHL, LUKE B | -6.949 | -0.21254 | -2.4674 |  |  |  | -13.94% | 17.6947
Data Order via Uncertainty Est | K.4.02.1.01.10 | LIUKIS, MARIA | -9.8797 | -0.56231 | -9.8797 |  |  |  | -80.08% | 12.3375
Sim Local and Map for Img Surfacing | K.4.02.1.04.10 | DAHL, LUKE B | 13.0083 | 0.52289 | 13.0083 |  |  |  | 92.5% | 14.0625
|  | TOTAL |  |  | -86.7963

## Summary
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
AMMOS PROG MGMT | A.1.01.0.01.01 | CUDA, DEBRA | 7.8057 | 0.14138 | 13.2957 |  |  |  | 14.58% | 91.1734
AMMOS PROG ADMIN | A.1.01.0.02.01 | CUDA, DEBRA | -4.5128 | -0.34989 | -4.5128 |  |  |  | -10.2% | 44.2615
MISSION INT OFFICE | A.1.01.0.04.11 | ELLIOTT, ROBERT G | 33.5777 | 1.0121 | 33.5777 |  |  |  | 43.42% | 77.338
CUSTOMER DEVELOPMENT | A.1.01.0.05.11 | ELLIOTT, ROBERT G | 12.5214 | 0.41172 | 12.5214 |  |  |  | 96.53% | 12.9716
BUSINESS MGT | B.1.01.0.01.02 | DI PAOLO, RUSSELL M | 0.47397 | -0.03029 | 0.47397 |  |  |  | 1.666% | 28.4561
BUSINESS SPT | B.1.01.0.02.02 | DI PAOLO, RUSSELL M | 8.7233 | 0.33909 | 8.7233 |  |  |  | 18.71% | 46.6172
BUSINESS SCHED | B.1.01.0.04.02 | DI PAOLO, RUSSELL M | -2.5303 | -0.08437 | -2.5303 |  |  |  | -5.777% | 43.7995
REF MISSION SYSTEMS | C.2.10.1.01.03 | STRANGE, NATHAN J | -11.7184 | -0.18197 | 47.4067 |  |  |  | 42.1% | 112.5968
Sys Deployment Imp | C.2.10.1.12.03 | PAJEVSKI, MICHAEL J | 4.9728 | -0.06429 | 2.4364 |  |  |  | 6.744% | 36.1292
MGSS Sys Engr | C.2.10.2.01.03 | RADULESCU, COSTIN | -24.0642 | -0.70037 | -17.6656 |  |  |  | -41.68% | 42.3829
AMMOS CATALOG | C.2.10.2.02.03 | ELLIOTT, ROBERT G | 0.35085 | -0.13578 | 0.35085 |  |  |  | 9.504% | 3.6918
MM GDS ENG | C.2.10.2.10.03 | O'BRIEN, ROBIN A | 2.2257 | 0.03318 | 2.2257 |  |  |  | 6.116% | 36.3913
SYS ARCH & ENG | C.2.10.2.12.05 | PAJEVSKI, MICHAEL J | 18.0869 | 0.51741 | 19.8061 |  |  |  | 49.24% | 40.2226
SOFTWARE SYS ENG | C.2.10.2.13.03 | GIESELMAN, KENNETH G | -2.0769 | -0.01938 | -12.8048 |  |  |  | -207.9% | 6.1585
COMPUTE PLATFORM ENG | C.2.10.2.19.03 | NGUYEN, VU H | 0.51052 | -0.07992 | 0.51052 |  |  |  | 1.474% | 34.6374
GDS Security | C.2.11.1.13.10 | PAJEVSKI, MICHAEL J | 8.1034 | -0.01177 | 18.473 |  |  |  | 48.11% | 38.4001
ASEC MAINT | C.2.11.2.05.07 | GIESELMAN, KENNETH G | -24.7306 | -0.87575 | -41.4941 |  |  |  | -91.21% | 45.4949
SEO SECURITY | C.2.11.2.11.03 | PAJEVSKI, MICHAEL J | -1.368 | 0.01584 | -1.368 |  |  |  | -11.12% | 12.2981
MGSS Configuration M | C.2.12.2.01.04 | NGUYEN, SHAWN N | -3.4345 | -0.36774 | -3.4345 |  |  |  | -4.765% | 72.0815
Config MGMT Mainten | C.2.12.2.02.07 | NGUYEN, SHAWN N | 0.771 | 0.00198 | 0.19214 |  |  |  | 7.056% | 2.7232
I&T VALIDATION | C.2.13.2.04.06 | MARKHAM, SCOTT D | 17.0748 | 0.80224 | 17.0748 |  |  |  | 15.45% | 110.5255
MGSS PORT CHARGES | C.2.13.2.08.09 | MARKHAM, SCOTT D | 5.4054 | 0 | 5.4054 |  |  |  | 64.68% | 8.3576
MM INT & TEST DEP SE | C.2.13.2.17.03 | MARKHAM, SCOTT D | 2.4318 | 0.05284 | 2.4318 |  |  |  | 6.512% | 37.3419
MM DEPLOYMENT ENG | C.2.13.2.18.03 | MARKHAM, SCOTT D | -2.1587 | -0.05886 | -2.1587 |  |  |  | -8.128% | 26.5581
MGSS - IMS | C.2.14.2.01.09 | MCCLEARY, JENNIFER M | 10.9351 | 0.33696 | 10.9351 |  |  |  | 40.56% | 26.9594
MM GDS SUPPORT | C.2.14.2.16.09 | O'BRIEN, ROBIN A | 31.101 | 1.1948 | -1.1465 |  |  |  | -1.804% | 63.5441
SEC PLAN-H/W-LIC | C.2.14.2.21.09 | O'BRIEN, ROBIN A | -5.2221 | -0.01218 | -5.2221 |  |  |  | -21.18% | 24.6594
SYS ENG SA | C.2.14.2.22.09 | O'BRIEN, ROBIN A | 51.5435 | 0 | 51.5435 |  |  |  | 100% | 51.5435
AMMOS Deployment in the Cloud | C.2.15.1.12.10 | RADULESCU, COSTIN | 17.7594 | 0.67759 | 17.7594 |  |  |  | 58.36% | 30.4307
ASEC Impl | C.2.15.1.15.10 | PAJEVSKI, MICHAEL J | 15.9564 | 0.49184 | 5.2285 |  |  |  | 29.35% | 17.8169
Common Logging Svc Impl | C.2.15.1.16.10 | PAJEVSKI, MICHAEL J | 3.3844 | 0 | -6.7291 |  |  |  | -82.2% | 8.1866
DTN Network Monitor Configuration | C.2.15.1.17.10 | PAJEVSKI, MICHAEL J | 0 | 0 | 8.8139 |  |  |  | 100% | 8.8139
ASIS | C.2.15.2.01.10 | GIESELMAN, KENNETH G | 7.132 | -0.06739 | -22.3019 |  |  |  | -43.16% | 51.6681
Common Logging Svc | C.2.15.2.06.10 | GIESELMAN, KENNETH G | 3.5227 | 0 | -6.7564 |  |  |  | -82.81% | 8.1593
CSE | C.2.15.2.07.10 | GIESELMAN, KENNETH G | 16.8777 | -0.1084 | 53.2415 |  |  |  | 59.15% | 90.0152
MGSS SQA Support | C.2.16.2.13.05 | BOKOR, EVA | -9.1926 | 1.3037 | -9.1926 |  |  |  | -24.66% | 37.2749
MGSS IMP & PLNG | E.1.00.0.00.01 | GUNN, JOHANNA M | 17.2526 | 0.56321 | 17.2526 |  |  |  | 24.29% | 71.0273
MDN MANAGEMENT | G.1.00.0.00.01 | BERRY, DAVID S | 12.6525 | 0.27461 | 12.6525 |  |  |  | 41.9% | 30.2004
MDN SYS ENG | G.1.00.0.00.03 | GERASIMATOS, DIMITRIOS V | 12.1355 | 0.41115 | 12.1355 |  |  |  | 38.61% | 31.4303
MONTE/MASAR PDM | G.1.00.0.01.01 | EVANS, DR. SCOTT E | -1.386 | -0.03029 | -1.386 |  |  |  | -4.348% | 31.875
MDN SOFTWARE ADV-2 | G.2.01.1.06.10 | EVANS, DR. SCOTT E | -23.3924 | -0.81734 | -23.3924 |  |  |  | -71.1% | 32.902
Automated RMM Design & Implemntn | G.2.01.1.12.10 | EVANS, DR. SCOTT E | -3.6229 | -0.18993 | -3.6229 |  |  |  | -10.32% | 35.1186
MONTE MAINT | G.2.01.2.02.07 | EVANS, DR. SCOTT E | 20.4142 | 0.81237 | 20.4142 |  |  |  | 38.27% | 53.3424
MONTE TRAIN & CUST SUPT | G.2.01.2.02.11 | EVANS, DR. SCOTT E | -0.66949 | -0.06314 | 8.7385 |  |  |  | 36.72% | 23.7949
NAV SW AUTOMA MAINT | G.2.01.2.03.07 | TABER, DR. WILLIAM L | -2.3858 | -0.11675 | -2.3858 |  |  |  | -26.27% | 9.0814
Monte/Masar "SparQ" 3D Viz Enh | G.3.01.1.03.10 | EVANS, DR. SCOTT E | 24.4365 | 0.84047 | 24.4365 |  |  |  | 100% | 24.4365
SPICE MAINT | G.4.01.2.01.07 | ACTON, CHARLES H JR. | 1.5756 | 0.04452 | 1.5756 |  |  |  | 100% | 1.5756
PLANETARY EPHEMERIS | G.5.01.2.01.09 | PARK, DR. SANG H | 2.5681 | 0.15461 | 2.5681 |  |  |  | 4.636% | 55.3882
SATELLITE EPHEMERIS | G.5.02.2.01.09 | PARK, DR. SANG H | -12.2097 | -0.41868 | -12.2097 |  |  |  | -24.65% | 49.537
CMT/AST EPHEMERIS | G.5.03.2.01.09 | PARK, DR. SANG H | 6.0305 | -0.13362 | 6.0305 |  |  |  | 9.258% | 65.1412
GRAVITY MODELLING | G.5.04.2.01.09 | PARK, DR. SANG H | -4.571 | -0.2297 | -4.571 |  |  |  | -22.8% | 20.0451
Lunar Conj Assessment | G.6.03.2.02.09 | BERRY, DAVID S | 1.2561 | 0.02548 | 1.2561 |  |  |  | 50.46% | 2.4893
Astrodynamics Tech Infusion | G.7.01.1.01.10 | EVANS, DR. SCOTT E | 3.1407 | 0.08738 | 3.1407 |  |  |  | 19.09% | 16.4541
MPSA MGMT | H.1.00.0.00.01 | CHAFIN, BRIAN G | 13.0276 | 0.30404 | 13.0276 |  |  |  | 32.92% | 39.5723
MGSS SEQ SE | H.1.00.0.00.03 | CHAFIN, BRIAN G | -15.7969 | -0.0278 | -19.4548 |  |  |  | -31.59% | 61.5915
SEQ SUBSYSTEM TEST | H.1.00.0.00.06 | CHAFIN, BRIAN G | 17.0802 | 0.44132 | 17.0802 |  |  |  | 24.62% | 69.3713
MPS MAINT NEW | H.1.00.0.00.07 | CHAFIN, BRIAN G | -11.1203 | -1.1262 | -11.1203 |  |  |  | -15.3% | 72.6843
Web Int for Plan Maint | H.1.00.2.02.07 | CHAFIN, BRIAN G | 2.3589 | 0.0848 | 2.3589 |  |  |  | 100% | 2.3589
SOA Rearchitecture | H.2.01.1.05.10 | CHAFIN, BRIAN G | -0.59751 | 0.00987 | -0.65386 |  |  |  | -2.67% | 24.4853
Aerie Adv MPS Seq | H.3.01.1.20.10 | CHAFIN, BRIAN G | 4.9445 | 0.18366 | 4.9445 |  |  |  | 5.231% | 94.5164
Spacecraft State Estimation | H.5.01.1.03.10 | CHEUNG, DR. KAR-MING | -0.96947 | -0.02531 | -0.96947 |  |  |  | #DIV/0! | 0
S/C Analysis Maint | H.5.01.2.01.07 | CHEUNG, DR. KAR-MING | 10.542 | 0.32193 | 10.542 |  |  |  | 43.48% | 24.2449
MCS MGT | J.1.00.0.00.01 | KHAZRA, MOOJAN | -1.2085 | -0.0917 | -1.2085 |  |  |  | -3.792% | 31.8708
MCS SYS ENG | J.1.00.0.00.03 | KHAZRA, MOOJAN | -0.37462 | -0.06207 | -0.37462 |  |  |  | -0.8983% | 41.7054
MCS TEST ENG | J.1.00.0.00.06 | SHAMILIAN, ARSHALUYS | -7.6857 | -0.38127 | -7.6857 |  |  |  | -14.41% | 53.3513
MCS SYS LVL MAINT | J.1.00.0.00.07 | KHAZRA, MOOJAN | 2.0639 | 0.00261 | 2.0639 |  |  |  | 3.069% | 67.2456
MMCS Support | J.1.00.0.00.11 | KHAZRA, MOOJAN | 4.1152 | 0.14776 | 4.1152 |  |  |  | 100% | 4.1152
Sys Admin & Dep SUPT | J.1.00.0.01.03 | KHAZRA, MOOJAN | 11.2288 | 0 | 11.2288 |  |  |  | 41.88% | 26.8133
Chill Mon Rep Dev Testing | J.1.00.1.05.10 | KHAZRA, MOOJAN | 6.6963 | 0.21524 | 6.6963 |  |  |  | 75.7% | 8.8453
VISTA Maintenance | J.1.00.2.05.07 | KHAZRA, MOOJAN | -0.10589 | 0 | -0.10589 |  |  |  | #DIV/0! | 0
Int Command Maint | J.2.02.2.01.07 | KHAZRA, MOOJAN | -1.0087 | -0.11572 | -1.0087 |  |  |  | -6.324% | 15.9514
Telemetry&Commanding Closed Loop Test Framework | J.2.07.1.17.10 | KHAZRA, MOOJAN | 0 | 0 | 24.9401 |  |  |  | 100% | 24.9401
AMPCS Pass Automation | J.2.07.2.12.07 | KHAZRA, MOOJAN | 1.6938 | 0.07738 | 1.6938 |  |  |  | 100% | 1.6938
TDAC - Maintenance | J.2.16.2.01.07 | KHAZRA, MOOJAN | 1.3893 | 0.05708 | 1.3893 |  |  |  | 9.427% | 14.737
DATA MGT MAINT | J.3.01.2.01.07 | KHAZRA, MOOJAN | 6.7652 | 0.16495 | 6.7652 |  |  |  | 15.75% | 42.958
MDMS (DOM Replacement) | J.3.02.1.04.10 | KHAZRA, MOOJAN | 19.3889 | 0.69638 | 19.3889 |  |  |  | 59.19% | 32.756
IDS MGMT | K.1.00.0.01.01 | DAHL, LUKE B | -2.6368 | -0.14296 | -2.6368 |  |  |  | -6.747% | 39.0816
IDS SYS ENG | K.1.00.0.01.03 | TINIO, ADRIAN W | 11.1434 | 0.3858 | 11.1434 |  |  |  | 28.02% | 39.7692
IDS I&T | K.1.00.0.01.06 | LEE, PHAN | -19.0712 | -0.69971 | -19.0712 |  |  |  | -55.45% | 34.3908
SYS SW-HW INF M | K.1.00.0.02.07 | LEUNG, ALEX | 10.9235 | -0.06386 | 10.7336 |  |  |  | 25.61% | 41.9066
Sys SW Modernization | K.1.00.0.04.07 | LIU, JEFF Y | -2.4442 | -0.15698 | -139.4175 |  |  |  | -548.4% | 25.4236
SYNOPSIS | K.1.00.1.04.10 | LEUNG, ALEX | -2.18 | -0.07011 | -2.18 |  |  |  | -41.42% | 5.2632
AFIDS Auto Plan Image | K.1.00.1.08.10 | LOGAN, DR. THOMAS L | 6.1649 | 0.16628 | 6.1649 |  |  |  | 43.99% | 14.015
IDS EXP & TAC MAINT | K.1.00.2.01.07 | TINIO, ADRIAN W | 16.4572 | 0.74917 | 16.4572 |  |  |  | 30.81% | 53.4214
IOS/SDS Cloud Deployment | K.2.01.1.08.10 | TINIO, ADRIAN W | 23.4966 | 0.76092 | 23.4966 |  |  |  | 76.69% | 30.6382
USER CONSULTANT | K.2.04.2.02.11 | DAHL, LUKE B | 4.6751 | 0.16534 | 4.6751 |  |  |  | 79.28% | 5.8973
CARGO | K.3.02.1.02.10 | DAHL, LUKE B | 3.1774 | 0.08436 | 3.1774 |  |  |  | 24.14% | 13.1634
CCSDS Architecture Support | K.4.01.2.01.03 | DAHL, LUKE B | -6.949 | -0.21254 | -2.4674 |  |  |  | -13.94% | 17.6947
Data Order via Uncertainty Est | K.4.02.1.01.10 | LIUKIS, MARIA | -9.8797 | -0.56231 | -9.8797 |  |  |  | -80.08% | 12.3375
Sim Local and Map for Img Surfacing | K.4.02.1.04.10 | DAHL, LUKE B | 13.0083 | 0.52289 | 13.0083 |  |  |  | 92.5% | 14.0625
RELAY SYS ENG | M.1.00.0.01.03 | CALL, JARED A | -10.268 | -0.46043 | -10.268 |  |  |  | -58.05% | 17.6896
RELAY I&T | M.1.00.0.01.06 | CALL, JARED A | -2.4033 | -0.41856 | -2.4033 |  |  |  | -8.15% | 29.4864
RELAY MAINT | M.1.00.0.01.07 | CALL, JARED A | -7.0896 | -0.31167 | -7.0896 |  |  |  | -58.31% | 12.159
Program Office | N.1.01.3.01.01 | WYATT, E JAY | 1.1147 | 0.03584 | 1.1147 |  |  |  | 7.661% | 14.5515
AMMOS DTN PILOT IMP | N.1.02.3.01.10 | TORGERSON, JORDAN L | 11.3231 | 0.42693 | 16.1666 |  |  |  | 65.59% | 24.6498
Next Gen Plan & Seq | N.1.03.3.01.10 | CHIEN, DR. STEVE A | 3.0899 | 0.30616 | 3.0899 |  |  |  | 41.18% | 7.5037
Low-Thrust Opt | N.1.04.3.01.10 | ANDERSON, DR. RODNEY L | -7.4796 | -0.26553 | -7.4796 |  |  |  | -80.95% | 9.2397
Interactive Data Vis | N.1.04.3.02.10 | STUART, JEFFREY R | -16.3305 | -0.17324 | -32.8075 |  |  |  | -700.5% | 4.6836
DATA DRIVEN EXPLORER | N.1.05.3.01.10 | TAPELLA, ROBERT K | 0.029648 | 0.05439 | 0.029648 |  |  |  | 0.1974% | 15.02
Patch | N.1.05.3.02.10 | AYOUB, FRANCOIS | 5.1741 | 0.2112 | 5.1741 |  |  |  | 100% | 5.1741
AUTO ARCH & FLIGHT-GROUND INTE. | N.1.06.3.01.10 | WYATT, E JAY | -3.1782 | -0.0277 | -3.1782 |  |  |  | -26.07% | 12.1896
|  | TOTAL VARIANCE |  |  | 216.9486 |  |  |  |  | 3238.7404

## VLOOKUP (hidden)
| Project Number | Task Name | Task Number | Task Manager | Burdened Cost Var YTD | FTE Avg Variance YTD | Burdened Oblig Var YTD | Burd Oblig Budg YTD | Burdened Oblig YTD | Burd Oblig Budg FY | Task Completion
| Project Number | Task Name | Task Number | Task Manager | Burdened Cost Var YTD | FTE Avg Variance YTD | Burdened Oblig Var YTD | Burd Oblig Budg YTD | Burdened Oblig YTD | Burd Oblig Budg FY | Task Completion Date
Sort | 1 |  | 2
A/D | A |  | A | [9 empty] | TASK CHECK
Sub | [12 empty] | MGMT | BO | ESO | I&P | NMD | MDAS | MPS | IOS | RMO | TECH | MISSING IF 0
| 107282 | AMMOS PROG MGMT | A.1.01.0.01.01 | PONS, JUDITH S | 7805.7263 | 0.14138 | 13295.6863 | 91173.4263 | 77877.74 | 1112005.0376 | 2021-09-26 | AMMOS PROG MGMT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | AMMOS PROG ADMIN | A.1.01.0.02.01 | PONS, JUDITH S | -4512.801 | -0.34989 | -4512.801 | 44261.539 | 48774.34 | 541433.3307 | 2021-09-26 | AMMOS PROG ADMIN | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MISSION INT OFFICE | A.1.01.0.04.11 | ELLIOTT, ROBERT G | 33577.7247 | 1.0121 | 33577.7247 | 77338.0447 | 43760.32 | 941181.3281 | 2021-09-26 | MISSION INT OFFICE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | CUSTOMER DEVELOPMENT | A.1.01.0.05.11 | ELLIOTT, ROBERT G | 12521.3857 | 0.41172 | 12521.3857 | 12971.6357 | 450.25 | 171423.3786 | 2021-09-26 | CUSTOMER DEVELOPMENT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | BUSINESS MGT | B.1.01.0.01.02 | DI PAOLO, RUSSELL M | 473.9715 | -0.03029 | 473.9715 | 28456.0515 | 27982.08 | 346094.823 | 2021-09-26 | BUSINESS MGT | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | BUSINESS SPT | B.1.01.0.02.02 | DI PAOLO, RUSSELL M | 8723.2812 | 0.33909 | 8723.2812 | 46617.2412 | 37893.96 | 567930.9827 | 2021-09-26 | BUSINESS SPT | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | BUSINESS SCHED | B.1.01.0.04.02 | DI PAOLO, RUSSELL M | -2530.2947 | -0.08437 | -2530.2947 | 43799.4753 | 46329.77 | 532483.6914 | 2021-09-26 | BUSINESS SCHED | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | REF MISSION SYSTEMS | C.2.10.1.01.03 | STRANGE, NATHAN J | -11718.3989 | -0.18197 | 47406.7393 | 112596.8093 | 65190.07 | 699979.3807 | 2021-09-26 | REF MISSION SYSTEMS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Sys Deployment Imp | C.2.10.1.12.03 | PAJEVSKI, MICHAEL J | 4972.7955 | -0.06429 | 2436.439 | 36129.239 | 33692.8 | 561954.7957 | 2021-09-26 | Sys Deployment Imp | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MGSS Sys Engr | C.2.10.2.01.03 | RADULESCU, COSTIN | -24064.163 | -0.70037 | -17665.5586 | 42382.9114 | 60048.47 | 465457.8949 | 2021-09-26 | MGSS Sys Engr | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | AMMOS CATALOG | C.2.10.2.02.03 | ELLIOTT, ROBERT G | 350.8531 | -0.13578 | 350.8531 | 3691.8131 | 3340.96 | 47993.7312 | 2021-09-26 | AMMOS CATALOG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MM GDS ENG | C.2.10.2.10.03 | O'BRIEN, ROBIN A | 2225.6644 | 0.03318 | 2225.6644 | 36391.3144 | 34165.65 | 444746.5994 | 2021-09-26 | MM GDS ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | SYS ARCH & ENG | C.2.10.2.12.05 | PAJEVSKI, MICHAEL J | 18086.8685 | 0.51741 | 19806.1223 | 40222.6323 | 20416.51 | 469812.8163 | 2021-09-26 | SYS ARCH & ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | SOFTWARE SYS ENG | C.2.10.2.13.03 | GIESELMAN, KENNETH G | -2076.8538 | -0.01938 | -12804.7638 | 6158.4963 | 18963.26 | 76581.617 | 2021-09-26 | SOFTWARE SYS ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | COMPUTE PLATFORM ENG | C.2.10.2.19.03 | NGUYEN, VU H | 510.521 | -0.07992 | 510.521 | 34637.421 | 34126.9 | 421104.2626 | 2021-09-26 | COMPUTE PLATFORM ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | GDS Security | C.2.11.1.13.10 | PAJEVSKI, MICHAEL J | 8103.3989 | -0.01177 | 18473.0376 | 38400.1076 | 19927.07 | 352101.8543 | 2021-09-26 | GDS Security | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | ASEC MAINT | C.2.11.2.05.07 | GIESELMAN, KENNETH G | -24730.5917 | -0.87575 | -41494.0679 | 45494.8621 | 86988.93 | 508947.0742 | 2021-09-26 | ASEC MAINT | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | SEO SECURITY | C.2.11.2.11.03 | PAJEVSKI, MICHAEL J | -1368.0411 | 0.01584 | -1368.0411 | 12298.1289 | 13666.17 | 151431.5478 | 2021-09-26 | SEO SECURITY | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MGSS Configuration M | C.2.12.2.01.04 | NGUYEN, SHAWN N | -3434.4824 | -0.36774 | -3434.4824 | 72081.5076 | 75515.99 | 878325.747 | 2021-09-26 | MGSS Configuration M | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Config MGMT Mainten | C.2.12.2.02.07 | NGUYEN, SHAWN N | 770.9969 | 0.00198 | 192.1369 | 2723.1769 | 2531.04 | 49904.0264 | 2021-09-26 | Config MGMT Mainten | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | I&T VALIDATION | C.2.13.2.04.06 | MARKHAM, SCOTT D | 17074.7981 | 0.80224 | 17074.7981 | 110525.5481 | 93450.75 | 1359690.4658 | 2021-09-26 | I&T VALIDATION | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MGSS PORT CHARGES | C.2.13.2.08.09 | MARKHAM, SCOTT D | 5405.423 | 0 | 5405.423 | 8357.563 | 2952.14 | 108648.354 | 2021-09-26 | MGSS PORT CHARGES | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MM INT & TEST DEP SE | C.2.13.2.17.03 | MARKHAM, SCOTT D | 2431.7979 | 0.05284 | 2431.7979 | 37341.8979 | 34910.1 | 454272.4398 | 2021-09-26 | MM INT & TEST DEP SE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MM DEPLOYMENT ENG | C.2.13.2.18.03 | MARKHAM, SCOTT D | -2158.6683 | -0.05886 | -2158.6683 | 26558.1116 | 28716.78 | 322857.0686 | 2021-09-26 | MM DEPLOYMENT ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MGSS - IMS | C.2.14.2.01.09 | MCCLEARY, JENNIFER M | 10935.0817 | 0.33696 | 10935.0817 | 26959.3917 | 16024.31 | 328206.526 | 2021-09-26 | MGSS - IMS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MM GDS SUPPORT | C.2.14.2.16.09 | O'BRIEN, ROBIN A | 31100.9707 | 1.1948 | -1146.4673 | 63544.0627 | 64690.53 | 750733.9504 | 2021-09-26 | MM GDS SUPPORT | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | SEC PLAN-H/W-LIC | C.2.14.2.21.09 | O'BRIEN, ROBIN A | -5222.0682 | -0.01218 | -5222.0682 | 24659.4118 | 29881.48 | 416981.7955 | 2021-09-26 | SEC PLAN-H/W-LIC | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | SYS ENG SA | C.2.14.2.22.09 | O'BRIEN, ROBIN A | 51543.4744 | 0 | 51543.4744 | 51543.4744 | 0 | 670065.191 | 2021-09-26 | SYS ENG SA | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | AMMOS Deployment in the Cloud | C.2.15.1.12.10 | RADULESCU, COSTIN | 17759.416 | 0.67759 | 17759.416 | 30430.736 | 12671.32 | 369953.7211 | 2021-09-26 | AMMOS Deployment in the Cloud | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | ASEC Impl | C.2.15.1.15.10 | PAJEVSKI, MICHAEL J | 15956.4041 | 0.49184 | 5228.4941 | 17816.8741 | 12588.38 | 219972.9472 | 2021-09-26 | ASEC Impl | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Common Logging Svc Impl | C.2.15.1.16.10 | PAJEVSKI, MICHAEL J | 3384.4089 | 0 | -6729.0588 | 8186.5612 | 14915.62 | 74261.1735 | 2021-09-26 | Common Logging Svc Impl | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | DTN Network Monitor Configuration | C.2.15.1.17.10 | PAJEVSKI, MICHAEL J | 0 | 0 | 8813.8647 | 8813.8647 | 0 | 8813.8647 | 2021-09-26 | DTN Network Monitor Configuration | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | ASIS | C.2.15.2.01.10 | GIESELMAN, KENNETH G | 7132.0269 | -0.06739 | -22301.8574 | 51668.0626 | 73969.92 | 559456.0874 | 2021-09-26 | ASIS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Common Logging Svc | C.2.15.2.06.10 | GIESELMAN, KENNETH G | 3522.7267 | 0 | -6756.3609 | 8159.2691 | 14915.63 | 73906.4227 | 2021-09-26 | Common Logging Svc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | CSE | C.2.15.2.07.10 | GIESELMAN, KENNETH G | 16877.7019 | -0.1084 | 53241.475 | 90015.235 | 36773.76 | 375043.2538 | 2021-09-26 | CSE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MGSS SQA Support | C.2.16.2.13.05 | BOKOR, EVA | -9192.6115 | 1.3037 | -9192.6115 | 37274.8685 | 46467.48 | 453155.7412 | 2021-09-26 | MGSS SQA Support | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MGSS IMP & PLNG | E.1.00.0.00.01 | GUNN, JOHANNA M | 17252.6438 | 0.56321 | 17252.6438 | 71027.3138 | 53774.67 | 863509.3247 | 2021-09-26 | MGSS IMP & PLNG | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MDN MANAGEMENT | G.1.00.0.00.01 | BERRY, DAVID S | 12652.5429 | 0.27461 | 12652.5429 | 30200.4329 | 17547.89 | 378767.7082 | 2021-09-26 | MDN MANAGEMENT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MDN SYS ENG | G.1.00.0.00.03 | GERASIMATOS, DIMITRIOS V | 12135.5163 | 0.41115 | 12135.5163 | 31430.3063 | 19294.79 | 385830.8477 | 2021-09-26 | MDN SYS ENG | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MONTE/MASAR PDM | G.1.00.0.01.01 | EVANS, DR. SCOTT E | -1385.9942 | -0.03029 | -1385.9942 | 31875.0458 | 33261.04 | 388083.423 | 2021-09-26 | MONTE/MASAR PDM | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MDN SOFTWARE ADV-2 | G.2.01.1.06.10 | EVANS, DR. SCOTT E | -23392.3564 | -0.81734 | -23392.3564 | 32902.0336 | 56294.39 | 399998.9388 | 2021-09-26 | MDN SOFTWARE ADV-2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Automated RMM Design & Implemntn | G.2.01.1.12.10 | EVANS, DR. SCOTT E | -3622.8778 | -0.18993 | -3622.8778 | 35118.5822 | 38741.46 | 357013.8905 | 2021-09-26 | Automated RMM Design & Implemntn | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MONTE MAINT | G.2.01.2.02.07 | EVANS, DR. SCOTT E | 20414.1837 | 0.81237 | 20414.1837 | 53342.4137 | 32928.23 | 638747.6801 | 2021-09-26 | MONTE MAINT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MONTE TRAIN & CUST SUPT | G.2.01.2.02.11 | EVANS, DR. SCOTT E | -669.4932 | -0.06314 | 8738.4588 | 23794.9188 | 15056.46 | 35825.2042 | 2021-09-26 | MONTE TRAIN & CUST SUPT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | NAV SW AUTOMA MAINT | G.2.01.2.03.07 | TABER, DR. WILLIAM L | -2385.8441 | -0.11675 | -2385.8441 | 9081.4459 | 11467.29 | 112639.6026 | 2021-09-26 | NAV SW AUTOMA MAINT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Monte/Masar "SparQ" 3D Viz Enh | G.3.01.1.03.10 | EVANS, DR. SCOTT E | 24436.5148 | 0.84047 | 24436.5148 | 24436.5148 | 0 | 297090.7537 | 2021-09-26 | Monte/Masar "SparQ" 3D Viz Enh | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | SPICE MAINT | G.4.01.2.01.07 | ACTON, CHARLES H JR. | 1575.6464 | 0.04452 | 1575.6464 | 1575.6464 | 0 | 20479.6251 | 2021-09-26 | SPICE MAINT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | PLANETARY EPHEMERIS | G.5.01.2.01.09 | PARK, DR. SANG H | 2568.0639 | 0.15461 | 2568.0639 | 55388.2239 | 52820.16 | 737667.9472 | 2021-09-26 | PLANETARY EPHEMERIS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | SATELLITE EPHEMERIS | G.5.02.2.01.09 | PARK, DR. SANG H | -12209.724 | -0.41868 | -12209.724 | 49536.976 | 61746.7 | 697789.4736 | 2021-09-26 | SATELLITE EPHEMERIS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | CMT/AST EPHEMERIS | G.5.03.2.01.09 | PARK, DR. SANG H | 6030.4713 | -0.13362 | 6030.4713 | 65141.1613 | 59110.69 | 908835.6172 | 2021-09-26 | CMT/AST EPHEMERIS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | GRAVITY MODELLING | G.5.04.2.01.09 | PARK, DR. SANG H | -4570.9781 | -0.2297 | -4570.9781 | 20045.0819 | 24616.06 | 321907.4464 | 2021-09-26 | GRAVITY MODELLING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Lunar Conj Assessment | G.6.03.2.02.09 | BERRY, DAVID S | 1256.069 | 0.02548 | 1256.069 | 2489.329 | 1233.26 | 30056.7936 | 2021-09-26 | Lunar Conj Assessment | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | Astrodynamics Tech Infusion | G.7.01.1.01.10 | EVANS, DR. SCOTT E | 3140.6558 | 0.08738 | 3140.6558 | 16454.0958 | 13313.44 | 200030.062 | 2021-09-26 | Astrodynamics Tech Infusion | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 107282 | MPSA MGMT | H.1.00.0.00.01 | CHAFIN, BRIAN G | 13027.6493 | 0.30404 | 13027.6493 | 39572.3492 | 26544.7 | 481093.6144 | 2021-09-26 | MPSA MGMT | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | MGSS SEQ SE | H.1.00.0.00.03 | CHAFIN, BRIAN G | -15796.871 | -0.0278 | -19454.791 | 61591.459 | 81046.25 | 996067.139 | 2021-09-26 | MGSS SEQ SE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | SEQ SUBSYSTEM TEST | H.1.00.0.00.06 | CHAFIN, BRIAN G | 17080.2132 | 0.44132 | 17080.2132 | 69371.2732 | 52291.06 | 846012.5217 | 2021-09-26 | SEQ SUBSYSTEM TEST | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | MPS MAINT NEW | H.1.00.0.00.07 | CHAFIN, BRIAN G | -11120.3484 | -1.1262 | -11120.3484 | 72684.3416 | 83804.69 | 874407.9189 | 2021-09-26 | MPS MAINT NEW | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | Web Int for Plan Maint | H.1.00.2.02.07 | CHAFIN, BRIAN G | 2358.9132 | 0.0848 | 2358.9132 | 2358.9132 | 0 | 28676.644 | 2021-09-26 | Web Int for Plan Maint | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | SOA Rearchitecture | H.2.01.1.05.10 | CHAFIN, BRIAN G | -597.5102 | 0.00987 | -653.8602 | 24485.3398 | 25139.2 | 299996.878 | 2021-09-26 | SOA Rearchitecture | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | Aerie Adv MPS Seq | H.3.01.1.20.10 | CHAFIN, BRIAN G | 4944.5235 | 0.18366 | 4944.5235 | 94516.3735 | 89571.85 | 1119583.9358 | 2021-09-26 | Aerie Adv MPS Seq | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | Spacecraft State Estimation | H.5.01.1.03.10 | CHEUNG, DR. KAR-MING | -969.47 | -0.02531 | -969.47 | 0 | 969.47 | 0 | 2021-09-26 | Spacecraft State Estimation | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | S/C Analysis Maint | H.5.01.2.01.07 | CHEUNG, DR. KAR-MING | 10541.9689 | 0.32193 | 10541.9689 | 24244.9289 | 13702.96 | 294732.705 | 2021-09-26 | S/C Analysis Maint | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 107282 | MCS MGT | J.1.00.0.00.01 | KHAZRA, MOOJAN | -1208.4809 | -0.0917 | -1208.4809 | 31870.819 | 33079.3 | 391555.2394 | 2021-09-26 | MCS MGT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | MCS SYS ENG | J.1.00.0.00.03 | KHAZRA, MOOJAN | -374.6194 | -0.06207 | -374.6194 | 41705.4206 | 42080.04 | 512893.7544 | 2021-09-26 | MCS SYS ENG | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | MCS TEST ENG | J.1.00.0.00.06 | SHAMILIAN, ARSHALUYS | -7685.7476 | -0.38127 | -7685.7476 | 53351.2524 | 61037 | 648616.3191 | 2021-09-26 | MCS TEST ENG | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | MCS SYS LVL MAINT | J.1.00.0.00.07 | KHAZRA, MOOJAN | 2063.8548 | 0.00261 | 2063.8548 | 67245.6148 | 65181.76 | 816956.5888 | 2021-09-26 | MCS SYS LVL MAINT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | MMCS Support | J.1.00.0.00.11 | SHAMILIAN, ARSHALUYS | 4115.2322 | 0.14776 | 4115.2322 | 4115.2322 | 0 | 50020.4298 | 2021-09-26 | MMCS Support | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | Sys Admin & Dep SUPT | J.1.00.0.01.03 | KHAZRA, MOOJAN | 11228.7602 | 0 | 11228.7602 | 26813.2502 | 15584.49 | 321759.0019 | 2021-09-26 | Sys Admin & Dep SUPT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | Chill Mon Rep Dev Testing | J.1.00.1.05.10 | KHAZRA, MOOJAN | 6696.3366 | 0.21524 | 6696.3366 | 8845.3466 | 2149.01 | 27927.2725 | 2021-09-26 | Chill Mon Rep Dev Testing | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | VISTA Maintenance | J.1.00.2.05.07 | KHAZRA, MOOJAN | -105.89 | 0 | -105.89 | 0 | 105.89 | 31528.2354 | 2021-09-26 | VISTA Maintenance | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | Int Command Maint | J.2.02.2.01.07 | KHAZRA, MOOJAN | -1008.6918 | -0.11572 | -1008.6918 | 15951.4282 | 16960.12 | 193931.1079 | 2021-09-26 | Int Command Maint | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | Telemetry&Commanding Closed Loop Test Framework | J.2.07.1.17.10 | KHAZRA, MOOJAN | 0 | 0 | 24940.0583 | 24940.0583 | 0 | 24940.0583 | 2021-09-26 | Telemetry&Commanding Closed Loop Test Framework | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | AMPCS Pass Automation | J.2.07.2.12.07 | KHAZRA, MOOJAN | 1693.7953 | 0.07738 | 1693.7953 | 1693.7953 | 0 | 20604.967 | 2021-09-26 | AMPCS Pass Automation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | TDAC - Maintenance | J.2.16.2.01.07 | KHAZRA, MOOJAN | 1389.2972 | 0.05708 | 1389.2972 | 14737.0272 | 13347.73 | 179161.8349 | 2021-09-26 | TDAC - Maintenance | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | DATA MGT MAINT | J.3.01.2.01.07 | KHAZRA, MOOJAN | 6765.18 | 0.16495 | 6765.18 | 42958 | 36192.82 | 522421.4 | 2021-09-26 | DATA MGT MAINT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | MDMS (DOM Replacement) | J.3.02.1.04.10 | KHAZRA, MOOJAN | 19388.9371 | 0.69638 | 19388.9371 | 32756.0371 | 13367.1 | 400030.0037 | 2021-09-26 | MDMS (DOM Replacement) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 107282 | IDS MGMT | K.1.00.0.01.01 | DAHL, LUKE B | -2636.8335 | -0.14296 | -2636.8335 | 39081.6265 | 41718.46 | 475561.1703 | 2021-09-26 | IDS MGMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | IDS SYS ENG | K.1.00.0.01.03 | TINIO, ADRIAN W | 11143.3678 | 0.3858 | 11143.3678 | 39769.1678 | 28625.8 | 484279.1415 | 2021-09-26 | IDS SYS ENG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | IDS I&T | K.1.00.0.01.06 | LEE, PHAN | -19071.1788 | -0.69971 | -19071.1788 | 34390.7512 | 53461.93 | 418094.497 | 2021-09-26 | IDS I&T | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | SYS SW-HW INF M | K.1.00.0.02.07 | LEUNG, ALEX | 10923.4683 | -0.06386 | 10733.5783 | 41906.6283 | 31173.05 | 522207.8024 | 2021-09-26 | SYS SW-HW INF M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | Sys SW Modernization | K.1.00.0.04.07 | LIU, JEFF Y | -2444.159 | -0.15698 | -139417.499 | 25423.631 | 164841.13 | 318572.0838 | 2021-09-26 | Sys SW Modernization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | SYNOPSIS | K.1.00.1.04.10 | LEUNG, ALEX | -2179.9844 | -0.07011 | -2179.9844 | 5263.2456 | 7443.23 | 63989.5328 | 2021-09-26 | SYNOPSIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | AFIDS Auto Plan Image | K.1.00.1.08.10 | LOGAN, DR. THOMAS L | 6164.8539 | 0.16628 | 6164.8539 | 14014.9538 | 7850.1 | 170991.2087 | 2021-09-26 | AFIDS Auto Plan Image | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | IDS EXP & TAC MAINT | K.1.00.2.01.07 | TINIO, ADRIAN W | 16457.2103 | 0.74917 | 16457.2103 | 53421.3903 | 36964.18 | 649212.0666 | 2021-09-26 | IDS EXP & TAC MAINT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | IOS/SDS Cloud Deployment | K.2.01.1.08.10 | TINIO, ADRIAN W | 23496.6136 | 0.76092 | 23496.6136 | 30638.1836 | 7141.57 | 375088.4143 | 2021-09-26 | IOS/SDS Cloud Deployment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | USER CONSULTANT | K.2.04.2.02.11 | DAHL, LUKE B | 4675.0731 | 0.16534 | 4675.0731 | 5897.2831 | 1222.21 | 71691.0321 | 2021-09-26 | USER CONSULTANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | CARGO | K.3.02.1.02.10 | DAHL, LUKE B | 3177.3681 | 0.08436 | 3177.3681 | 13163.3881 | 9986.02 | 160035.8342 | 2021-09-26 | CARGO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | CCSDS Architecture Support | K.4.01.2.01.03 | DAHL, LUKE B | -6948.9817 | -0.21254 | -2467.3817 | 17694.7283 | 20162.11 | 175193.129 | 2021-09-26 | CCSDS Architecture Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | Data Order via Uncertainty Est | K.4.02.1.01.10 | LIUKIS, MARIA | -9879.7195 | -0.56231 | -9879.7195 | 12337.5205 | 22217.24 | 149980.5248 | 2021-09-26 | Data Order via Uncertainty Est | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | Sim Local and Map for Img Surfacing | K.4.02.1.04.10 | DAHL, LUKE B | 13008.2547 | 0.52289 | 13008.2547 | 14062.5047 | 1054.25 | 170976.2253 | 2021-09-26 | Sim Local and Map for Img Surfacing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 107282 | RELAY SYS ENG | M.1.00.0.01.03 | CALL, JARED A | -10268.0257 | -0.46043 | -10268.0257 | 17689.5943 | 27957.62 | 215053.7744 | 2021-09-26 | RELAY SYS ENG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 107282 | RELAY I&T | M.1.00.0.01.06 | CALL, JARED A | -2403.2747 | -0.41856 | -2403.2747 | 29486.4153 | 31889.69 | 358471.3432 | 2021-09-26 | RELAY I&T | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 107282 | RELAY MAINT | M.1.00.0.01.07 | CALL, JARED A | -7089.6151 | -0.31167 | -7089.6151 | 12158.9549 | 19248.57 | 148040.4412 | 2021-09-26 | RELAY MAINT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 107282 | Program Office | N.1.01.3.01.01 | WYATT, E JAY | 1114.7259 | 0.03584 | 1114.7259 | 14551.4559 | 13436.73 | 184957.6806 | 2021-09-26 | Program Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 107282 | AMMOS DTN PILOT IMP | N.1.02.3.01.10 | TORGERSON, JORDAN L | 11323.1036 | 0.42693 | 16166.6349 | 24649.7749 | 8483.14 | 229809.7323 | 2021-09-26 | AMMOS DTN PILOT IMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 107282 | Next Gen Plan & Seq | N.1.03.3.01.10 | CHIEN, DR. STEVE A | 3089.872 | 0.30616 | 3089.872 | 7503.682 | 4413.81 | 150176.0536 | 2021-09-26 | Next Gen Plan & Seq | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 107282 | Low-Thrust Opt | N.1.04.3.01.10 | ANDERSON, DR. RODNEY L | -7479.6082 | -0.26553 | -7479.6082 | 9239.6718 | 16719.28 | 112937.6871 | 2021-09-26 | Low-Thrust Opt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 107282 | Interactive Data Vis | N.1.04.3.02.10 | STUART, JEFFREY R | -16330.4793 | -0.17324 | -32807.4993 | 4683.6107 | 37491.11 | 150005.2724 | 2021-09-26 | Interactive Data Vis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 107282 | DATA DRIVEN EXPLORER | N.1.05.3.01.10 | TAPELLA, ROBERT K | 29.648 | 0.05439 | 29.648 | 15020.008 | 14990.36 | 164980.4402 | 2021-09-26 | DATA DRIVEN EXPLORER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 107282 | Patch | N.1.05.3.02.10 | AYOUB, FRANCOIS | 5174.1007 | 0.2112 | 5174.1007 | 5174.1007 | 0 | 11037.8991 | 2021-09-26 | Patch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 107282 | AUTO ARCH & FLIGHT-GROUND INTE. | N.1.06.3.01.10 | WYATT, E JAY | -3178.2252 | -0.0277 | -3178.2252 | 12189.5648 | 15367.79 | 155989.5087 | 2021-09-26 | AUTO ARCH & FLIGHT-GROUND INTE. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0