## Sheet1
Status Date: 10/25/20
MGSS Status Indicator | ID | WBS | #CAM | Task Name | % Complete | Duration | Start | Act/Est Start | Finish | Act/Est Finish | Baseline Finish | Explanation of Changes from Previous Month
| 1 | REF | REF | Technology | 82% | 1664 d | 2014-06-30 | 2014-06-30 | 2021-11-16 |  | 2021-11-16
| 2 | REF | REF | Archive | 100% | 1231 d | 2014-06-30 | 2014-06-30 | 2019-12-16 | 2019-12-16 | NA
| 306 | 01.01.02 | BCastano | Autonomy Evaluation | 100% | 165 d | 2019-11-14 | 2019-11-14 | 2020-08-07 | 2020-08-07 | 2020-01-23
| 309 | REF | LTorgerson | AMMOS DTN Pilot Implementation | 94% | 449 d | 2019-09-30 | 2019-09-30 | 2021-09-23 |  | 2021-09-23
3 | 310 | N.1.02.3.01.10 | LTorgerson | DTN File Sync to MITRE/MSFC | 0% | 1 d | 2020-12-30 |  | 2020-12-30 |  | 2019-11-01
0 | 311 | 02.01.12 | LTorgerson | ION Config tool to AMMOS tookit | 100% | 118 d | 2020-04-15 | 2020-04-15 | 2020-09-25 | 2020-09-25 | 2019-12-20
0 | 312 | 02.01.12 | LTorgerson | DTN MCC Conops - draft 1 | 100% | 1 d | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30
3 | 313 | N.1.02.3.01.10 | LTorgerson | DTN File Sync to AMMOS | 0% | 1 d | 2020-10-30 |  | 2020-10-30 |  | 2020-06-29
3 | 314 | N.1.02.3.01.10 | LTorgerson | DTN MCC Conops - draft 2 | 0% | 1 d | 2020-10-30 |  | 2020-10-30 |  | 2020-08-31
| 315 | REF | LTorgerson | File Synch Software | 91% | 248 d | 2019-09-30 | 2019-09-30 | 2020-10-30 |  | 2020-03-16
0 | 316 | 02.01.12 | LTorgerson | Consider Test Results and Plan Future Development | 100% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | 2020-09-24 | 2020-03-16
2 | 317 | N.1.02.3.01.10 | LTorgerson | Consider Test Results and Plan Future Development - FY21 remaining effort | 0% | 23 d | 2020-09-28 |  | 2020-10-30 |  | NA
| 318 | 02.01.12 | LTorgerson | DTN-AMP GUI for NM&C | 100% | 208 d | 2019-09-30 | 2019-09-30 | 2020-08-27 | 2020-08-27 | 2020-09-30
3 | 326 | N.1.02.3.01.10 | LTorgerson | Reports and Activities | 0% | 201 d | 2020-11-02 |  | 2021-09-23 |  | 2021-09-23
3 | 327 | N.1.02.3.01.10 | LTorgerson | Set up repository for AMMOS DTN tools and reports | 0% | 1 d | 2020-11-02 |  | 2020-11-02 |  | 2020-11-02
3 | 328 | N.1.02.3.01.10 | LTorgerson | Brief DTN Network Conops to AMMOS, MAROS & other ops personnel - Initial | 0% | 1 d | 2020-11-16 |  | 2020-11-16 |  | 2020-11-16
3 | 329 | N.1.02.3.01.10 | LTorgerson | Brief DTN Network Conops to AMMOS, MAROS & other ops personnel - Final | 0% | 1 d | 2021-05-10 |  | 2021-05-10 |  | 2021-05-10
3 | 330 | N.1.02.3.01.10 | LTorgerson | Initial MOS-DSN-DTN scheduling coordination reports | 0% | 1 d | 2021-03-29 |  | 2021-03-29 |  | 2021-03-29
3 | 331 | N.1.02.3.01.10 | LTorgerson | Final MOS-DSN-DTN scheduling coordination reports | 0% | 1 d | 2021-09-23 |  | 2021-09-23 |  | 2021-09-23
| 332 | N.1.02.3.01.10 | LTorgerson | DTN Software Tools for AMMOS | 0% | 184 d | 2020-11-30 |  | 2021-09-23 |  | 2021-09-23
3 | 333 | N.1.02.3.01.10 | LTorgerson | DTN-enabled AIT - Prelim | 0% | 1 d | 2020-12-28 |  | 2020-12-28 |  | 2020-12-28
3 | 334 | N.1.02.3.01.10 | LTorgerson | DTN-enabled AIT - Final | 0% | 1 d | 2021-06-14 |  | 2021-06-14 |  | 2021-06-14
| 335 | N.1.02.3.01.10 | LTorgerson | DTN network model and ION configuration tools - Milestones | 0% | 184 d | 2020-11-30 |  | 2021-09-23 |  | 2021-09-23
3 | 336 | N.1.02.3.01.10 | LTorgerson | DTN network model and ION configuration tools - #1 | 0% | 0 d | 2020-11-30 |  | 2020-11-30 |  | 2020-11-30
3 | 337 | N.1.02.3.01.10 | LTorgerson | DTN network model and ION configuration tools - #2 | 0% | 0 d | 2021-03-29 |  | 2021-03-29 |  | 2021-03-29
3 | 338 | N.1.02.3.01.10 | LTorgerson | DTN network model and ION configuration tools - #3 | 0% | 0 d | 2021-06-28 |  | 2021-06-28 |  | 2021-06-28
3 | 339 | N.1.02.3.01.10 | LTorgerson | DTN network model and ION configuration tools - #4 | 0% | 0 d | 2021-09-23 |  | 2021-09-23 |  | 2021-09-23
3 | 340 | N.1.02.3.01.10 | LTorgerson | DTN File Synch Software alpha testing complete | 0% | 1 d | 2020-12-28 |  | 2020-12-28 |  | 2020-12-28
3 | 341 | N.1.02.3.01.10 | LTorgerson | DTN File Synch demo and publish in GITHUB | 0% | 1 d | 2021-02-22 |  | 2021-02-22 |  | 2021-02-22
| 342 | AMES - BYPASS | LTorgerson | AMES Deep Learning & Precursor Identification Tasks | 100% | 225 d | 2019-09-27 | 2019-09-27 | 2020-09-25 | 2020-09-25 | 2020-09-25
| 348 | REF | SChien | Next Gen Plan & Seq | 30% | 439 d | 2019-10-15 | 2019-10-15 | 2021-09-23 |  | 2021-09-23
0 | 349 | 03.01.13 | SChien | 1st Qtr: Complete design for 2 incremental propagation timeline types | 100% | 0 d | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-12-27
0 | 350 | 03.01.13 | SChien | 2nd Qtr: Complete software prototype for 2 incremental propagation timeline types | 100% | 60 d | 2019-10-15 | 2019-10-15 | 2020-01-13 | 2020-01-13 | 2020-03-27
0 | 351 | 03.01.13 | SChien | COVID IMPACT**CANCELED** 3rd Qtr: Report on incremental propagation timeline types at peer reviewed workshop or conference | 100% | 105 d | 2020-01-14 | 2020-01-14 | 2020-06-29 | 2020-06-29 | 2020-06-26
0 | 353 | 03.01.13 | SChien | Demonstrate preliminary prototype of state-base campaign scheduling | 100% | 0 d | 2020-09-15 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 2020-09-15
2 | 354 | N.1.03.3.01.10 | SChien | FY21 Q1: frequency / periodicity rules, eg "there exists an instance of A every D seconds" | 0% | 58 d | 2020-09-28 |  | 2020-12-30 |  | 2020-12-30
2 | 355 | N.1.03.3.01.10 | SChien | FY21 Q1: cardinality / multiplicity rules, eg "there exist N instances of A within time range [T0,T1]" | 0% | 58 d | 2020-09-28 |  | 2020-12-30 |  | 2020-12-30
3 | 356 | N.1.03.3.01.10 | SChien | FY21 Q2: ordering and mutex rules, eg "there exists a unique A before each B" "there exists some A before every B" "there does not exist any instance of A and B that occur simultaneously" | 0% | 55 d | 2021-01-04 |  | 2021-03-31 |  | 2021-03-31
3 | 357 | N.1.03.3.01.10 | SChien | FY21 Q2: state transition rule, eg "an A exists whenever state S changes from V0 to V1" | 0% | 55 d | 2021-01-04 |  | 2021-03-31 |  | 2021-03-31
3 | 358 | N.1.03.3.01.10 | SChien | FY21 Q3: aggregation rules, eg "the sum of all durations of instances of A within time range [T0,T1] is at least D seconds" | 0% | 58 d | 2021-04-01 |  | 2021-06-30 |  | 2021-06-30
3 | 359 | N.1.03.3.01.10 | SChien | FY21 Q4: composition of rules/combinations of other rules, eg "there exist N instances of A within each period that state S has value V0" | 0% | 53 d | 2021-07-01 |  | 2021-09-23 |  | 2021-09-23
3 | 360 | N.1.03.3.01.10 | SChien | FY21 Q4: paper submitted to peer reviewed venue on above | 0% | 53 d | 2021-07-01 |  | 2021-09-23 |  | 2021-09-23
| 361 | REF | RAnderson | Low Thrust Option | 38% | 482 d | 2019-09-30 | 2019-09-30 | 2021-11-16 |  | 2021-11-16
0 | 362 | 04.01.13 | RAnderson | Annual Report | 100% | 1 d | 2019-11-15 | 2019-11-15 | 2019-11-15 | 2019-11-15 | 2019-11-15
0 | 363 | 04.01.13 | RAnderson | Perform detailed DV and topology comparison of optimal trajectories for complex trajectory combinations | 100% | 39 d | 2019-10-01 | 2019-10-01 | 2019-12-02 | 2019-12-02 | 2019-12-02
0 | 364 | 04.01.13 | RAnderson | Implement low-thrust transfers directly using low-energy components including three-dimensional orbits | 100% | 63 d | 2019-09-30 | 2019-09-30 | 2020-01-10 | 2020-01-10 | 2020-01-10
0 | 365 | 04.01.13 | RAnderson | Implement low-thrust transfers directly using low-energy components including invariant manifolds | 100% | 88 d | 2020-01-13 | 2020-01-13 | 2020-06-01 | 2020-06-01 | 2020-06-01
0 | 366 | 04.01.13 | RAnderson | Draft of Conference Paper | 100% | 1 d | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-05-15
0 | 367 | 04.01.13 | RAnderson | Conference Paper (Spring 2020) | 100% | 1 d | 2020-08-03 | 2020-08-03 | 2020-08-03 | 2020-08-03 | 2020-06-01
0 | 368 | 04.01.13 | RAnderson | Implement low-thrust transfers directly using low-energy using invariant manifold components across energies | 100% | 81 d | 2020-05-01 | 2020-05-01 | 2020-09-04 | 2020-09-04 | 2020-07-01
0 | 369 | 04.01.13 | RAnderson | Draft of conference paper | 100% | 1 d | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-07-15
0 | 370 | 04.01.13 | RAnderson | Conference Paper (Summer 2020) | 100% | 1 d | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-08-03
0 | 371 | 04.01.13 | RAnderson | Study the use of nearly periodic orbit components in low-thrust transfer solutions | 100% | 55 d | 2020-07-01 | 2020-07-01 | 2020-09-24 | 2020-09-24 | 2020-09-24
2 | 372 | N.1.04.3.01.10 | RAnderson | Study the use of nearly periodic orbit components in low-thrust transfer solutions - (remaining FY21 effort) | 0% | 27 d | 2020-09-28 |  | 2020-11-05 |  | 2020-11-05
3 | 373 | N.1.04.3.01.10 | RAnderson | Annual Report | 0% | 0 d | 2020-11-16 |  | 2020-11-16 |  | 2020-11-16
2 | 374 | N.1.04.3.01.10 | RAnderson | Survey foundational machine learning methods for orbit transfer approach including GPUs | 0% | 154 d | 2020-09-28 |  | 2021-06-03 |  | 2021-06-03
3 | 375 | N.1.04.3.01.10 | RAnderson | Draft of Conference Paper (FY21) | 0% | 1 d | 2021-06-01 |  | 2021-06-01 |  | 2021-06-01
3 | 376 | N.1.04.3.01.10 | RAnderson | Conference Paper (Spring 2021) | 0% | 1 d | 2021-06-15 |  | 2021-06-15 |  | 2021-06-15
3 | 377 | N.1.04.3.01.10 | RAnderson | Combine different orbit type components for complete solutions | 0% | 150 d | 2020-12-01 |  | 2021-08-02 |  | 2021-06-01
3 | 378 | N.1.04.3.01.10 | RAnderson | Draft of Conference Paper (FY21) | 0% | 1 d | 2021-08-02 |  | 2021-08-02 |  | 2021-08-02
3 | 379 | N.1.04.3.01.10 | RAnderson | Conference Paper (Summer 2021) | 0% | 1 d | 2021-08-16 |  | 2021-08-16 |  | 2021-08-16
3 | 380 | N.1.04.3.01.10 | RAnderson | Implement more realistic trajectory models using the GPU | 0% | 138 d | 2021-02-01 |  | 2021-09-07 |  | 2021-09-07
3 | 381 | N.1.04.3.01.10 | RAnderson | Complete process for generating complete low-thrust solutions for sample scenarios | 0% | 73 d | 2021-06-01 |  | 2021-09-23 |  | 2021-09-23
3 | 382 | N.1.04.3.01.10 | RAnderson | Complete search algorithms and algorithm document | 0% | 0 d | 2021-09-23 |  | 2021-09-23 |  | 2021-09-27
3 | 383 | N.1.04.3.01.10 | RAnderson | Final Report | 0% | 0 d | 2021-11-16 |  | 2021-11-16 |  | 2021-11-16
| 384 | REF | JStuart | Interactive Data Vis | 45% | 449 d | 2019-09-30 | 2019-09-30 | 2021-09-23 |  | 2021-09-23
0 | 385 | 04.01.14 | JStuart | Transition AR Software ('Sagan') to multi-mission funding support | 100% | 57 d | 2019-09-30 | 2019-09-30 | 2019-12-31 | 2019-12-31 | 2019-12-31
3 | 387 | N.1.04.3.02.10 | JStuart | Transition Orbit Determination Software ('OD-D') to multi-mission funding support - FY21 | 0% | 52 d | 2020-12-01 |  | 2021-02-25 |  | 2021-02-25
| 388 | REF | JStuart | Development of General Purpose VR/AR Tool ('Sagan') | 35% | 449 d | 2019-09-30 | 2019-09-30 | 2021-09-23 |  | 2021-09-23
0 | 389 | 04.01.14 | JStuart | LOE: Non mission-specific enhancements to AR and web interface | 100% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | 2020-09-24 | 2019-12-31
3 | 391 | N.1.04.3.02.10 | JStuart | LOE: Non mission-specific enhancements to AR and web interface | 9% | 224 d | 2020-09-28 | 2020-09-28 | 2021-09-23 |  | 2021-09-23
2 | 392 | N.1.04.3.02.10 | JStuart | Support Europa Clipper delta-CDR | 0% | 53 d | 2020-09-28 |  | 2020-12-21 |  | 2020-12-21
2 | 393 | N.1.04.3.02.10 | JStuart | Support Trident Discovery Site Visit | 0% | 36 d | 2020-09-28 |  | 2020-11-19 |  | 2020-11-19
2 | 394 | N.1.04.3.02.10 | JStuart | Support SunRISE SRR / mission development | 0% | 164 d | 2020-09-28 |  | 2021-06-21 |  | 2021-06-21
| 395 | REF | JStuart | Sustained Development of Orbit Determination Dashboard (OD-D) | 55% | 449 d | 2019-09-30 | 2019-09-30 | 2021-09-23 |  | 2021-09-23
0 | 396 | 04.01.14 | JStuart | LOE: Minor bug fixes and enhancements as users request | 100% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | 2020-09-24 | 2019-12-31
3 | 397 | N.1.04.3.02.10 | JStuart | LOE: Minor bug fixes and enhancements as users request | 9% | 224 d | 2020-09-28 | 2020-09-28 | 2021-09-23 |  | 2021-09-23
| 398 | 04.01.14 | JStuart | Expansion of Monte Carlo Analysis Tool to maneuver planning (and other statistical cases) | 100% | 48 d | 2019-09-30 | 2019-09-30 | 2019-12-13 | 2019-12-13 | 2020-02-27
| 403 | REF | JStuart | Development of Monte/SparQ library for mission-specific visual analysis environments | 58% | 389 d | 2019-09-30 | 2019-09-30 | 2021-06-21 |  | 2020-10-30
0 | 404 | 04.01.14 | JStuart | Completion of prototype cases for VIVID lab presentation | 100% | 22 d | 2019-09-30 | 2019-09-30 | 2019-10-31 | 2019-10-31 | 2019-10-31
0 | 405 | 04.01.14 | JStuart | Synthesize most common use cases / graphics among MDNav users | 100% | 203 d | 2019-11-01 | 2019-11-01 | 2020-09-24 | 2020-09-24 | 2019-12-31
2 | 406 | N.1.04.3.02.10 | JStuart | Synthesize most common use cases / graphics among MDNav users - FY21 | 0% | 23 d | 2020-09-28 |  | 2020-10-30 |  | 2020-10-30
3 | 407 | N.1.04.3.02.10 | JStuart | Development of API / library of functions for common use cases | 0% | 141 d | 2020-11-02 |  | 2021-06-21 |  | 2020-09-24
| 408 | N.1.04.3.02.10 | JStuart | Quantitative User Analysis | 0% | 93 d | 2021-01-04 |  | 2021-05-28 |  | 2020-05-29
3 | 409 | N.1.04.3.02.10 | JStuart | Definition of metrics and experiment design | 0% | 17 d | 2021-01-04 |  | 2021-01-28 |  | 2020-01-30
3 | 410 | N.1.04.3.02.10 | JStuart | User interviews and tests | 0% | 38 d | 2021-02-01 |  | 2021-03-31 |  | 2020-03-31
3 | 411 | N.1.04.3.02.10 | JStuart | Quantitative analysis & preparation for publication | 0% | 38 d | 2021-04-01 |  | 2021-05-28 |  | 2020-05-29
| 412 | 04.01.14 | JStuart | Continued development of Porter (Manuever Analysis Tool for MONTE LAMBIC) | 69% | 167 d | 2020-06-01 | 2020-06-01 | 2021-02-25 |  | 2020-09-24
0 | 413 | 04.01.14 | JStuart | Intern co-projects (one MDNav, one HCI) to continue dashboard development | 100% | 59 d | 2020-06-01 | 2020-06-01 | 2020-08-31 | 2020-08-31 | 2020-08-31
0 | 414 | 04.01.14 | JStuart | Interns refreshed on status of initial prototype & address initial "to-dos" from end of previous development | 100% | 31 d | 2020-06-01 | 2020-06-01 | 2020-07-16 | 2020-07-16 | 2020-07-16
0 | 415 | 04.01.14 | JStuart | Follow-on interviews and iterations of prototype | 100% | 28 d | 2020-07-20 | 2020-07-20 | 2020-08-31 | 2020-08-31 | 2020-08-31
3 | 416 | N.1.04.3.02.10 | JStuart | Identify follow-on funding for sustained development (as appropriate) | 0% | 52 d | 2020-12-01 |  | 2021-02-25 |  | 2020-09-24
| 417 | N.1.04.3.02.10 | JStuart | Sustained Development of Porter, maneuver analysis tool | 0% | 93 d | 2020-09-28 |  | 2021-03-01 |  | 2021-03-01
2 | 418 | N.1.04.3.02.10 | JStuart | Intern co-projects (one MDNav, one HCI) to prototype Porter | 0% | 36 d | 2020-09-28 |  | 2020-11-19 |  | 2020-11-19
3 | 419 | N.1.04.3.02.10 | JStuart | Identify follow-on funding for sustained development (as appropriate) | 0% | 35 d | 2021-01-04 |  | 2021-03-01 |  | 2021-03-01
0 | 420 | 04.01.14 | JStuart | Presentation at Conference (SciPy, AAS, Viz, etc.) | 100% | 59 d | 2020-06-01 | 2020-06-01 | 2020-08-31 | 2020-08-31 | 2020-08-31
| 421 | N.1.04.3.02.10 | JStuart | Identify user needs and initial development of new prototype related to optimization | 0% | 76 d | 2021-02-01 |  | 2021-05-28 |  | 2021-05-28
3 | 422 | N.1.04.3.02.10 | JStuart | Intern co-projects (one MDNav, one HCI) to prototype rajectory optimization dashboard | 0% | 58 d | 2021-02-01 |  | 2021-04-30 |  | 2021-04-30
3 | 423 | N.1.04.3.02.10 | JStuart | First round of interviews and development of initial prototype | 0% | 17 d | 2021-02-01 |  | 2021-02-25 |  | 2021-02-25
3 | 424 | N.1.04.3.02.10 | JStuart | Follow-on interviews and iterations of prototype | 0% | 41 d | 2021-03-01 |  | 2021-04-30 |  | 2021-04-30
3 | 425 | N.1.04.3.02.10 | JStuart | Identify follow-on funding for sustained development (as appropriate) | 0% | 18 d | 2021-05-03 |  | 2021-05-28 |  | 2021-05-28
3 | 426 | N.1.04.3.02.10 | JStuart | Presentation at Conference (SciPy, AAS, Viz, etc.) | 0% | 76 d | 2021-05-03 |  | 2021-08-31 |  | 2021-08-31
| 427 | REF | JLightholder | CODEX - Complex Data Explorer | 54% | 448 d | 2019-10-01 | 2019-10-01 | 2021-09-23 |  | 2021-09-23
0 | 428 | 05.01.13 | JLightholder | Design and Implement "Data Quality Scan" User Interface | 100% | 62 d | 2019-10-01 | 2019-10-01 | 2019-12-31 | 2019-12-31 | 2019-12-31
0 | 429 | 05.01.13 | JLightholder | Feature Bar Extension to Support Multiple Interaction Windows | 100% | 37 d | 2020-01-02 | 2020-01-02 | 2020-02-25 | 2020-02-25 | 2020-02-28
0 | 430 | 05.01.13 | JLightholder | Extend Server Data Reader Capabilities to for Additional Data Types | 100% | 26 d | 2020-02-26 | 2020-02-26 | 2020-04-01 | 2020-04-01 | 2020-04-15
0 | 431 | 05.01.13 | JLightholder | Extend Runtime Prediction Model to Support Features/Samples in Calculation | 100% | 10 d | 2020-03-02 | 2020-03-02 | 2020-03-13 | 2020-03-13 | 2020-05-15
0 | 432 | 05.01.13 | JLightholder | Design and Implement "Model Training" User Interface | 100% | 13 d | 2020-03-16 | 2020-03-16 | 2020-04-01 | 2020-04-01 | 2020-06-15
0 | 433 | 05.01.13 | JLightholder | Enable Session Saving / Loading | 100% | 55 d | 2020-04-15 | 2020-04-15 | 2020-07-01 | 2020-07-01 | 2020-07-31
0 | 434 | 05.01.13 | JLightholder | Enable Data / Code / Selection / Feature Export | 100% | 36 d | 2020-07-01 | 2020-07-01 | 2020-08-20 | 2020-08-20 | 2020-08-25
0 | 435 | 05.01.13 | JLightholder | Advanced User Guidance Through Dynamic Error Reporting | 100% | 22 d | 2020-08-21 | 2020-08-21 | 2020-09-22 | 2020-09-22 | 2020-09-25
2 | 436 | N.1.05.3.01.10 | JLightholder | Formalize user-facing data-science and ML content: guidance, interface optimizations, simple deployment/installation | 50% | 33 d | 2020-10-01 | 2020-10-01 | 2020-11-19 | 2020-12-01 | 2020-11-19 | Some workforce vacation; may face additional delays if some server issues (not managed by our team) cannot be worked out; we have worked out some installation problems that will make CODEX easier to install even if the server is delayed
3 | 437 | N.1.05.3.01.10 | JLightholder | Data scaling to allow broad views of large data sets and detailed analysis of smaller subsets | 10% | 23 d | 2020-11-23 | 2020-10-01 | 2021-01-04 | 2021-01-04 | 2021-01-04 | Work on scaling data-size more effectiely has started
3 | 438 | N.1.05.3.01.10 | JLightholder | Use selections to restrict the scope of analysis (“this is good data”) | 0% | 17 d | 2021-01-05 |  | 2021-02-01 |  | 2021-02-01
3 | 439 | N.1.05.3.01.10 | JLightholder | Selection- and Feature-math | 0% | 17 d | 2021-02-02 |  | 2021-03-01 |  | 2021-03-01
3 | 440 | N.1.05.3.01.10 | JLightholder | ML to anticipate upcoming problems based on unusual new time-series trends using active labeling (“More like this”) | 0% | 59 d | 2021-03-02 |  | 2021-06-01 |  | 2021-06-01
3 | 441 | N.1.05.3.01.10 | JLightholder | Linking between algorithms and plots (e.g., 1. find correlation 2. use those correlations to visualize unusual events in a time series plot) | 0% | 38 d | 2021-06-02 |  | 2021-08-02 |  | 2021-08-02
3 | 442 | N.1.05.3.01.10 | JLightholder | Improved regression with sensitivity analysis | 0% | 20 d | 2021-08-03 |  | 2021-09-01 |  | 2021-09-01
3 | 443 | N.1.05.3.01.10 | JLightholder | Improved understanding through Feature importance | 0% | 14 d | 2021-09-02 |  | 2021-09-23 |  | 2021-09-23
| 444 | 05.01.14 | LDahl | PATCH | 100% | 221 d | 2019-10-04 | 2019-10-04 | 2020-09-24 | 2020-09-24 | 2020-09-30
0 | 445 | 05.01.14 | LDahl | Identify appropriate photclinometry model for surface use | 100% | 44 d | 2019-10-04 | 2019-10-04 | 2019-12-13 | 2019-12-13 | 2019-12-13
0 | 446 | 05.01.14 | LDahl | Determine how to constrain PC using correlation results | 100% | 82 d | 2019-12-16 | 2019-12-16 | 2020-04-28 | 2020-04-28 | 2020-02-13
0 | 447 | 05.01.14 | LDahl | Implement photoclinometry model with correlation constraints | 100% | 93 d | 2020-02-18 | 2020-02-18 | 2020-07-10 | 2020-07-10 | 2020-04-15
0 | 448 | 05.01.14 | LDahl | Evaluate results against existing products | 100% | 39 d | 2020-07-27 | 2020-07-27 | 2020-09-24 | 2020-09-24 | 2020-08-31
0 | 449 | 05.01.14 | LDahl | Write report detailing performance of algorithm | 100% | 17 d | 2020-08-31 | 2020-08-31 | 2020-09-24 | 2020-09-24 | 2020-09-30
| 450 | N.1.06.3.01.10 | Schung | Autonomy Architecture and Flight-Ground Interface | 0% | 224 d | 2020-09-28 |  | 2021-09-23 |  | 2021-09-23
2 | 451 | N.1.06.3.01.10 | Schung | Qtr1: Determine the representative future autonomous system concept/architecture and AMMOS that will be the basis for the flight-ground interface architecture | 0% | 58 d | 2020-09-28 |  | 2020-12-30 |  | 2020-12-30
2 | 452 | N.1.06.3.01.10 | Schung | Qtr1: Develop initial logical model of flight-ground interface based on a preliminary vision for the future autonomous system | 0% | 58 d | 2020-09-28 |  | 2020-12-30 |  | 2020-12-30
3 | 453 | N.1.06.3.01.10 | Schung | Qtr2: Develop draft logical model of flight-ground interface based on other NASA Center’s inputs | 0% | 55 d | 2021-01-04 |  | 2021-03-31 |  | 2021-03-31
3 | 454 | N.1.06.3.01.10 | Schung | Qtr3: Prototype flight-ground interface | 0% | 58 d | 2021-04-01 |  | 2021-06-30 |  | 2021-06-30
3 | 455 | N.1.06.3.01.10 | Schung | Qtr4: Develop final logical model of flight-ground interface incorporating the lessons learned from the prototyping effort | 0% | 53 d | 2021-07-01 |  | 2021-09-23 |  | 2021-09-23