## Sheet1
Plans vs Actuals - Financial Summary as of Complete Month ($K)
Time run: 11/10/2020 9:26:48 AM
Account Number | Project Name | Task Name | CAM/Task Manager Name | Cognizant Task Org | Task Start Date | Task Completion Date | FY Burdened Rptg Cost Plan | YTD Burdened Rptg Costs Plan | YTD Burdened Rptg Costs Actual | YTD Burdened Rptg Costs Variance | YTD FTE Average Plan | YTD FTE Average Actual | YTD FTE Average Variance | Burdened Encumbrance Balance | Burdened Service Encumbrance Balance
107282 - N.1.05.3.01.10 | AMMOS | DATA DRIVEN EXPLORER | TAPELLA, ROBERT K | 398H | 2020-09-28 | 2021-09-26 | 164.9804 | 15.02 | 0 | 15.02 | 0.636 | 0 | 0.636 | 0 | 0
107282 - N.1.05.3.01.10.A | AMMOS | DATA DRIVEN EXPLORER | TAPELLA, ROBERT K | 398H | 2020-09-28 | 2021-09-26 | 0 | 0 | 14.9904 | -14.9904 | 0 | 0.5816 | -0.5816 | 0 | 0
Grand Total | [6 empty] | 164.9804 | 15.02 | 14.9904 | 0.029648 | 0.636 | 0.5816 | 0.054395 | 0 | 0