## Sheet1
FY20 Schedule Planning
(Note: Implemenations Scheduled through 6-Year Plan Completion Date)
ID | #Project # | #WBS | #CAM | Task Name | Duration | Start | Finish | Deadline | Predecessors ID # or Task Name | Successors ID # or Task Name | Notes/Comments
1 |  |  |  | Design and Implement "Data Quality Scan" User Interface | 90 | 2019-10-01 | 2020-01-01 | 2019-01-20 | N/A | N/A
2 |  |  |  | Feature Bar Extension to Support Multiple Interaction Windows | 60 | 1/1/120 | 2020-03-01 | 2020-03-30 | N/A | N/A
3 |  |  |  | Extend Server Data Reader Capabilities to for Additional Data Types | 45 | 2020-03-01 | 2020-04-15 | 2020-05-01 | N/A | N/A
4 |  |  |  | Extend Runtime Prediction Model to Support Features/Samples in Calculation | 30 | 2020-04-15 | 2020-05-15 | 2020-05-30 | N/A | N/A
5 |  |  |  | Design and Implement "Model Training" User Interface | 30 | 2020-05-15 | 2020-06-15 | 2019-07-20 | N/A | N/A
6 |  |  |  | Enable Session Saving / Loading | 45 | 2020-06-15 | 2020-08-01 | 2020-08-25 | N/A | N/A
7 |  |  |  | Enable Data / Code / Selection / Feature Export | 25 | 2020-08-01 | 2020-07-25 | 2020-09-25 | N/A | N/A
8 |  |  |  | Advanced User Guidance Through Dynamic Error Reporting | 40 | 2020-07-25 | 2020-09-25 | 2020-09-25 | N/A | N/A