## Sheet1
Status Date: 8/23/19
MGSS Status Indicator | ID | WBS | #CAM | Task Name | % Complete | Duration | Start | Act/Est Start | Finish | Act/Est Finish | Baseline Finish | Explanation of Changes from Previous Month
| 1 | REF |  | Technology | 87% | 1439 d | 2014-06-30 | 2014-06-30 | 2020-11-16 | NA | 2017-12-22
| 2 | REF |  | FY17 | 100% | 804 d | 2014-06-30 | 2014-06-30 | 2018-01-26 | 2018-01-26 | 2017-12-22
| 132 | REF |  | FY18 | 100% | 302 d | 2017-09-25 | 2017-09-25 | 2019-01-29 | 2019-01-29 | 2018-11-16
| 221 | REF |  | FY19 | 65% | 619 d | 2017-12-29 | 2017-12-29 | 2020-09-25 | NA | 2020-09-25
| 222 | 106409-01.01.01.A | Randerson | Low Thrust Option | 72% | 256 d | 2018-10-01 | 2018-10-01 | 2019-11-15 | NA | 2019-11-15
0 | 223 | 106409-01.01.01.A | RAnderson | Perform Comparison of low-thrust solutions to optimal impulsive low-energy solutions across design space | 100% | 110 d | 2018-10-01 | 2018-10-01 | 2019-03-28 | 2019-03-28 | 2018-10-29
0 | 224 | 106409-01.01.01.A | RAnderson | Computation of low-thrust/low-energy results for more complex multi-body orbits to synthesize for search methodologies | 100% | 140 d | 2018-10-01 | 2018-10-01 | 2019-05-15 | 2019-05-15 | 2018-10-30
1 | 225 | 106409-01.01.01.A | RAnderson | Compute low-thrust solutions between complex combinations of three-body orbits using low-energy solutions | 90% | 190 d | 2018-10-01 | 2018-10-01 | 2019-08-05 | NA | 2019-04-15
2 | 228 | 106409-01.01.01.A | RAnderson | Perform in-depth comparison of DV requirements of optimal low-energy vs. low-thrust trajectories | 35% | 128 d | 2019-03-04 | 2019-03-04 | 2019-09-20 | NA | 2019-09-20
2 | 229 | 106409-01.01.01.A | RAnderson | Perform detailed DV topology comparison of optimal trajectories for libration orbits | 25% | 128 d | 2019-03-04 | 2019-03-04 | 2019-09-20 | NA | 2019-05-15
0 | 230 | 106409-01.01.01.A | RAnderson | Draft of Conference Paper | 100% | 26 d | 2019-06-17 | 2019-06-17 | 2019-07-26 | 2019-07-26 | 2019-07-31
1 | 231 | 106409-01.01.01.A | RAnderson | Conference Paper (Summer 2019) | 0% | 1 d | 2019-07-29 | NA | 2019-07-29 | NA | 2019-08-01
3 | 232 | 106409-01.01.01.A | RAnderson | Annual Report | 0% | 1 d | 2019-11-15 | NA | 2019-11-15 | NA | 2019-11-15
| 233 | 106409-02.01.12 | LTorgerson | AMMOS DTN Pilot Implementation | 64% | 281 d | 2018-10-01 | 2018-10-01 | 2019-12-31 | NA | 2019-09-30
| 234 | 106409-02.01.12 | LTorgerson | File Synch Software | 86% | 157 d | 2019-01-22 | 2019-01-22 | 2019-09-27 | NA | 2018-12-27
0 | 235 | 106409-02.01.12 | LTorgerson | Deliver to MITRE & MSFC for Alpha Testing | 100% | 48 d | 2019-01-22 | 2019-01-22 | 2019-03-29 | 2019-03-29 | 2018-10-01
0 | 236 | 106409-02.01.12 | LTorgerson | JPL/MITRE/MSFC Alpha Testing | 100% | 40 d | 2019-04-01 | 2019-04-01 | 2019-05-31 | 2019-05-31 | 2018-12-27
0 | 237 | 106409-02.01.12 | LTorgerson | Minor Bug Fixes | 100% | 19 d | 2019-06-03 | 2019-06-03 | 2019-07-01 | 2019-07-01 | 2018-12-27
3 | 238 | 106409-02.01.12 | LTorgerson | Consider Test Results and Plan Future Development | 0% | 18 d | 2019-08-29 | NA | 2019-09-27 | NA | 2018-12-27
| 239 | 106409-02.01.12 | LTorgerson | DTN-AMP GUI for NM&C | 61% | 281 d | 2018-10-01 | 2018-10-01 | 2019-12-31 | NA | 2019-09-30
0 | 240 | 106409-02.01.12 | LTorgerson | Document Initial Set of GUI Requirements (APL) | 100% | 56 d | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-12-28 | 2018-12-20
0 | 241 | 106409-02.01.12 | LTorgerson | Document Overall New GUI Design Approach (JPL) | 100% | 75 d | 2018-10-01 | 2018-10-01 | 2019-01-31 | 2019-01-31 | 2018-12-20
0 | 242 | 106409-02.01.12 | LTorgerson | Review and Document Data Model (APL with JPL Participation) | 100% | 100 d | 2018-11-05 | 2018-11-05 | 2019-04-18 | 2019-04-18 | 2018-12-20
1 | 243 | 106409-02.01.12 | LTorgerson | Data Model Published | 80% | 33 d | 2019-05-21 | 2019-05-21 | 2019-07-12 | NA | 2018-12-20
1 | 244 | 106409-02.01.12 | LTorgerson | Overall System Design Published | 0% | 1 d | 2019-07-15 | NA | 2019-07-15 | NA | 2018-12-20
1 | 245 | 106409-02.01.12 | LTorgerson | Design & Prototype Python Based SQL Interface for GUI (JPL) | 90% | 131 d | 2019-01-22 | 2019-01-22 | 2019-08-15 | NA | 2019-02-22
1 | 246 | 106409-02.01.12 | LTorgerson | Design User Facing GUI (JPL) | 90% | 131 d | 2019-01-22 | 2019-01-22 | 2019-08-15 | NA | 2019-03-28
0 | 247 | 106409-02.01.12 | LTorgerson | Finalize and Publish SQL Schema (APL) | 100% | 1 d | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2019-04-01
1 | 248 | 106409-02.01.12 | LTorgerson | Produce Python Test Scripts (APL) to Test SQL DB Ops | 10% | 95 d | 2019-04-02 | 2019-04-02 | 2019-08-15 | NA | 2019-05-31
2 | 249 | 106409-02.01.12 | LTorgerson | Prototype Python SQL Interface for GUI (JPL) | 0% | 43 d | 2019-08-16 | NA | 2019-10-16 | NA | 2019-06-28
2 | 250 | 106409-02.01.12 | LTorgerson | Prototype Initial GUI (JPL) | 10% | 87 d | 2019-04-29 | 2019-04-29 | 2019-08-30 | NA | 2019-06-28
1 | 251 | 106409-02.01.12 | LTorgerson | Demo Initial GUI with Python SQL I/F (JPL/APL) | 0% | 1 d | 2019-08-19 | NA | 2019-08-19 | NA | 2019-07-01
2 | 252 | 106409-02.01.12 | LTorgerson | Develop User Facing Portion of GUI (JPL) | 0% | 61 d | 2019-08-20 | NA | 2019-11-13 | NA | 2019-08-15
3 | 253 | 106409-02.01.12 | LTorgerson | Test GUI/Python/SQL/DTN-AMP MGR as a System (JPL/APL) | 0% | 26 d | 2019-11-14 | NA | 2019-12-30 | NA | 2019-09-26
3 | 254 | 106409-02.01.12 | LTorgerson | Demo of Basic GUI System for OPS (JPL/APL) | 0% | 0 d | 2019-12-31 | NA | 2019-12-31 | NA | 2019-09-30
| 255 | 106409-03.01.13 | SChien | Next Gen Plan & Seq | 75% | 224 d | 2018-10-01 | 2018-10-01 | 2019-09-26 | NA | 2019-09-25
0 | 256 | 106409-03.01.13 | SChien | Build More Complex Test Domain | 100% | 92 d | 2018-10-01 | 2018-10-01 | 2019-02-28 | 2019-02-28 | 2018-12-28
2 | 258 |  | SChien | Provide interface specifications for at least two timeline types supporting incremental modeling for inclusion into the Merlin architecture | 0% | 30 d | 2019-08-12 | NA | 2019-09-26 | NA | NA
| 259 |  | SChien | Mission Analysis | 0% | 39 d | 2019-07-29 | NA | 2019-09-26 | NA | NA
2 | 260 |  | SChien | Complete preliminary design for coverage greedy search in CLASP coverage scheduler. Implement strawman non incremental greedy search algorithm | 0% | 39 d | 2019-07-29 | NA | 2019-09-26 | NA | NA
| 263 | 106409-04.01.14 | JStuart | Interactive Data Vis | 53% | 432 d | 2018-10-01 | 2018-10-01 | 2020-08-27 | NA | 2019-09-26
0 | 264 | 106409-04.01.14 | JStuart | Stabilize SunRISE Hololens Demo | 100% | 20 d | 2018-10-01 | 2018-10-01 | 2018-10-30 | 2018-10-30 | 2018-10-30
0 | 265 | 106409-04.01.14 | JStuart | Secure non-AMMOS funding of VR/AR Prototype for use as generalized design tool | 100% | 146 d | 2018-10-01 | 2018-10-01 | 2019-05-23 | 2019-05-23 | 2018-12-28
2 | 266 | 106409-04.01.14 | JStuart | Secure non-AMMOS funding for Orbit Determination Dashboard (OD-D) Development | 0% | 16 d | 2019-08-01 | NA | 2019-08-26 | NA | 2019-01-31
| 267 | 106409-04.01.14 | JStuart | Development of General Purpose VR/AR Tool | 34% | 376 d | 2019-01-02 | 2019-01-02 | 2020-08-27 | NA | 2019-08-29
2 | 268 | 106409-04.01.14 | JStuart | Generalized AR Trajectory Viewer with Wed-Portal Interface | 80% | 151 d | 2019-01-02 | 2019-01-02 | 2019-08-29 | NA | 2019-06-26
3 | 269 | 106409-04.01.14 | JStuart | Integrate VR Manipulation Prototype with Institutional Backend Solver (e.g. Monte) | 0% | 207 d | 2019-10-01 | NA | 2020-08-27 | NA | 2019-08-29
| 270 | 106409-04.01.14 | JStuart | Sustained Development of Orbit Determination Dashboard | 59% | 63 d | 2019-06-05 | 2019-06-05 | 2019-09-12 | NA | 2019-08-29
1 | 271 | 106409-04.01.14 | JStuart | Web Portal Access for MDNav user base | 75% | 36 d | 2019-06-05 | 2019-06-05 | 2019-07-31 | NA | 2019-02-28
2 | 272 | 106409-04.01.14 | JStuart | User interface (UX) interviews and feedback for HCI developers | 75% | 50 d | 2019-06-10 | 2019-06-10 | 2019-08-26 | NA | 2019-04-30
2 | 273 | 106409-04.01.14 | JStuart | Integration of UX feedback into Beta Prototype | 25% | 41 d | 2019-07-11 | 2019-07-11 | 2019-09-12 | NA | 2019-08-29
| 274 | 106409-04.01.14 | JStuart | Expansion of Monte Carlo Analysis Tool from missed thrust to other statistical analysis (planetary protection, conjunction analysis) | 40% | 205 d | 2019-01-22 | 2019-01-22 | 2019-12-13 | NA | 2019-08-29
0 | 275 | 106409-04.01.14 | JStuart | Identification of Common Use Case (e.g. maneuver design) subject matter expert to provide data | 100% | 43 d | 2019-01-22 | 2019-01-22 | 2019-03-28 | 2019-03-28 | 2019-04-30
3 | 276 | 106409-04.01.14 | JStuart | Intern co-projects (one MDNav, one HCI) to prototype Monte Carlo dashboard | 0% | 65 d | 2019-09-03 | NA | 2019-12-13 | NA | 2019-08-29
0 | 277 | 106409-04.01.14 | JStuart | Identification and Initial Development of new prototype related to one of: broad search, optimization, maneuver planning | 100% | 58 d | 2019-04-01 | 2019-04-01 | 2019-06-28 | 2019-06-28 | 2019-05-28
2 | 278 | 106409-04.01.14 | JStuart | Presentation at Conference (SciPy, ASS, etc.) | 0% | 36 d | 2019-08-01 | NA | 2019-09-26 | NA | 2019-09-26
| 279 | 106409-04.01.15A | LTorgerson | AMES Deep Learning & Precursor Identification Task | 95% | 619 d | 2017-12-29 | 2017-12-29 | 2020-09-25 | NA | 2020-09-25
0 | 280 | 106409-04.01.15A | LTorgerson | A Target Mission and End User Identified | 100% | 0 d | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29
0 | 281 | 106409-04.01.15A | LTorgerson | Data Sources, Faults, SMEs Identified | 100% | 0 d | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30
0 | 282 | 106409-04.01.15A | LTorgerson | Data Processed for Learning | 100% | 0 d | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29
0 | 283 | 106409-04.01.15A | LTorgerson | Model Prototyped in Python | 100% | 0 d | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
0 | 284 | 106409-04.01.15A | LTorgerson | Validation Completed (offline data) | 100% | 56 d | 2018-11-19 | 2018-11-19 | 2019-02-22 | 2019-02-22 | 2018-12-28
0 | 285 | 106409-04.01.15A | LTorgerson | Explanation-visualization Developed | 100% | 65 d | 2019-02-25 | 2019-02-25 | 2019-05-24 | 2019-05-24 | 2019-03-29
2 | 286 | 106409-04.01.15A | LTorgerson | Model Extended for Streaming Data | 90% | 106 d | 2019-03-18 | 2019-03-18 | 2019-08-29 | NA | 2019-06-28
3 | 287 | 106409-04.01.15A | LTorgerson | "Operation Like" Playback Demo | 0% | 0 d | 2019-09-27 | NA | 2019-09-27 | NA | 2019-09-27
3 | 288 | 106409-04.01.15A | LTorgerson | Mission Data, Architecture, Hooks Identified | 0% | 0 d | 2019-12-27 | NA | 2019-12-27 | NA | 2019-12-27
3 | 289 | 106409-04.01.15A | LTorgerson | Model Attached to Hooks | 0% | 0 d | 2020-03-27 | NA | 2020-03-27 | NA | 2020-03-27
3 | 290 | 106409-04.01.15A | LTorgerson | Operational Concept Demo | 0% | 0 d | 2020-06-26 | NA | 2020-06-26 | NA | 2020-06-26
3 | 291 | 106409-04.01.15A | LTorgerson | Deliverables Submitted | 0% | 0 d | 2020-09-25 | NA | 2020-09-25 | NA | 2020-09-25
| 292 | 106409-05.01.13 | JLightholder | Data-Driven Explorer | 90% | 88 d | 2019-05-08 | 2019-05-08 | 2019-09-25 | NA | 2019-09-26
0 | 293 | 106409-05.01.13 | JLightholder | Complete REDUX Port | 100% | 14 d | 2019-05-08 | 2019-05-08 | 2019-05-30 | 2019-05-30 | 2019-04-30
0 | 294 | 106409-05.01.13 | JLightholder | Basic User-Testing for Current Bug Scan | 100% | 15 d | 2019-05-31 | 2019-05-31 | 2019-06-24 | 2019-06-24 | 2019-05-31
1 | 295 | 106409-05.01.13 | JLightholder | Speed Optimization | 100% | 25 d | 2019-06-25 | 2019-06-25 | 2019-08-01 | 2019-08-03 | 2019-07-31
2 | 296 | 106409-05.01.13 | JLightholder | Encapsulate Regression/Curve Fitting/ Model Objects | 100% | 34 d | 2019-08-05 | 2019-08-15 | 2019-09-25 | 2019-08-25 | 2019-09-26
3 | 297 | 106409-05.01.13 | JLightholder | Demo Emphasizing Dataset Exploration/Bad Value Scan, Dimensionality Reduction, Logical Selections, Regression and Model Re-usage | 50% | 0 d | 2019-09-25 | 2019-08-15 | 2019-09-25 | NA | 2019-09-26
| 298 | 106409-01.01.01.A | RAnderson | FY20 | 0% | 257 d | 2019-09-30 | NA | 2020-11-16 | NA | NA
3 | 299 | 106409-01.01.01.A | RAnderson | Implement low-thrust transfers directly using low-energy components including invariant manifolds & orbits | 0% | 225 d | 2019-09-30 | NA | 2020-09-24 | NA | NA
3 | 300 | 106409-01.01.01.A | RAnderson | Perform detailed DV topology comparison of optimal trajectories for complex trajectories | 0% | 81 d | 2019-10-01 | NA | 2020-02-11 | NA | 2019-09-23
3 | 301 | 106409-01.01.01.A | RAnderson | Draft of Conference Paper | 0% | 11 d | 2020-01-15 | NA | 2020-02-03 | NA | NA
3 | 302 | 106409-01.01.01.A | RAnderson | Conference Paper (Winter 2020) | 0% | 0 d | 2020-02-03 | NA | 2020-02-03 | NA | NA
3 | 303 | 106409-01.01.01.A | RAnderson | Draft of Conference Paper | 0% | 11 d | 2020-07-15 | NA | 2020-07-30 | NA | NA
3 | 304 | 106409-01.01.01.A | RAnderson | Conference Paper (Summer 2020) | 0% | 1 d | 2020-08-03 | NA | 2020-08-03 | NA | NA
3 | 305 | 106409-01.01.01.A | RAnderson | Complete search algorithms and algorithm document | 0% | 0 d | 2020-09-24 | NA | 2020-09-24 | NA | NA
3 | 306 | 106409-01.01.01.A | RAnderson | Final Report | 0% | 0 d | 2020-11-16 | NA | 2020-11-16 | NA | NA