## Sheet1
Status Date: 12/29/19
MGSS Status Indicator | ID | WBS | #CAM | Task Name | % Complete | Duration | Start | Act/Est Start | Finish | Act/Est Finish | Baseline Finish | Explanation of Changes from Previous Month
| 3 | REF | REF | FY17 | 100% | 804 d | 2014-06-30 | 2014-06-30 | 2018-01-26 | 2018-01-26 | 2017-12-22
| 133 | REF | REF | FY18 | 100% | 302 d | 2017-09-25 | 2017-09-25 | 2019-01-29 | 2019-01-29 | 2018-11-16
| 222 | REF | REF | FY19 | 99% | 417 d | 2017-12-29 | 2017-12-29 | 2019-11-01 |  | 2020-09-25
| 271 | 04.01.14 | JStuart | Interactive Data Vis | 98% | 247 d | 2018-10-01 | 2018-10-01 | 2019-11-01 |  | 2019-09-26
0 | 272 | 04.01.14 | JStuart | Stabilize SunRISE Hololens Demo | 100% | 20 d | 2018-10-01 | 2018-10-01 | 2018-10-30 | 2018-10-30 | 2018-10-30
0 | 273 | 04.01.14 | JStuart | Secure non-AMMOS funding of VR/AR Prototype for use as generalized design tool | 100% | 146 d | 2018-10-01 | 2018-10-01 | 2019-05-23 | 2019-05-23 | 2018-12-28
| 275 | 04.01.14 | JStuart | Development of General Purpose VR/AR Tool | 95% | 217 d | 2019-01-02 | 2019-01-02 | 2019-12-16 | NA | 2019-08-29
1 | 276 | 04.01.14 | JStuart | Generalized AR Trajectory Viewer with Wed-Portal Interface | 95% | 217 d | 2019-01-02 | 2019-01-02 | 2019-12-16 | NA | 2019-06-26
| 278 | 04.01.14 | JStuart | Sustained Development of Orbit Determination Dashboard | 100% | 51 d | 2019-06-05 | 2019-06-05 | 2019-08-23 | 2019-08-23 | 2019-08-29
| 282 | 04.01.14 | JStuart | Expansion of Monte Carlo Analysis Tool from missed thrust to other statistical analysis (planetary protection, conjunction analysis) | 100% | 43 d | 2019-01-22 | 2019-01-22 | 2019-03-28 | 2019-03-28 | 2019-08-29
0 | 285 | 04.01.14 | JStuart | Identification and Initial Development of new prototype related to one of: broad search, optimization, maneuver planning | 100% | 58 d | 2019-04-01 | 2019-04-01 | 2019-06-28 | 2019-06-28 | 2019-05-28
0 | 286 | 04.01.14 | JStuart | Presentation at Conference (SciPy, ASS, etc.) | 100% | 15 d | 2019-08-01 | 2019-08-01 | 2019-08-23 | 2019-08-23 | 2019-09-26
| 287 | 04.01.15A | LTorgerson | AMES Deep Learning & Precursor Identification Task | 100% | 394 d | 2017-12-29 | 2017-12-29 | 2019-09-27 | 2019-09-27 | 2020-09-25
| 300 | 05.01.13 | JLightholder | Data-Driven Explorer | 100% | 88 d | 2019-05-08 | 2019-05-08 | 2019-09-25 | 2019-09-25 | 2019-09-26
| 306 | 01.01.02 | BCastano | Autonomy Evaluation | 50% | 40 d | 2019-11-14 | 2019-11-14 | 2020-01-23 | NA | 2020-01-23
0 | 307 | 01.01.02 | BCastano | Report Outline with key topics areas | 100% | 1 d | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2019-11-14
3 | 308 | 01.01.02 | BCastano | Final Report | 0% | 1 d | 2020-01-23 | NA | 2020-01-23 | NA | 2020-01-23
| 309 | 02.01.12 | LTorgerson | AMMOS DTN Pilot Implementation | 0% | 157 d | 2019-12-20 | NA | 2020-08-31 | NA | 2020-08-31
3 | 310 | 02.01.12 | LTorgerson | DTN File Sync to MITRE/MSFC | 0% | 1 d | 2019-12-31 | NA | 2019-12-31 | NA | 2019-11-01
1 | 311 | 02.01.12 | LTorgerson | ION Config tool to AMMOS tookit | 0% | 1 d | 2019-12-20 | NA | 2019-12-20 | NA | 2019-12-20
3 | 312 | 02.01.12 | LTorgerson | DTN MCC Conops - draft 1 | 0% | 1 d | 2020-03-30 | NA | 2020-03-30 | NA | 2020-03-30
3 | 313 | 02.01.12 | LTorgerson | DTN File Sync to AMMOS | 0% | 1 d | 2020-06-29 | NA | 2020-06-29 | NA | 2020-06-29
3 | 314 | 02.01.12 | LTorgerson | DTN MCC Conops - draft 2 | 0% | 1 d | 2020-08-31 | NA | 2020-08-31 | NA | 2020-08-31
| 315 | 02.01.12 | LTorgerson | File Synch Software | 30% | 102 d | 2019-09-30 | 2019-09-30 | 2020-03-16 | NA | 2020-03-16
2 | 316 | 02.01.12 | LTorgerson | Consider Test Results and Plan Future Development | 30% | 102 d | 2019-09-30 | 2019-09-30 | 2020-03-16 | NA | 2020-03-16
| 317 | 02.01.12 | LTorgerson | DTN-AMP GUI for NM&C | 50% | 228 d | 2019-09-30 | 2019-09-30 | 2020-09-30 | NA | 2020-09-30
0 | 318 | 02.01.12 | LTorgerson | Overall System Design Published | 100% | 1 d | 2019-11-01 | 2019-11-01 | 2019-11-01 | 2019-11-01 | 2019-09-30
2 | 319 | 02.01.12 | LTorgerson | Produce Python Test Scripts (APL) to Test SQL DB Ops | 50% | 93 d | 2019-09-30 | 2019-09-30 | 2020-03-02 | NA | 2020-03-02
3 | 320 | 02.01.12 | LTorgerson | Demo Initial GUI with Python SQL I/F (JPL/APL) | 0% | 1 d | 2020-09-30 | NA | 2020-09-30 | NA | 2020-09-30
| 325 | AMES - BYPASS | LTorgerson | AMES Deep Learning & Precursor Identification Tasks | 0% | 225 d | 2019-09-27 | 2019-09-27 | 2020-09-25 | NA | 2020-09-25
0 | 326 | AMES - BYPASS | LTorgerson | "Operation Like" Playback Demo | 100% | 0 d | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2019-09-27
3 | 327 | AMES - BYPASS | LTorgerson | Mission Data, Architecture, Hooks Identified | 0% | 0 d | 2020-02-28 | NA | 2020-02-28 | NA | 2019-12-27
3 | 328 | AMES - BYPASS | LTorgerson | Model Attached to Hooks | 0% | 0 d | 2020-05-29 | NA | 2020-05-29 | NA | 2020-03-27
3 | 329 | AMES - BYPASS | LTorgerson | Operational Concept Demo | 0% | 0 d | 2020-08-28 | NA | 2020-08-28 | NA | 2020-06-26
3 | 330 | AMES - BYPASS | LTorgerson | Deliverables Submitted | 0% | 0 d | 2020-09-25 | NA | 2020-09-25 | NA | 2020-09-25
| 331 | 03.01.13 | SChien | Next Gen Plan & Seq | 40% | 157 d | 2019-10-15 | 2019-10-15 | 2020-06-26 | NA | 2020-09-25
0 | 332 | 03.01.13 | SChien | 1st Qtr: Complete design for 2 incremental propagation timeline types | 100% | 0 d | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-12-27
2 | 333 | 03.01.13 | SChien | 2nd Qtr: Complete software prototype for 2 incremental propagation timeline types | 40% | 112 d | 2019-10-15 | 2019-10-15 | 2020-03-27 | NA | 2020-03-27
3 | 334 | 03.01.13 | SChien | 3rd Qtr: Report on incremental propagation timeline types at peer reviewed workshop or conference | 0% | 0 d | 2020-06-26 | NA | 2020-06-26 | NA | 2020-06-26
| 336 | 04.01.13 | RAnderson | Low Thrust Option | 13% | 482 d | 2019-09-30 | 2019-09-30 | 2021-11-16 | NA | 2021-11-16
0 | 337 | 04.01.13 | RAnderson | Annual Report | 100% | 1 d | 2019-11-15 | 2019-11-15 | 2019-11-15 | 2019-11-15 | 2019-11-15
1 | 338 | 04.01.13 | RAnderson | Perform detailed DV and topology comparison of optimal trajectories for complex trajectory combinations | 95% | 39 d | 2019-10-01 | 2019-10-01 | 2019-12-02 | NA | 2019-12-02
2 | 339 | 04.01.13 | RAnderson | Implement low-thrust transfers directly using low-energy components including three-dimensional orbits | 45% | 63 d | 2019-09-30 | 2019-09-30 | 2020-01-10 | NA | 2020-01-10
3 | 340 | 04.01.13 | RAnderson | Implement low-thrust transfers directly using low-energy components including invariant manifolds | 0% | 88 d | 2020-01-13 | NA | 2020-06-01 | NA | 2020-06-01
3 | 341 | 04.01.13 | RAnderson | Draft of Conference Paper | 0% | 1 d | 2020-05-15 | NA | 2020-05-15 | NA | 2020-05-15
3 | 342 | 04.01.13 | RAnderson | Conference Paper (Spring 2020) | 0% | 1 d | 2020-06-01 | NA | 2020-06-01 | NA | 2020-06-01
3 | 343 | 04.01.13 | RAnderson | Implement low-thrust transfers directly using low-energy using invariant manifold components across energies | 0% | 39 d | 2020-05-01 | NA | 2020-07-01 | NA | 2020-07-01
3 | 344 | 04.01.13 | RAnderson | Draft of conference paper | 0% | 1 d | 2020-07-15 | NA | 2020-07-15 | NA | 2020-07-15
3 | 345 | 04.01.13 | RAnderson | Conference Paper (Summer 2020) | 0% | 1 d | 2020-08-03 | NA | 2020-08-03 | NA | 2020-08-03
3 | 346 | 04.01.13 | RAnderson | Study the use of nearly periodic orbit components in low-thrust transfer solutions | 0% | 55 d | 2020-07-01 | NA | 2020-09-24 | NA | 2020-09-24
3 | 347 | 04.01.13 | RAnderson | Annual Report | 0% | 0 d | 2020-11-16 | NA | 2020-11-16 | NA | 2020-11-16
3 | 348 | 04.01.13 | RAnderson | Combine different orbit type components for complete solutions | 0% | 152 d | 2020-09-28 | NA | 2021-06-01 | NA | 2021-06-01
3 | 349 | 04.01.13 | RAnderson | Complete process for generating complete low-thrust solutions for sample scenarios | 0% | 72 d | 2021-06-02 | NA | 2021-09-23 | NA | 2021-09-23
3 | 350 | 04.01.13 | RAnderson | Complete search algorithms and algorithm document | 0% | 1 d | 2021-09-27 | NA | 2021-09-27 | NA | 2021-09-27
3 | 351 | 04.01.13 | RAnderson | Final Report | 0% | 0 d | 2021-11-16 | NA | 2021-11-16 | NA | 2021-11-16
| 352 | 04.01.14 | JStuart | Interactive Data Vis | 17% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | NA | 2020-09-24
2 | 353 | 04.01.14 | JStuart | Transition AR Software ('Sagan') to multi-mission funding support | 75% | 57 d | 2019-09-30 | 2019-09-30 | 2019-12-31 | NA | 2019-12-31
3 | 354 | 04.01.14 | JStuart | Transition Orbit Determination Software ('OD-D') to multi-mission funding support | 0% | 36 d | 2020-01-02 | NA | 2020-03-02 | NA | 2019-12-31
| 355 | 04.01.14 | JStuart | Development of General Purpose VR/AR Tool ('Sagan') | 17% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | NA | 2019-12-31
2 | 356 | 04.01.14 | JStuart | LOE: Non mission-specific enhancements to AR and web interface | 17% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | NA | 2019-12-31
| 358 | 04.01.14 | JStuart | Sustained Development of Orbit Determination Dashboard (OD-D) | 17% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | NA | 2019-12-31
2 | 359 | 04.01.14 | JStuart | LOE: Minor bug fixes and enhancements as users request | 17% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | NA | 2019-12-31
| 360 | 04.01.14 | JStuart | Expansion of Monte Carlo Analysis Tool to maneuver planning (and other statistical cases) | 38% | 92 d | 2019-09-30 | 2019-09-30 | 2020-02-27 | NA | 2020-02-27
1 | 361 | 04.01.14 | JStuart | Intern co-projects (one MDNav, one HCI) to prototype Monte Carlo dashboard | 75% | 48 d | 2019-09-30 | 2019-09-30 | 2019-12-13 | NA | 2019-12-13
0 | 362 | 04.01.14 | JStuart | First round of interviews and development of initial prototype | 100% | 14 d | 2019-09-30 | 2019-09-30 | 2019-10-18 | 2019-10-18 | 2019-10-18
1 | 363 | 04.01.14 | JStuart | Follow-on interviews and iterations of prototype | 10% | 29 d | 2019-10-21 | 2019-10-21 | 2019-12-05 | NA | 2019-12-05
2 | 364 | 04.01.14 | JStuart | Identify follow-on funding for sustained development (as appropriate) | 0% | 49 d | 2019-12-09 | NA | 2020-02-27 | NA | 2020-02-27
| 365 | 04.01.14 | JStuart | Development of Monte/SparQ library for mission-specific visual analysis environments | 16% | 225 d | 2019-09-30 | 2019-09-30 | 2020-09-24 | NA | 2020-09-24
0 | 366 | 04.01.14 | JStuart | Completion of prototype cases for VIVID lab presentation | 100% | 22 d | 2019-09-30 | 2019-09-30 | 2019-10-31 | 2019-10-31 | 2019-10-31
2 | 367 | 04.01.14 | JStuart | Synthesize most common use cases / graphics among MDNav users | 25% | 53 d | 2019-11-01 | 2019-11-01 | 2020-01-30 | NA | 2019-12-31
3 | 368 | 04.01.14 | JStuart | Development of API / library of functions for common use cases | 0% | 150 d | 2020-02-03 | NA | 2020-09-24 | NA | 2020-09-24
| 369 | 04.01.14 | JStuart | Quantitative User Analysis | 0% | 93 d | 2020-01-02 | NA | 2020-05-29 | NA | 2020-05-29
3 | 370 | 04.01.14 | JStuart | Definition of metrics and experiment design | 0% | 18 d | 2020-01-02 | NA | 2020-01-30 | NA | 2020-01-30
3 | 371 | 04.01.14 | JStuart | User interviews and tests | 0% | 37 d | 2020-02-03 | NA | 2020-03-31 | NA | 2020-03-31
3 | 372 | 04.01.14 | JStuart | Quantitative analysis & preparation for publication | 0% | 38 d | 2020-04-01 | NA | 2020-05-29 | NA | 2020-05-29
| 373 | 04.01.14 | JStuart | Identify user needs and initial development of new prototype related to optimization | 0% | 75 d | 2020-06-01 | NA | 2020-09-24 | NA | 2020-09-24
3 | 374 | 04.01.14 | JStuart | Intern co-projects (one MDNav, one HCI) to prototype rajectory optimization dashboard | 0% | 59 d | 2020-06-01 | NA | 2020-08-31 | NA | 2020-08-31
3 | 375 | 04.01.14 | JStuart | First round of interviews and development of initial prototype | 0% | 31 d | 2020-06-01 | NA | 2020-07-16 | NA | 2020-07-16
3 | 376 | 04.01.14 | JStuart | Follow-on interviews and iterations of prototype | 0% | 28 d | 2020-07-20 | NA | 2020-08-31 | NA | 2020-08-31
3 | 377 | 04.01.14 | JStuart | Identify follow-on funding for sustained development (as appropriate) | 0% | 16 d | 2020-09-01 | NA | 2020-09-24 | NA | 2020-09-24
3 | 378 | 04.01.14 | JStuart | Presentation at Conference (SciPy, AAS, Viz, etc.) | 0% | 59 d | 2020-06-01 | NA | 2020-08-31 | NA | 2020-08-31
| 379 | 05.01.13 | JLightholder | CODEX - Complex Data Explorer | 19% | 224 d | 2019-10-01 | 2019-10-01 | 2020-09-25 | NA | 2020-09-25
2 | 380 | 05.01.13 | JLightholder | Design and Implement "Data Quality Scan" User Interface | 100% | 62 d | 2019-10-01 | 2019-10-01 | 2019-12-31 | 2019-12-31 | 2019-12-31
3 | 381 | 05.01.13 | JLightholder | Feature Bar Extension to Support Multiple Interaction Windows | 25% | 40 d | 2020-01-02 | 2020-01-01 | 2020-02-28 | NA | 2020-02-28
3 | 382 | 05.01.13 | JLightholder | Extend Server Data Reader Capabilities to for Additional Data Types | 0% | 33 d | 2020-03-02 | NA | 2020-04-15 | NA | 2020-04-15
3 | 383 | 05.01.13 | JLightholder | Extend Runtime Prediction Model to Support Features/Samples in Calculation | 0% | 22 d | 2020-04-16 | NA | 2020-05-15 | NA | 2020-05-15
3 | 384 | 05.01.13 | JLightholder | Design and Implement "Model Training" User Interface | 0% | 20 d | 2020-05-18 | NA | 2020-06-15 | NA | 2020-06-15
3 | 385 | 05.01.13 | JLightholder | Enable Session Saving / Loading | 0% | 33 d | 2020-06-16 | NA | 2020-07-31 | NA | 2020-07-31
3 | 386 | 05.01.13 | JLightholder | Enable Data / Code / Selection / Feature Export | 0% | 17 d | 2020-08-03 | NA | 2020-08-25 | NA | 2020-08-25
3 | 387 | 05.01.13 | JLightholder | Advanced User Guidance Through Dynamic Error Reporting | 0% | 22 d | 2020-08-26 | NA | 2020-09-25 | NA | 2020-09-25
| 388 | 05.01.14 | LDahl | PATCH | 20% | 224 d | 2019-10-04 | 2019-10-04 | 2020-09-30 | NA | 2020-09-30
0 | 389 | 05.01.14 | LDahl | Identify appropriate photclinometry model for surface use | 100% | 44 d | 2019-10-04 | 2019-10-04 | 2019-12-13 | 2019-12-13 | 2019-12-13
2 | 390 | 05.01.14 | LDahl | Determine how to constrain PC using correlation results | 0% | 36 d | 2019-12-16 | NA | 2020-02-13 | NA | 2020-02-13
3 | 391 | 05.01.14 | LDahl | Implement photoclinometry model with correlation constraints | 0% | 38 d | 2020-02-18 | NA | 2020-04-15 | NA | 2020-04-15
3 | 392 | 05.01.14 | LDahl | Evaluate results against existing products | 0% | 87 d | 2020-04-16 | NA | 2020-08-31 | NA | 2020-08-31
3 | 393 | 05.01.14 | LDahl | Write report detailing performance of algorithm | 0% | 19 d | 2020-09-01 | NA | 2020-09-30 | NA | 2020-09-30