## TECH
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
Program Office | 01.01.01 | WYATT, E JAY | 7.7273 | 0.055264 | 7.7273 |  |  |  | 11.79% | 65.5495
Autonomy Evaluation | 01.01.02 | CASTANO, REBECCA | 44.4248 | 0.33241 | 44.4248 |  |  |  | 77.23% | 57.5261
AMMOS DTN PILOT IMP | 02.01.12 | TORGERSON, JORDAN L | -0.74389 | 0.03997 | -0.74389 |  |  |  | -1.71% | 43.5088
Next Gen Plan & Seq | 03.01.13 | CHIEN, STEVE | 22.5899 | 0.22611 | 22.5899 |  |  |  | 39.33% | 57.4357
Low-Thrust Opt | 04.01.13 | ANDERSON, DR. RODNEY L | 0.32043 | -0.014757 | 0.32043 |  |  |  | 0.6377% | 50.2472
Interactive Data Vis | 04.01.14 | STUART, JEFFREY R | -13.1371 | 0.23345 | 3.1153 |  |  |  | 4.661% | 66.8367
DATA DRIVEN EXPLORER | 05.01.13 | LIGHTHOLDER, JACK | -24.9037 | -0.15988 | -24.9037 | Workforce redirect to Mars 2020 delivery | Workforce now available again. Bringing on another develop to re-sync with budget. | 2020-04-01 | -33.95% | 73.3463
PATCH | 05.01.14 | RADULESCU, COSTIN | 37.7778 | 0.23725 | 37.7778 |  |  |  | 45.53% | 82.9755
|  | TOTAL |  |  | 90.308

## MGMT
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
AMMOS PROG MGMT | A.1.01.0.01.01 | PONS, JUDITH S | -13.5042 | 0.00756 | -24.9344 |  |  |  | -5.996% | 415.8186
AMMOS PROG ADMIN | A.1.01.0.02.01 | PONS, JUDITH S | 57.2787 | 0.22938 | 56.9715 |  |  |  | 24.03% | 237.0466
MISSION INT OFFICE | A.1.01.0.04.01 | ELLIOTT, ROBERT G | 98.3238 | 0.6174 | 98.391 |  |  |  | 19.81% | 496.7343
|  | TOTAL |  |  | 130.428

## BO
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
BUSINESS MGT | B.1.01.0.01.02 | DI PAOLO, RUSSELL M | 12.6138 | 0.06169 | 12.6138 |  |  |  | 9.404% | 134.1274
BUSINESS SPT | B.1.01.0.02.02 | DI PAOLO, RUSSELL M | 29.3482 | 0.22021 | 29.3482 |  |  |  | 15.58% | 188.4316
BUSINESS SCHED | B.1.01.0.04.02 | DI PAOLO, RUSSELL M | -3.2291 | 0.00249 | -3.2291 |  |  |  | -1.55% | 208.3612
CUSTOMER DEVELOPMENT | B.1.02.0.01.02 | ELLIOTT, ROBERT G | 18.2058 | 0.14904 | -0.97684 |  |  |  | -1.588% | 61.531
|  | TOTAL |  |  | 37.756

## SPO
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MGSS IMP & PLNG | E.1.00.0.00.01 | GUNN, JOHANNA M | 0.48983 | -0.09115 | 0.48983 |  |  |  | 0.2318% | 211.3122
|  | TOTAL |  |  | 0.48983

## RMO
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
RELAY SYS ENG | M.1.00.0.01.03 | CALL, JARED A | -5.78 | -0.02698 | -5.78 |  |  |  | -2.997% | 192.8916
RELAY I&T | M.1.00.0.01.06 | CALL, JARED A | 13.2637 | -0.11881 | 13.2637 |  |  |  | 10.27% | 129.2035
RELAY MAINT | M.1.00.0.01.07 | CALL, JARED A | -21.2287 | -0.2587 | -21.2287 |  |  |  | -37.15% | 57.1413
|  | TOTAL |  |  | -13.745

## SEO
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MGSS Sys Engr | C.2.01.2.01.03 | RADULESCU, COSTIN | -10.9812 | -0.02326 | -6.4377 |  |  |  | -3.599% | 178.8708
MM GDS ENG | C.2.01.2.10.03 | O'BRIEN, ROBIN A | -8.9508 | -0.10229 | -9.6353 |  |  |  | -6.081% | 158.4618
SEO SECURITY | C.2.01.2.11.03 | PAJEVSKI, MICHAEL J | -1.2932 | 0.04085 | -1.2932 |  |  |  | -2.281% | 56.6947
SYS ARCH & ENG | C.2.01.2.12.03 | PAJEVSKI, MICHAEL J | 85.6117 | 0.45064 | 85.6117 |  |  |  | 24.31% | 352.1079
SOFTWARE SYS ENG | C.2.01.2.13.03 | PAJEVSKI, MICHAEL J | 5.5162 | 0.055739 | 6.1971 |  |  |  | 26.9% | 23.039
MGSS Configuration M | C.2.04.2.01.04 | SHIN, SEUNG H | 9.0016 | 0.28599 | 9.0016 |  |  |  | 2.895% | 310.9225
Config MGMT Mainten | C.2.04.2.01.08 | SHIN, SEUNG H | 18.0884 | 0.05626 | 17.4596 |  |  |  | 17.99% | 97.0295
MGSS - IMS | C.2.06.2.01.03 | MCCLEARY, JENNIFER M | 29.4581 | 0.15053 | 29.4612 |  |  |  | 30.87% | 95.4357
GDS Security | C.2.07.1.13.10 | PAJEVSKI, MICHAEL J | 34.7821 | 0.07211 | 35.2773 |  |  |  | 14.67% | 240.4884
Integrated AMMOS | C.2.07.1.14.10 | NGUYEN, VU H | -7.6298 | -0.038052 | -14.4874 |  |  |  | -10.39% | 139.4316
I&T VALIDATION | C.2.07.2.04.06 | MARKHAM, SCOTT D | 36.7924 | 0.17872 | 7.3663 |  |  |  | 1.41% | 522.3898
MGSS PORT CHARGES | C.2.07.2.08.09 | MARKHAM, SCOTT D | -4.6145 | 0 | -4.6145 |  |  |  | -11.21% | 41.1632
MM GDS SUPPORT | C.2.07.2.16.03 | O'BRIEN, ROBIN A | 153.9741 | 1.0717 | 153.9741 |  |  |  | 49.7% | 309.7941
MM INT & TEST DEP SE | C.2.07.2.17.03 | MARKHAM, SCOTT D | 10.0698 | 0.06692 | 10.0698 |  |  |  | 5.745% | 175.272
MM DEPLOYMENT ENG | C.2.07.2.18.03 | MARKHAM, SCOTT D | -9.3629 | -0.01342 | -9.3629 |  |  |  | -7.458% | 125.5386
COMPUTE PLATFORM ENG | C.2.07.2.19.03 | NGUYEN, VU H | 13.7152 | 0.09011 | -9.251 |  |  |  | -5.993% | 154.3724
SEC PLAN-H/W-LIC | C.2.07.2.21.03 | O'BRIEN, ROBIN A | -14.7705 | 0.03874 | -19.0098 |  |  |  | -13.34% | 142.5022
SYS ENG SA | C.2.07.2.22.03 | CASTILLO, OSCAR | -21.2365 | 0 | -21.2365 |  |  |  | -8.553% | 248.2865
COMMON LOGGING SVC | C.2.08.1.06.10 | PAJEVSKI, MICHAEL J | -18.5314 | 0 | -9.0647 |  |  |  | 0% | 0
SDDA | C.2.08.1.07.10 | DAHL, LUKE | 48.3468 | 0.40195 | 48.3468 |  |  |  | 52.42% | 92.223
Config Module Imp | C.2.08.1.13.10 | GIESELMAN, KENNETH G | 7.4827 | 0 | 0.00042735 |  |  |  | 0.0003967% | 107.7194
ASIS | C.2.08.2.01.10 | PAJEVSKI, MICHAEL J | -1.0108 | -0.04116 | 1.4845 |  |  |  | 0.4589% | 323.4666
ASEC MAINT | C.2.08.2.05.08 | PAJEVSKI, MICHAEL J | -12.0486 | -0.1232 | -16.0934 |  |  |  | -5.667% | 283.9662
Common Logging Svc Maint | C.2.08.2.06.07 | PAJEVSKI, MICHAEL J | 2.2711 | 0 | 1.1134 |  |  |  | 4.471% | 24.9029
CSE | C.2.08.2.07.07 | PAJEVSKI, MICHAEL J | 74.1466 | 0.01045 | 79.6474 |  |  |  | 43.51% | 183.0393
REF MISSION SYSTEMS | C.2.09.1.01.10 | STRANGE, NATHAN J | 84.7869 | 0.42192 | 82.7588 |  |  |  | 24.37% | 339.6139
AMMOS CATALOG | C.2.09.2.02.03 | DAHL, LUKE | 14.1378 | 0 | 28.3151 |  |  |  | 141.1% | 20.0607
|  | TOTAL |  |  | 475.5986

## MDN
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MDN MANAGEMENT | G.1.00.0.00.01 | BERRY, DAVID S | -3.912 | -0.057008 | -3.912 |  |  |  | -3.771% | 103.7357
MDN SYS ENG | G.1.00.0.00.03 | GERASIMATOS, DIMITRIOS V | -44.1253 | -0.29116 | -44.1253 |  |  |  | -30.74% | 143.5212
MONTE/MASAR PDM | G.1.00.0.01.01 | EVANS, DR. SCOTT E | -22.0437 | -0.1157 | -22.0437 |  |  |  | -14.69% | 150.0551
MDN SOFTWARE ADV | G.2.01.1.06.10 | EVANS, DR. SCOTT E | 70.528 | 0.50408 | 5.6649 |  |  |  | 4.281% | 132.3323
Primitive Body Nav | G.2.01.1.10.10 | PAVLAK, DR. THOMAS A | -19.397 | -0.05086 | -54.7713 |  |  |  | -79.72% | 68.7041
Statistical Navigation Truth Sim | G.2.01.1.11.10 | EVANS, DR. SCOTT E | 56.9879 | 0.4175 | 56.9879 |  |  |  | 64.15% | 88.8374
Automated RMM Design & Implemntn | G.2.01.1.12.10 | GARCIA, MARK D | 68.5399 | 0.41271 | 68.5399 |  |  |  | 64.33% | 106.5422
Nav Sanity Check Tool | G.2.01.1.13.10 | EVANS, DR. SCOTT E | -0.10603 | 0 | -0.10603 |  |  |  | #DIV/0! | 0
Monte NIDO Replacement | G.2.01.1.14.10 | EVANS, DR. SCOTT E | -1.9203 | 0 | -1.9203 |  |  |  | #DIV/0! | 0
MONTE MAINT | G.2.01.2.02.07 | EVANS, DR. SCOTT E | 80.0856 | 0.69203 | 80.032 |  |  |  | 31.95% | 250.454
MONTE TRAIN & CUST SUPT | G.2.01.2.02.10 | EVANS, DR. SCOTT E | -3.393 | -0.078403 | -35.6707 |  |  |  | -250.6% | 14.2362
NAV SW AUTOMA MAINT | G.2.01.2.03.07 | TABER, DR. WILLIAM L | 0.928 | -0.019257 | 0.928 |  |  |  | 2.07% | 44.8243
LANDMARK TRACKING SW | G.2.02.1.04.10 | VAUGHAN, ANDREW T | 16.6308 | 0 | -1.3895 |  |  |  | #DIV/0! | 0
ONIPS MODERNIZATION | G.2.02.1.05.10 | EVANS, DR. SCOTT E | -14.1319 | -0.37673 | -14.1319 |  |  |  | -9.957% | 141.9326
PLANETARY EPHEMERIS | G.5.01.2.01.09 | PARK, DR. SANG H | 7.3741 | -0.092647 | 6.7976 |  |  |  | 2.406% | 282.5408
SATELLITE EPHEMERIS | G.5.02.2.01.09 | PARK, DR. SANG H | -48.7628 | -0.40183 | -63.0415 |  |  |  | -24.11% | 261.5157
CMT/AST EPHEMERIS | G.5.03.2.01.09 | PARK, DR. SANG H | 10.8367 | -0.42048 | 28.8019 |  |  |  | 14.27% | 359.7517
GRAVITY MODELLING | G.5.04.2.01.09 | PARK, DR. SANG H | -15.8766 | -0.34271 | -29.2858 |  |  |  | -28.32% | 103.396
Astrodynamics Tech Infusion | G.7.01.1.01.10 | EVANS, DR. SCOTT E | -65.7971 | -0.33794 | -65.7971 |  |  |  | -76.64% | 85.8495
|  | TOTAL |  |  | -88.443

## MPSA
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MPS MGMT | H.1.00.0.00.01 | CHAFIN, BRIAN G | 35.6107 | 0.15699 | 35.6107 |  |  |  | 19.01% | 187.2991
MGSS SEQ SE | H.1.00.0.00.03 | CHAFIN, BRIAN G | -2.2243 | -0.05349 | -2.2206 |  |  |  | -0.6021% | 368.8348
SEQ SUBSYSTEM TEST | H.1.00.0.00.06 | CHAFIN, BRIAN G | 143.4242 | 1.1037 | 143.4242 |  |  |  | 32.71% | 438.5002
MPS MAINT NEW | H.1.00.0.00.07 | CHAFIN, BRIAN G | -115.6004 | -0.819 | -165.6345 |  |  |  | -57.05% | 290.3321
CAST | H.1.00.1.08.10 | CHAFIN, BRIAN G | -1.5672 | 0 | -1.5672 |  |  |  | 0% | 0
Web Int for Plan Maint | H.1.00.2.02.07 | CHAFIN, BRIAN G | -14.0888 | -0.11542 | -14.0888 |  |  |  | -125.7% | 11.2101
SOA Rearchitecture | H.2.01.1.05.10 | CHAFIN, BRIAN G | 7.1314 | 0.036198 | 7.1314 |  |  |  | 25.07% | 28.4461
Web Interface | H.2.01.1.06.10 | CHAFIN, BRIAN G | -1.0807 | 0 | -1.0807 |  |  |  | 0% | 0
SERVICE MANAGEMENT I | H.3.01.1.10.10 | TUNG, DR. YU-WEN | -0.75006 | 0 | -0.75006 |  |  |  | 0% | 0
Advance MPSA | H.3.01.1.20.10 | CHAFIN, BRIAN G | 60.1141 | 0.30362 | 60.1141 |  |  |  | 9.586% | 627.0981
S/C Analysis Maint | H.5.01.2.01.07 | CHEUNG, DR. KAR-MING | 20.8124 | 0.16079 | 20.8124 |  |  |  | 18.42% | 113.0188
|  | TOTAL |  |  | 81.751

## MMCS
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
MCS MGT | J.1.00.0.00.01 | KHAZRA, MOOJAN | 2.991 | -0.03214 | 2.991 |  |  |  | 1.954% | 153.0745
MCS SYS ENG | J.1.00.0.00.03 | KHAZRA, MOOJAN | -80.922 | -0.46872 | -79.4899 |  |  |  | -34.28% | 231.9094
MCS TEST ENG | J.1.00.0.00.06 | SHAMILIAN, ARSHALUYS | -30.1642 | -0.31023 | -22.4504 |  |  |  | -9.026% | 248.7166
MCS SYS LVL MAINT | J.1.00.0.00.07 | KHAZRA, MOOJAN | -141.4928 | -1.2639 | -141.4928 |  |  |  | -43.66% | 324.0939
Sys Admin & Dep SUPT | J.1.00.0.01.03 | KHAZRA, MOOJAN | 34.5794 | 0 | 34.5794 |  |  |  | 25.24% | 137.0081
INFO ARCH STANDARDS | J.1.00.0.02.03 | KHAZRA, MOOJAN | 0 | 0 | 0 |  |  |  | 0% | 0
Chill Mon Rep Dev Testing | J.1.00.1.05.10 | KHAZRA, MOOJAN | 17.3105 | 0.1866 | 17.3105 |  |  |  | 59.48% | 29.1009
MCWS New Dev | J.2.02.1.02.10 | KHAZRA, MOOJAN | 23.4766 | 0.21826 | 23.4766 |  |  |  | 27.69% | 84.7687
MC D/L PROC PERF IMP | J.2.02.1.03.10 | DEFORREST, LLOYD R | -14.1987 | 0 | -2.725 |  |  |  | 0% | 0
INTEGRATED COMMAND | J.2.02.1.04.10 | DEFORREST, LLOYD R | -1.4271 | 0 | -1.4271 |  |  |  | 0% | 0
TSDB Integration | J.2.02.1.06.10 | KHAZRA, MOOJAN | 27.4345 | 0.33498 | 27.4345 |  |  |  | 22.34% | 122.8137
Int Command Maint | J.2.02.2.01.07 | KHAZRA, MOOJAN | -50.9433 | -0.74694 | -36.4649 |  |  |  | -23.94% | 152.2936
AMPCS SLE CFDP DEV | J.2.07.1.09.10 | DEFORREST, LLOYD R | -1.2552 | 0 | -1.2552 |  |  |  | 0% | 0
AMPCS Pass Automation | J.2.07.1.12.10 | KHAZRA, MOOJAN | -25.6684 | -0.19745 | -25.6684 |  |  |  | -45.19% | 56.8066
TDAC - Maintenance | J.2.16.2.01.07 | KHAZRA, MOOJAN | 7.5874 | 0.054831 | 7.5874 |  |  |  | 20.24% | 37.4908
DATA MGT MAINT | J.3.01.2.01.07 | RAZO, GUSTAVO | 45.3409 | 0.34836 | 45.3409 |  |  |  | 23.62% | 191.9345
DOM Next Gen Prototype | J.3.02.1.02.10 | KHAZRA, MOOJAN | -60.7224 | -0.49392 | -60.7224 |  |  |  | -58.67% | 103.4985
|  | TOTAL |  |  | -212.9755

## IDS
Account Title | Task Number | Task Manager |  |  |  | VARIANCE EXPLANATION (Variances/Major Drivers) | CORRECTIVE ACTION(s) (Action/Mitigation Plan) | Recovery Date | Variance to Plan | YTD Budget ($K) | Cost & Schedule Alignment
|  |  | COST YTD VAR | FTE YTD VAR | OBS YTD VAR
IDS MGMT | K.1.00.0.01.01 | DAHL, LUKE B | 32.0834 | 0.09849 | 32.0834 |  |  |  | 17.52% | 183.1153
IDS SYS ENG | K.1.00.0.01.03 | TINIO, ADRIAN W | 18.2411 | 0.33651 | 25.5751 |  |  |  | 13.71% | 186.5284
IDS I&T | K.1.00.0.01.06 | LEE, PHAN | 17.4653 | 0.17135 | 15.8288 |  |  |  | 9.755% | 162.2686
SYS SW-HW INF M | K.1.00.0.02.07 | FUNG, JANET G | 3.1136 | -0.02247 | 3.1136 |  |  |  | 1.115% | 279.3282
AIT | K.1.00.0.03.07 | JOYCE, MICHAEL J | -37.1076 | -0.60405 | -37.1076 |  |  |  | -34.97% | 106.1168
Sys SW Modernization | K.1.00.0.04.07 | DAHL, LUKE B | 92.647 | 0.34516 | 56.0683 |  |  |  | 33.75% | 166.1262
CWS 2.0 | K.1.00.1.06.10 | HOLLINS, GALEN A | -3.3276 | -0.05231 | -3.3276 |  |  |  | -8.821% | 37.7235
IDS EXP & TAC MAINT | K.1.00.2.01.07 | TINIO, ADRIAN W | 7.1473 | 0.0653 | 0.85873 |  |  |  | 0.4221% | 203.4464
Data Drive | K.2.02.1.06.10 | ALGERMISSEN, STIRLING S | 22.1814 | 0.32096 | -2.2795 |  |  |  | -2.142% | 106.4101
USER CONSULTANT | K.2.04.2.02.09 | DAHL, LUKE B | 0.28218 | 0.00721 | -0.5004 |  |  |  | -2.166% | 23.1073
CARGO | K.3.02.1.02.10 | RADULESCU, COSTIN | 4.7277 | 0.00286 | 4.7277 |  |  |  | 7.58% | 62.3682
MIST Restart | K.3.02.1.05.10 | DAHL, LUKE B | -23.555 | -0.12991 | -13.9174 |  |  |  | -53.37% | 26.0796
ASTRO Lien | K.3.02.1.08.10 | DAHL, LUKE B | -9.8626 | 0.10908 | -9.8626 |  |  |  | -7.262% | 135.8029
CCSDS Architecture Support | K.4.01.2.01.03 | DAHL, LUKE B | 19.1565 | 0.1477 | 18.6775 |  |  |  | 27.89% | 66.9717
Data Order via Uncertainty Est | K.4.02.1.01.10 | RADULESCU, COSTIN | -31.7741 | -0.12931 | -31.7741 |  |  |  | -53.66% | 59.2168
|  | TOTAL |  |  | 58.1641

## VLOOKUP (hidden)
| Project Number | Task Name | Task Number | Task Manager | Burdened Cost Var YTD | FTE Avg Variance YTD | Burdened Oblig Var YTD | Burd Oblig Budg YTD | Burdened Oblig YTD | Burd Oblig Budg FY | Task Completion
| Project Number | Task Name | Task Number | Task Manager | Burdened Cost Var YTD | FTE Avg Variance YTD | Burdened Oblig Var YTD | Burd Oblig Budg YTD | Burdened Oblig YTD | Burd Oblig Budg FY | Task Completion Date
Sort | 1 |  | 2
A/D | A |  | A | [10 empty] | TASK CHECK
Sub | [13 empty] | MGMT | BO | ESO | I&P | NMD | MDAS | MPS | IOS | RMO | TECH | MISSING IF 0
59 | 106464 | Undistributed Labor | 99 | UNKNOWN | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Undistributed Labor | Undistributed Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 106410 | MISSION INT OFFICE | A.1.01.0.04.01 | ELLIOTT, ROBERT G | 98323.8279 | 0.6174 | 98390.9879 | 496734.2679 | 401715.58 | 592098.2265 | 2020-09-27 | MISSION INT OFFICE | MISSION INT OFFICE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
1 | 106411 | Integrated AMMOS | C.2.07.1.14.10 | NGUYEN, VU H | -7629.7861 | -0.038052 | -14487.3785 | 139431.6339 | 180327.6285 | 196925.2443 | 2020-09-27 | Integrated AMMOS | Integrated AMMOS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2 | 106410 | RELAY SYS ENG | M.1.00.0.01.03 | CALL, JARED A | -5780.0202 | -0.02698 | -5780.0202 | 192891.6399 | 198671.66 | 211154.3612 | 2020-09-27 | RELAY SYS ENG | RELAY SYS ENG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
3 | 106413 | Advance MPSA | H.3.01.1.20.10 | CHAFIN, BRIAN G | 60114.0994 | 0.30362 | 60114.0994 | 627098.1194 | 566984.02 | 684766.7279 | 2020-09-27 | Advance MPSA | Advance MPSA | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
4 | 106464 | Data Drive | K.2.02.1.06.10 | ALGERMISSEN, STIRLING S | 22181.413 | 0.32096 | -2279.4889 | 106410.1429 | 108689.6318 | 82626.4367 | 2020-09-27 | Data Drive | Data Drive | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
5 | 106412 | SPICE MAINT | G.4.01.2.01.07 | ACTON, CHARLES H JR | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | SPICE MAINT | SPICE MAINT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 106413 | Web Interface | H.2.01.1.06.10 | CHAFIN, BRIAN G | -1080.65 | 0 | -1080.65 | 0 | 1080.65 | 0 | 2020-09-27 | Web Interface | Web Interface | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
7 | 106412 | Primitive Body Nav | G.2.01.1.10.10 | PAVLAK, DR. THOMAS A | -19397.0154 | -0.05086 | -54771.2772 | 68704.1046 | 123475.3818 | 80330.7269 | 2020-09-27 | Primitive Body Nav | Primitive Body Nav | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
8 | 106464 | Data Order via Uncertainty Est | K.4.02.1.01.10 | RADULESCU, COSTIN | -31774.0669 | -0.12931 | -31774.0669 | 59216.8131 | 90990.88 | 69512.8183 | 2020-09-27 | Data Order via Uncertainty Est | Data Order via Uncertainty Est | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
9 | 106413 | MPS MGMT | H.1.00.0.00.01 | CHAFIN, BRIAN G | 35610.6699 | 0.15699 | 35610.6699 | 187299.0799 | 151688.41 | 232869.5469 | 2020-09-27 | MPS MGMT | MPS MGMT | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
10 | 106463 | MCS SYS ENG | J.1.00.0.00.03 | KHAZRA, MOOJAN | -80921.9655 | -0.46872 | -79489.8622 | 231909.3944 | 312831.36 | 259588.7856 | 2020-09-27 | MCS SYS ENG | MCS SYS ENG | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
11 | 106463 | MCS TEST ENG | J.1.00.0.00.06 | SHAMILIAN, ARSHALUYS | -30164.1649 | -0.31023 | -22450.3629 | 248716.5552 | 293637.4073 | 326273.6004 | 2020-09-27 | MCS TEST ENG | MCS TEST ENG | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
12 | 106464 | IDS SYS ENG | K.1.00.0.01.03 | TINIO, ADRIAN W | 18241.0578 | 0.33651 | 25575.1375 | 186528.3978 | 160953.2603 | 213391.0571 | 2020-09-27 | IDS SYS ENG | IDS SYS ENG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
13 | 106410 | BUSINESS MGT | B.1.01.0.01.02 | DI PAOLO, RUSSELL M | 12613.7563 | 0.06169 | 12613.7563 | 134127.4163 | 121513.66 | 149030.3736 | 2020-09-27 | BUSINESS MGT | BUSINESS MGT | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
14 | 106410 | BUSINESS SCHED | B.1.01.0.04.02 | DI PAOLO, RUSSELL M | -3229.1272 | 0.00249 | -3229.1272 | 208361.2428 | 211590.37 | 201717.7281 | 2020-09-27 | BUSINESS SCHED | BUSINESS SCHED | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15 | 106412 | PLANETARY EPHEMERIS | G.5.01.2.01.09 | PARK, DR. SANG H | 7374.1117 | -0.092647 | 6797.6398 | 282540.8117 | 322074.0774 | 396793.6551 | 2020-09-27 | PLANETARY EPHEMERIS | PLANETARY EPHEMERIS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
16 | 106412 | GRAVITY MODELLING | G.5.04.2.01.09 | PARK, DR. SANG H | -15876.6204 | -0.34271 | -29285.8066 | 103395.9596 | 179012.6718 | 185958.0322 | 2020-09-27 | GRAVITY MODELLING | GRAVITY MODELLING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
17 | 106413 | SEQUENCING FOR CUBES | H.3.01.1.16.10 | CHAFIN, BRIAN G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | SEQUENCING FOR CUBES | SEQUENCING FOR CUBES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 106412 | MODERNIZING SPICE | G.4.01.1.05.10 | ACTON, CHARLES H JR | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | MODERNIZING SPICE | MODERNIZING SPICE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 106464 | Search Data Driven Analytics | K.4.02.1.03.10 | ALGERMISSEN, STIRLING S | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Search Data Driven Analytics | Search Data Driven Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 106463 | Ref Msn T/C Closed Loop Framewrk | J.2.16.1.02.10 | SUN, QUENTIN | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Ref Msn T/C Closed Loop Framewrk | Ref Msn T/C Closed Loop Framewrk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 106463 | MCS SYS LVL MAINT | J.1.00.0.00.07 | KHAZRA, MOOJAN | -141492.7925 | -1.2639 | -141492.7925 | 324093.9075 | 465586.7 | 340421.7391 | 2020-09-27 | MCS SYS LVL MAINT | MCS SYS LVL MAINT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
27 | 106463 | MC D/L PROC PERF IMP | J.2.02.1.03.10 | DEFORREST, LLOYD R | -14198.73 | 0 | -2725.0001 | 0 | 2725.0001 | 0 | 2020-09-27 | MC D/L PROC PERF IMP | MC D/L PROC PERF IMP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
28 | 106463 | TDAC - Maintenance | J.2.16.2.01.07 | KHAZRA, MOOJAN | 7587.4397 | 0.054831 | 7587.4397 | 37490.7997 | 29903.36 | 68602.519 | 2020-09-27 | TDAC - Maintenance | TDAC - Maintenance | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
29 | 106463 | Chill Mon Rep Dev Testing | J.1.00.1.05.10 | KHAZRA, MOOJAN | 17310.4736 | 0.1866 | 17310.4736 | 29100.8736 | 11790.4 | 36398.7156 | 2020-09-27 | Chill Mon Rep Dev Testing | Chill Mon Rep Dev Testing | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
30 | 106464 | AFIDS Follow-On | K.1.00.1.10.10 | LOGAN, DR. THOMAS L | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | AFIDS Follow-On | AFIDS Follow-On | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 106464 | AIT | K.1.00.0.03.07 | JOYCE, MICHAEL J | -37107.5957 | -0.60405 | -37107.5957 | 106116.7943 | 143224.39 | 83147.2044 | 2020-09-27 | AIT | AIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
32 | 106412 | Automated RMM Design & Implemntn | G.2.01.1.12.10 | GARCIA, MARK D | 68539.9109 | 0.41271 | 68539.9109 | 106542.1609 | 38002.25 | 170407.6605 | 2020-09-27 | Automated RMM Design & Implemntn | Automated RMM Design & Implemntn | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
33 | 106464 | 3D Polygonal Mesh & Points | K.3.02.1.01.10 | DAHL, LUKE B | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | 3D Polygonal Mesh & Points | 3D Polygonal Mesh & Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 106409 | Interactive Data Vis | 04.01.14 | STUART, JEFFREY R | -13137.0518 | 0.23345 | 3115.311 | 66836.6682 | 63721.3572 | 71504.1382 | 2020-09-27 | Interactive Data Vis | Interactive Data Vis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
35 | 106464 | USER CONSULTANT | K.2.04.2.02.09 | DAHL, LUKE B | 282.1795 | 0.00721 | -500.4005 | 23107.2895 | 23607.69 | 28578.713 | 2020-09-27 | USER CONSULTANT | USER CONSULTANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
36 | 106411 | MM GDS ENG | C.2.01.2.10.03 | O'BRIEN, ROBIN A | -8950.762 | -0.10229 | -9635.342 | 158461.8379 | 168097.18 | 190017.0791 | 2020-09-27 | MM GDS ENG | MM GDS ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
37 | 106411 | MGSS Tools Maint & R | C.2.07.2.09.07 | O'BRIEN, ROBIN A | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | MGSS Tools Maint & R | MGSS Tools Maint & R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 106411 | MM INT & TEST DEP SE | C.2.07.2.17.03 | MARKHAM, SCOTT D | 10069.7675 | 0.06692 | 10069.7675 | 175272.0275 | 165202.26 | 212105.8196 | 2020-09-27 | MM INT & TEST DEP SE | MM INT & TEST DEP SE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
39 | 106412 | MIRAGE MONTE MIGRATI | G.2.01.1.08.10 | PARK, DR. SANG H | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | MIRAGE MONTE MIGRATI | MIRAGE MONTE MIGRATI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 106411 | GDS Security | C.2.07.2.24.03 | PAJEVSKI, MICHAEL J | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | GDS Security | GDS Security | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
41 | 106464 | ASTRO Lien | K.3.02.1.08.10 | DAHL, LUKE B | -9862.6102 | 0.10908 | -9862.6102 | 135802.8898 | 145665.5 | 144028.0967 | 2020-09-27 | ASTRO Lien | ASTRO Lien | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
42 | 106413 | Automated Planning | H.2.01.1.03.10 | CHAFIN, BRIAN G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Automated Planning | Automated Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 106413 | Activity Plng Fidelity & Speed Enhance | H.2.01.1.07.10 | CHAFIN, BRIAN G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Activity Plng Fidelity & Speed Enhance | Activity Plng Fidelity & Speed Enhance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 106413 | Automated Plan Expansion | H.2.01.1.04.10 | CHAFIN, BRIAN G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Automated Plan Expansion | Automated Plan Expansion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 106410 | RELAY I&T | M.1.00.0.01.06 | CALL, JARED A | 13263.7079 | -0.11881 | 13263.7079 | 129203.5279 | 115939.82 | 143132.3518 | 2020-09-27 | RELAY I&T | RELAY I&T | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
46 | 106409 | Miss Ops Desg and Analysis | 03.01.15 | CHIEN, DR. STEVE A | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Miss Ops Desg and Analysis | Miss Ops Desg and Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 106463 | HI PERF TELEM QUERY | J.2.15.1.02.10 | DEFORREST, LLOYD R | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | HI PERF TELEM QUERY | HI PERF TELEM QUERY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 106413 | SOA Rearchitecture | H.2.01.1.05.10 | CHAFIN, BRIAN G | 7131.3507 | 0.036198 | 7131.3507 | 28446.0607 | 21314.71 | 20368.5714 | 2020-09-27 | SOA Rearchitecture | SOA Rearchitecture | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
49 | 106412 | Astrodynamics Tech Infusion | G.7.01.1.01.10 | EVANS, DR. SCOTT E | -65797.1417 | -0.33794 | -65797.1417 | 85849.4783 | 151646.62 | 102929.6346 | 2020-09-27 | Astrodynamics Tech Infusion | Astrodynamics Tech Infusion | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
50 | 106409 | Deep LRN and PRO ID | 04.01.15 | TORGERSON, JORDAN L | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Deep LRN and PRO ID | Deep LRN and PRO ID | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 106413 | SEQ SUBSYSTEM TEST | H.1.00.0.00.06 | CHAFIN, BRIAN G | 143424.2342 | 1.1037 | 143424.2342 | 438500.1742 | 295075.94 | 418685.6324 | 2020-09-27 | SEQ SUBSYSTEM TEST | SEQ SUBSYSTEM TEST | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
52 | 106463 | MCS MGT | J.1.00.0.00.01 | KHAZRA, MOOJAN | 2991.024 | -0.03214 | 2991.024 | 153074.504 | 150083.48 | 184918.7464 | 2020-09-27 | MCS MGT | MCS MGT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
53 | 106463 | TSDB Integration | J.2.02.1.06.10 | KHAZRA, MOOJAN | 27434.5231 | 0.33498 | 27434.5231 | 122813.7231 | 95379.2 | 49674.7755 | 2020-09-27 | TSDB Integration | TSDB Integration | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
54 | 106410 | BUSINESS SPT | B.1.01.0.02.02 | DI PAOLO, RUSSELL M | 29348.2379 | 0.22021 | 29348.2379 | 188431.5579 | 159083.32 | 187799.5302 | 2020-09-27 | BUSINESS SPT | BUSINESS SPT | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
55 | 106410 | MGSS IMP & PLNG | E.1.00.0.00.01 | GUNN, JOHANNA M | 489.8294 | -0.09115 | 489.8268 | 211312.1794 | 210822.3527 | 262138.0818 | 2020-09-27 | MGSS IMP & PLNG | MGSS IMP & PLNG | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
56 | 106411 | SOFTWARE SYS ENG | C.2.01.2.13.03 | PAJEVSKI, MICHAEL J | 5516.2204 | 0.055739 | 6197.144 | 23038.9604 | 17522.74 | 27904.9483 | 2020-09-27 | SOFTWARE SYS ENG | SOFTWARE SYS ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
57 | 106411 | INS INF FAC & NET | C.2.07.2.20.03 | O'BRIEN, ROBIN A | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | INS INF FAC & NET | INS INF FAC & NET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 106412 | ONIPS MODERNIZATION | G.2.02.1.05.10 | EVANS, DR. SCOTT E | -14131.9355 | -0.37673 | -14131.9355 | 141932.5545 | 156064.49 | 166042.974 | 2020-09-27 | ONIPS MODERNIZATION | ONIPS MODERNIZATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
19 | 106412 | Nav Sanity Check Tool | G.2.01.1.13.10 | EVANS, DR. SCOTT E | -106.03 | 0 | -106.03 | 0 | 106.03 | 0 | 2020-09-27 | Nav Sanity Check Tool | Nav Sanity Check Tool | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
60 | 106412 | Undistributed Labor | 99 | UNKNOWN | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Undistributed Labor | Undistributed Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 106411 | I&T VALIDATION | C.2.07.2.04.06 | MARKHAM, SCOTT D | 36792.3715 | 0.17872 | 7366.2707 | 522389.7915 | 515023.5208 | 698679.6193 | 2020-09-27 | I&T VALIDATION | I&T VALIDATION | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
62 | 106413 | MAROS MAINT | H.1.00.2.01.07 | CALL, JARED A | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | MAROS MAINT | MAROS MAINT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 106463 | DATA MGT MAINT | J.3.01.2.01.07 | RAZO, GUSTAVO | 45340.948 | 0.34836 | 45340.948 | 191934.478 | 146593.53 | 220321.4531 | 2020-09-27 | DATA MGT MAINT | DATA MGT MAINT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
64 | 106463 | AMPCS Pass Automation | J.2.07.1.12.10 | KHAZRA, MOOJAN | -25668.3873 | -0.19745 | -25668.3873 | 56806.6127 | 82475 | 65153.1671 | 2020-09-27 | AMPCS Pass Automation | AMPCS Pass Automation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
65 | 106411 | CSE | C.2.08.2.07.07 | PAJEVSKI, MICHAEL J | 74146.6252 | 0.01045 | 79647.4187 | 183039.2552 | 147174.5423 | 335704.0923 | 2020-09-27 | CSE | CSE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
66 | 106409 | Program Office | 01.01.01 | WYATT, E JAY | 7727.3474 | 0.055264 | 7727.3474 | 65549.5274 | 57822.18 | 90589.1719 | 2020-09-27 | Program Office | Program Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
67 | 106409 | Next Gen Plan & Seq | 03.01.13 | CHIEN, DR. STEVE A | 22589.8914 | 0.22611 | 22589.8914 | 57435.7113 | 34845.82 | 51394.3506 | 2020-09-27 | Next Gen Plan & Seq | Next Gen Plan & Seq | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
68 | 106410 | AMMOS PROG ADMIN | A.1.01.0.02.01 | PONS, JUDITH S | 57278.6788 | 0.22938 | 56971.4803 | 237046.5588 | 180075.0785 | 239099.4104 | 2020-09-27 | AMMOS PROG ADMIN | AMMOS PROG ADMIN | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
69 | 106411 | COMPUTE PLATFORM ENG | C.2.07.2.19.03 | NGUYEN, VU H | 13715.2457 | 0.09011 | -9250.9511 | 154372.4057 | 242385.8963 | 294483.8851 | 2020-09-27 | COMPUTE PLATFORM ENG | COMPUTE PLATFORM ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
70 | 106411 | SEC PLAN-H/W-LIC | C.2.07.2.21.03 | O'BRIEN, ROBIN A | -14770.4663 | 0.03874 | -19009.8056 | 142502.1737 | 161511.9793 | 306723.0801 | 2020-09-27 | SEC PLAN-H/W-LIC | SEC PLAN-H/W-LIC | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
71 | 106412 | MDN MANAGEMENT | G.1.00.0.00.01 | BERRY, DAVID S | -3912.0222 | -0.057008 | -3912.0222 | 103735.7478 | 107647.77 | 130256.7976 | 2020-09-27 | MDN MANAGEMENT | MDN MANAGEMENT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
72 | 106412 | Monte NIDO Replacement | G.2.01.1.14.10 | EVANS, DR. SCOTT E | -1920.26 | 0 | -1920.26 | 0 | 1920.26 | 0 | 2020-09-27 | Monte NIDO Replacement | Monte NIDO Replacement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
73 | 106413 | Web Int for Plan Maint | H.1.00.2.02.07 | CHAFIN, BRIAN G | -14088.8399 | -0.11542 | -14088.8399 | 11210.0501 | 25298.89 | 11340.3115 | 2020-09-27 | Web Int for Plan Maint | Web Int for Plan Maint | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
74 | 106463 | AMPCS SLE CFDP DEV | J.2.07.1.09.10 | DEFORREST, LLOYD R | -1255.2 | 0 | -1255.2 | 0 | 1255.2 | 0 | 2020-09-27 | AMPCS SLE CFDP DEV | AMPCS SLE CFDP DEV | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
75 | 106412 | MONTE MAINT | G.2.01.2.02.07 | EVANS, DR. SCOTT E | 80085.6095 | 0.69203 | 80032.0295 | 250454.0195 | 170421.99 | 287849.9384 | 2020-09-27 | MONTE MAINT | MONTE MAINT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
76 | 106411 | Config MGMT Mainten | C.2.04.2.01.08 | SHIN, SEUNG H | 18088.3638 | 0.05626 | 17459.5706 | 97029.5438 | 79569.9732 | 117192.0536 | 2020-09-27 | Config MGMT Mainten | Config MGMT Mainten | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
77 | 106413 | S/C Analysis Maint | H.5.01.2.01.07 | CHEUNG, DR. KAR-MING | 20812.4083 | 0.16079 | 20812.4083 | 113018.7583 | 92206.35 | 127532.8316 | 2020-09-27 | S/C Analysis Maint | S/C Analysis Maint | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
78 | 106463 | DOM Next Gen Prototype | J.3.02.1.02.10 | KHAZRA, MOOJAN | -60722.3649 | -0.49392 | -60722.3649 | 103498.4851 | 164220.85 | 115825.3787 | 2020-09-27 | DOM Next Gen Prototype | DOM Next Gen Prototype | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
79 | 106463 | INFO ARCH STANDARDS | J.1.00.0.02.03 | KHAZRA, MOOJAN | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | INFO ARCH STANDARDS | INFO ARCH STANDARDS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
80 | 106463 | INTEGRATED COMMAND | J.2.02.1.04.10 | DEFORREST, LLOYD R | -1427.07 | 0 | -1427.07 | 0 | 1427.07 | 0 | 2020-09-27 | INTEGRATED COMMAND | INTEGRATED COMMAND | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
81 | 106464 | IDS MVOR | K.3.01.1.07.10 | DAHL, LUKE B | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | IDS MVOR | IDS MVOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 106464 | Sys SW Modernization | K.1.00.0.04.07 | DAHL, LUKE B | 92646.9525 | 0.34516 | 56068.2744 | 166126.1625 | 144806.0673 | 299968.4397 | 2020-09-27 | Sys SW Modernization | Sys SW Modernization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
83 | 106409 | DATA DRIVEN EXPLORER | 05.01.13 | LIGHTHOLDER, JACK A | -24903.727 | -0.15988 | -24903.727 | 73346.323 | 98250.05 | 74529.1174 | 2020-09-27 | DATA DRIVEN EXPLORER | DATA DRIVEN EXPLORER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
84 | 106410 | AMMOS PROG MGMT | A.1.01.0.01.01 | PONS, JUDITH S | -13504.1802 | 0.00756 | -24934.4401 | 415818.6498 | 446104.93 | 558403.35 | 2020-09-27 | AMMOS PROG MGMT | AMMOS PROG MGMT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
85 | 106412 | MONTE/MASAR PDM | G.1.00.0.01.01 | EVANS, DR. SCOTT E | -22043.6686 | -0.1157 | -22043.6686 | 150055.0814 | 172098.75 | 176855.4864 | 2020-09-27 | MONTE/MASAR PDM | MONTE/MASAR PDM | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
86 | 106412 | POINCARE | G.2.01.1.09.10 | VAQUERO ESCRIBANO, DR. TATIANA MAR | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | POINCARE | POINCARE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 106412 | Monte/Masar "SparQ" 3D Viz Enh | G.3.01.1.03.10 | EVANS, DR. SCOTT E | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Monte/Masar "SparQ" 3D Viz Enh | Monte/Masar "SparQ" 3D Viz Enh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 106411 | Config Module Imp | C.2.08.1.13.10 | GIESELMAN, KENNETH G | 7482.7355 | 0 | 0.42735 | 107719.3555 | 178952.6955 | 154500 | 2020-09-27 | Config Module Imp | Config Module Imp | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
89 | 106413 | Search Data Driven Analytics | H.5.01.1.01.10 | CHAFIN, BRIAN G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Search Data Driven Analytics | Search Data Driven Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 106410 | MaROS Parameter Validation | M.1.00.1.02.10 | CALL, JARED A | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | MaROS Parameter Validation | MaROS Parameter Validation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 106411 | Behavior Recon | C.2.08.1.09.10 | PAJEVSKI, MICHAEL J | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Behavior Recon | Behavior Recon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 106411 | MGSS Configuration M | C.2.04.2.01.04 | SHIN, SEUNG H | 9001.5849 | 0.28599 | 9001.5849 | 310922.4949 | 301920.91 | 366823.8288 | 2020-09-27 | MGSS Configuration M | MGSS Configuration M | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
93 | 106412 | Nav Evolution | G.6.03.2.01.03 | WOOD, DR. LINCOLN J | 0 | 0 | 0 | 0 | 0 | 0 | 2018-09-30 | Nav Evolution | Nav Evolution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 106410 | RELAY MAINT | M.1.00.0.01.07 | CALL, JARED A | -21228.6515 | -0.2587 | -21228.6515 | 57141.3085 | 78369.96 | 66497.6921 | 2020-09-27 | RELAY MAINT | RELAY MAINT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
95 | 106412 | NAV SW AUTOMA MAINT | G.2.01.2.03.07 | TABER, DR. WILLIAM L | 927.9973 | -0.019257 | 927.9973 | 44824.3073 | 43896.31 | 52584.7654 | 2020-09-27 | NAV SW AUTOMA MAINT | NAV SW AUTOMA MAINT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
96 | 106464 | IDS EXP & TAC MAINT | K.1.00.2.01.07 | TINIO, ADRIAN W | 7147.2677 | 0.0653 | 858.7337 | 203446.4477 | 202587.714 | 231210.1022 | 2020-09-27 | IDS EXP & TAC MAINT | IDS EXP & TAC MAINT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
97 | 106411 | AMMOS CATALOG | C.2.09.2.02.03 | BENECKEN, ZSARINA | 14137.8467 | 0 | 28315.1038 | 20060.6567 | 5922.81 | 44852 | 2020-09-27 | AMMOS CATALOG | AMMOS CATALOG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
98 | 106412 | Statistical Navigation Truth Sim | G.2.01.1.11.10 | EVANS, DR. SCOTT E | 56987.8701 | 0.4175 | 56987.8701 | 88837.3701 | 31849.5 | 105699.3587 | 2020-09-27 | Statistical Navigation Truth Sim | Statistical Navigation Truth Sim | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
99 | 106464 | IDS MGMT | K.1.00.0.01.01 | DAHL, LUKE B | 32083.4311 | 0.09849 | 32083.4311 | 183115.3011 | 151031.87 | 224247.4052 | 2020-09-27 | IDS MGMT | IDS MGMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
100 | 106464 | IDS I&T | K.1.00.0.01.06 | LEE, PHAN | 17465.3146 | 0.17135 | 15828.8246 | 162268.5646 | 146439.74 | 177059.7114 | 2020-09-27 | IDS I&T | IDS I&T | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
101 | 106463 | MCWS New Dev | J.2.02.1.02.10 | KHAZRA, MOOJAN | 23476.6453 | 0.21826 | 23476.6453 | 84768.6853 | 61292.04 | 85861.5474 | 2020-09-27 | MCWS New Dev | MCWS New Dev | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
102 | 106409 | Low-Thrust Opt | 04.01.13 | ANDERSON, DR. RODNEY L | 320.4263 | -0.014757 | 320.4263 | 50247.1763 | 49926.75 | 72479.9039 | 2020-09-27 | Low-Thrust Opt | Low-Thrust Opt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
103 | 106410 | CUSTOMER DEVELOPMENT | B.1.02.0.01.02 | ELLIOTT, ROBERT G | 18205.7804 | 0.14904 | -976.8396 | 61531.0004 | 62507.84 | 87930.896 | 2020-09-27 | CUSTOMER DEVELOPMENT | CUSTOMER DEVELOPMENT | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
104 | 106411 | MM GDS SUPPORT | C.2.07.2.16.03 | O'BRIEN, ROBIN A | 153974.0997 | 1.0717 | 153974.0997 | 309794.0897 | 155819.99 | 328579.1944 | 2020-09-27 | MM GDS SUPPORT | MM GDS SUPPORT | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
105 | 106412 | LANDMARK TRACKING SW | G.2.02.1.04.10 | VAUGHAN, ANDREW T | 16630.84 | 0 | -1389.5015 | 0 | 1389.5015 | 0 | 2020-09-27 | LANDMARK TRACKING SW | LANDMARK TRACKING SW | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
106 | 106409 | Autonomy Evaluation | 01.01.02 | CASTANO, DR. REBECCA | 44424.8055 | 0.33241 | 44424.8055 | 57526.0555 | 13101.25 | 25280.4614 | 2020-09-27 | Autonomy Evaluation | Autonomy Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
107 | 106463 | Sys Admin & Dep SUPT | J.1.00.0.01.03 | KHAZRA, MOOJAN | 34579.363 | 0 | 34579.363 | 137008.063 | 102428.7 | 292900 | 2020-09-27 | Sys Admin & Dep SUPT | Sys Admin & Dep SUPT | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
108 | 106464 | IDS TOOL BOX | K.2.01.1.07.10 | DEEN, ROBERT G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | IDS TOOL BOX | IDS TOOL BOX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 106464 | Prod Generation Acct | K.1.00.1.07.10 | FUNG, JANET G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Prod Generation Acct | Prod Generation Acct | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 106463 | Search Data Driven Analytics | J.3.02.1.03.10 | KHAZRA, MOOJAN | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Search Data Driven Analytics | Search Data Driven Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 106411 | CROSS CUT SEC ENHANCE | C.2.08.1.08.10 | PAJEVSKI, MICHAEL J | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | CROSS CUT SEC ENHANCE | CROSS CUT SEC ENHANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 106464 | CCSDS Architecture Support | K.4.01.2.01.03 | DAHL, LUKE B | 19156.5271 | 0.1477 | 18677.5071 | 66971.7171 | 48294.21 | 85410.3769 | 2020-09-27 | CCSDS Architecture Support | CCSDS Architecture Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
113 | 106411 | GDS Security | C.2.07.1.13.10 | PAJEVSKI, MICHAEL J | 34782.1348 | 0.07211 | 35277.3294 | 240488.4248 | 222006.0486 | 395107.5716 | 2020-09-27 | GDS Security | GDS Security | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
114 | 106411 | ASEC MAINT | C.2.08.2.05.08 | PAJEVSKI, MICHAEL J | -12048.5596 | -0.1232 | -16093.4426 | 283966.1604 | 309904.9205 | 396099.6253 | 2020-09-27 | ASEC MAINT | ASEC MAINT | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
115 | 106413 | Advanced Planning & Sequencing | H.1.00.1.11.10 | CHAFIN, BRIAN G | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Advanced Planning & Sequencing | Advanced Planning & Sequencing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 106464 | CARGO | K.3.02.1.02.10 | RADULESCU, COSTIN | 4727.7413 | 0.00286 | 4727.7413 | 62368.1712 | 57640.43 | 70367.4675 | 2020-09-27 | CARGO | CARGO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
117 | 106464 | CWS 2.0 | K.1.00.1.06.10 | HOLLINS, GALEN A | -3327.5713 | -0.05231 | -3327.5713 | 37723.4987 | 41051.07 | 41245.8374 | 2020-09-27 | CWS 2.0 | CWS 2.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
118 | 106464 | MM GEOGRAPH INFO SYS | K.2.01.1.06.10 | CALEF, DR. FRED J | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | MM GEOGRAPH INFO SYS | MM GEOGRAPH INFO SYS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 106411 | AMMOS CubeSat Support | C.2.07.2.25.09 | MARKHAM, SCOTT D | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | AMMOS CubeSat Support | AMMOS CubeSat Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 106464 | MIST Restart | K.3.02.1.05.10 | DAHL, LUKE B | -23555.0292 | -0.12991 | -13917.4455 | 26079.6408 | 49634.67 | 85160.6507 | 2020-09-27 | MIST Restart | MIST Restart | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
121 | 106409 | AMMOS DTN PILOT IMP | 02.01.12 | TORGERSON, JORDAN L | -743.886 | 0.03997 | -743.886 | 43508.834 | 44252.72 | 43503.623 | 2020-09-27 | AMMOS DTN PILOT IMP | AMMOS DTN PILOT IMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
122 | 106411 | MGSS Sys Engr | C.2.01.2.01.03 | RADULESCU, COSTIN | -10981.2271 | -0.02326 | -6437.6691 | 178870.8229 | 187646.62 | 222395.4236 | 2020-09-27 | MGSS Sys Engr | MGSS Sys Engr | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
123 | 106411 | SEO SECURITY | C.2.01.2.11.03 | PAJEVSKI, MICHAEL J | -1293.1761 | 0.04085 | -1293.1761 | 56694.6739 | 57987.85 | 65620.2483 | 2020-09-27 | SEO SECURITY | SEO SECURITY | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
125 | 106411 | MGSS - IMS | C.2.06.2.01.03 | MCCLEARY, JENNIFER M | 29458.1288 | 0.15053 | 29461.1741 | 95435.6988 | 65974.5247 | 107650.6892 | 2020-09-27 | MGSS - IMS | MGSS - IMS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
126 | 106411 | MM DEPLOYMENT ENG | C.2.07.2.18.03 | MARKHAM, SCOTT D | -9362.8962 | -0.01342 | -9362.8962 | 125538.6338 | 134901.53 | 133676.0898 | 2020-09-27 | MM DEPLOYMENT ENG | MM DEPLOYMENT ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
127 | 106411 | ASIS | C.2.08.2.01.10 | PAJEVSKI, MICHAEL J | -1010.7805 | -0.04116 | 1484.4528 | 323466.6195 | 370629.6176 | 540460.3132 | 2020-09-27 | ASIS | ASIS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
128 | 106411 | REF MISSION SYSTEMS | C.2.09.2.04.03 | RADULESCU, COSTIN | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | REF MISSION SYSTEMS | REF MISSION SYSTEMS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
129 | 106412 | MDN SOFTWARE ADV | G.2.01.1.06.10 | EVANS, DR. SCOTT E | 70527.982 | 0.50408 | 5664.862 | 132332.312 | 126667.45 | 156087.7434 | 2020-09-27 | MDN SOFTWARE ADV | MDN SOFTWARE ADV | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
130 | 106412 | MONTE TRAIN & CUST SUPT | G.2.01.2.02.10 | EVANS, DR. SCOTT E | -3392.9781 | -0.078403 | -35670.7348 | 14236.2419 | 67860.2026 | 28429.0462 | 2020-09-27 | MONTE TRAIN & CUST SUPT | MONTE TRAIN & CUST SUPT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
131 | 106411 | MGSS PORT CHARGES | C.2.07.2.08.09 | MARKHAM, SCOTT D | -4614.5241 | 0 | -4614.5241 | 41163.2259 | 45777.75 | 88000 | 2020-09-27 | MGSS PORT CHARGES | MGSS PORT CHARGES | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
132 | 106412 | MDN PORT CHARGES | G.1.00.0.00.08 | GERASIMATOS, DIMITRIOS V | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | MDN PORT CHARGES | MDN PORT CHARGES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 106411 | ENT SYS MGMT | C.2.08.1.05.10 | PAJEVSKI, MICHAEL J | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | ENT SYS MGMT | ENT SYS MGMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 106409 | PATCH | 05.01.14 | RADULESCU, COSTIN | 37777.8388 | 0.23725 | 37777.8388 | 82975.5088 | 45197.67 | 57293.1623 | 2020-09-27 | PATCH | PATCH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
135 | 106411 | REF MISSION SYSTEMS | C.2.09.1.01.10 | STRANGE, NATHAN J | 84786.8874 | 0.42192 | 82758.7812 | 339613.8874 | 263702.2241 | 544247.1057 | 2020-09-27 | REF MISSION SYSTEMS | REF MISSION SYSTEMS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
136 | 106413 | MPS MAINT NEW | H.1.00.0.00.07 | CHAFIN, BRIAN G | -115600.3597 | -0.819 | -165634.4744 | 290332.1103 | 455966.5847 | 328237.9708 | 2020-09-27 | MPS MAINT NEW | MPS MAINT NEW | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
137 | 106464 | SYS SW-HW INF M | K.1.00.0.02.07 | FUNG, JANET G | 3113.6487 | -0.02247 | 3113.6487 | 279328.2087 | 276214.56 | 394009.5435 | 2020-09-27 | SYS SW-HW INF M | SYS SW-HW INF M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
138 | 106411 | SDDA | C.2.08.1.07.10 | RADULESCU, COSTIN | 48346.7687 | 0.40195 | 48346.7687 | 92222.9587 | 43876.19 | 149593.3582 | 2020-09-27 | SDDA | SDDA | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
139 | 106413 | CAST | H.1.00.1.08.10 | CHAFIN, BRIAN G | -1567.18 | 0 | -1567.18 | 0 | 1567.18 | 0 | 2020-09-27 | CAST | CAST | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
140 | 106464 | Mesh Geomtry Streaming & Dist | K.2.04.1.01.10 | DAHL, LUKE B | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Mesh Geomtry Streaming & Dist | Mesh Geomtry Streaming & Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 106413 | MGSS SEQ SE | H.1.00.0.00.03 | CHAFIN, BRIAN G | -2224.323 | -0.05349 | -2220.6036 | 368834.777 | 371055.3806 | 557123.0391 | 2020-09-27 | MGSS SEQ SE | MGSS SEQ SE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
142 | 106413 | SERVICE MANAGEMENT I | H.3.01.1.10.10 | TUNG, DR. YU-WEN | -750.06 | 0 | -750.06 | 0 | 750.06 | 0 | 2020-09-27 | SERVICE MANAGEMENT I | SERVICE MANAGEMENT I | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
143 | 106413 | BEHAVIORAL RECON CAP | H.3.01.1.19.10 | CHEUNG, DR. KAR-MING | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | BEHAVIORAL RECON CAP | BEHAVIORAL RECON CAP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 106409 | Auto Sys Interfaces | 03.01.14 | CHIEN, DR. STEVE A | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | Auto Sys Interfaces | Auto Sys Interfaces | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 106411 | SYS ARCH & ENG | C.2.01.2.12.03 | PAJEVSKI, MICHAEL J | 85611.7273 | 0.45064 | 85611.7273 | 352107.9173 | 266496.19 | 403968.3916 | 2020-09-27 | SYS ARCH & ENG | SYS ARCH & ENG | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
146 | 106411 | SYS ENG SA | C.2.07.2.22.03 | CASTILLO, OSCAR | -21236.5493 | 0 | -21236.5493 | 248286.5008 | 269523.05 | 440304 | 2020-09-27 | SYS ENG SA | SYS ENG SA | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
147 | 106411 | COMMON LOGGING SVC | C.2.08.1.06.10 | PAJEVSKI, MICHAEL J | -18531.37 | 0 | -9064.6622 | 0 | 9064.6622 | 0 | 2020-09-27 | COMMON LOGGING SVC | COMMON LOGGING SVC | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
148 | 106412 | MDN SYS ENG | G.1.00.0.00.03 | GERASIMATOS, DIMITRIOS V | -44125.2943 | -0.29116 | -44125.2943 | 143521.1757 | 187646.47 | 174988.6056 | 2020-09-27 | MDN SYS ENG | MDN SYS ENG | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
149 | 106412 | SATELLITE EPHEMERIS | G.5.02.2.01.09 | PARK, DR. SANG H | -48762.7602 | -0.40183 | -63041.5064 | 261515.6998 | 373698.3618 | 377493.9872 | 2020-09-27 | SATELLITE EPHEMERIS | SATELLITE EPHEMERIS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
20 | 106412 | CMT/AST EPHEMERIS | G.5.03.2.01.09 | PARK, DR. SANG H | 10836.6742 | -0.42048 | 28801.8742 | 359751.7042 | 348935.43 | 459747.9803 | 2020-09-27 | CMT/AST EPHEMERIS | CMT/AST EPHEMERIS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
21 | 106463 | Int Command Maint | J.2.02.2.01.07 | KHAZRA, MOOJAN | -50943.2878 | -0.74694 | -36464.8798 | 152293.6322 | 203236.92 | 143261.5127 | 2020-09-27 | Int Command Maint | Int Command Maint | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
22 | 106411 | Common Logging Svc Maint | C.2.08.2.06.07 | PAJEVSKI, MICHAEL J | 2271.1118 | 0 | 1113.3881 | 24902.8618 | 34793.0638 | 65720 | 2020-09-27 | Common Logging Svc Maint | Common Logging Svc Maint | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
23 | 106464 | SPICEcraft | K.3.02.1.04.10 | CALEF, DR. FRED J | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | SPICEcraft | SPICEcraft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 106464 | DataDrive | K.2.04.1.03.10 | RADULESCU, COSTIN | 0 | 0 | 0 | 0 | 0 | 0 | 2020-09-27 | DataDrive | DataDrive
[5 empty] | 845160.7397 | 3.3045 | 559332.1142 | 15657905.3797 | 15698328.3291 | 19865456.4171 |  | 0