## Sheet1
Status Date: 9/27/19
MGSS Status Indicator | ID | WBS | #CAM | Task Name | % Complete | Duration | Start | Act/Est Start | Finish | Act/Est Finish | Baseline Finish | Explanation of Changes from Previous Month
| 223 | 01.01.01.A | Randerson | Low Thrust Option | 95% | 256 d | Mon 10/1/18 | Mon 10/1/18 | Fri 11/15/19
0 | 224 | 01.01.01.A | RAnderson | Perform Comparison of low-thrust solutions to optimal impulsive low-energy solutions across design space | 100% | 110 d | Mon 10/1/18 | Mon 10/1/18 | Thu 3/28/19 | Thu 3/28/19
0 | 225 | 01.01.01.A | RAnderson | Computation of low-thrust/low-energy results for more complex multi-body orbits to synthesize for search methodologies | 100% | 140 d | Mon 10/1/18 | Mon 10/1/18 | Wed 5/15/19 | Wed 5/15/19
0 | 226 | 01.01.01.A | RAnderson | Compute low-thrust solutions between complex combinations of three-body orbits using low-energy solutions | 100% | 190 d | Mon 10/1/18 | Mon 10/1/18 | Mon 8/5/19 | Mon 8/5/19
1 | 229 | 01.01.01.A | RAnderson | Perform in-depth comparison of DV requirements of optimal low-energy vs. low-thrust trajectories | 87% | 128 d | Mon 3/4/19 | Mon 3/4/19 | Fri 9/20/19
1 | 230 | 01.01.01.A | RAnderson | Perform detailed DV topology comparison of optimal trajectories for libration orbits | 87% | 128 d | Mon 3/4/19 | Mon 3/4/19 | Fri 9/20/19
0 | 231 | 01.01.01.A | RAnderson | Draft of Conference Paper | 100% | 26 d | Mon 6/17/19 | Mon 6/17/19 | Fri 7/26/19 | Fri 7/26/19
0 | 232 | 01.01.01.A | RAnderson | Conference Paper (Summer 2019) | 100% | 1 d | Mon 7/29/19 | Mon 7/29/19 | Mon 7/29/19 | Mon 7/29/19
3 | 233 | 01.01.01.A | RAnderson | Annual Report | 0% | 1 d | Fri 11/15/19 |  | Fri 11/15/19
| 234 | 02.01.12 | LTorgerson | AMMOS DTN Pilot Implementation | 69% | 281 d | Mon 10/1/18 | Mon 10/1/18 | Tue 12/31/19
| 235 | 02.01.12 | LTorgerson | File Synch Software | 86% | 157 d | Tue 1/22/19 | Tue 1/22/19 | Fri 9/27/19
0 | 236 | 02.01.12 | LTorgerson | Deliver to MITRE & MSFC for Alpha Testing | 100% | 48 d | Tue 1/22/19 | Tue 1/22/19 | Fri 3/29/19 | Fri 3/29/19
0 | 237 | 02.01.12 | LTorgerson | JPL/MITRE/MSFC Alpha Testing | 100% | 40 d | Mon 4/1/19 | Mon 4/1/19 | Fri 5/31/19 | Fri 5/31/19
0 | 238 | 02.01.12 | LTorgerson | Minor Bug Fixes | 100% | 19 d | Mon 6/3/19 | Mon 6/3/19 | Mon 7/1/19 | Mon 7/1/19
1 | 239 | 02.01.12 | LTorgerson | Consider Test Results and Plan Future Development | 0% | 18 d | Thu 8/29/19 |  | Fri 9/27/19
| 240 | 02.01.12 | LTorgerson | DTN-AMP GUI for NM&C | 66% | 281 d | Mon 10/1/18 | Mon 10/1/18 | Tue 12/31/19
0 | 241 | 02.01.12 | LTorgerson | Document Initial Set of GUI Requirements (APL) | 100% | 56 d | Mon 10/1/18 | Mon 10/1/18 | Fri 12/28/18 | Fri 12/28/18
0 | 242 | 02.01.12 | LTorgerson | Document Overall New GUI Design Approach (JPL) | 100% | 75 d | Mon 10/1/18 | Mon 10/1/18 | Thu 1/31/19 | Thu 1/31/19
0 | 243 | 02.01.12 | LTorgerson | Review and Document Data Model (APL with JPL Participation) | 100% | 100 d | Mon 11/5/18 | Mon 11/5/18 | Thu 4/18/19 | Thu 4/18/19
0 | 244 | 02.01.12 | LTorgerson | Data Model Published | 100% | 33 d | Tue 5/21/19 | Tue 5/21/19 | Fri 7/12/19 | Fri 7/12/19
3 | 245 | 02.01.12 | LTorgerson | Overall System Design Published | 0% | 1 d | Mon 9/30/19 |  | Mon 9/30/19
1 | 246 | 02.01.12 | LTorgerson | Design & Prototype Python Based SQL Interface for GUI (JPL) | 90% | 157 d | Tue 1/22/19 | Tue 1/22/19 | Thu 9/26/19
1 | 247 | 02.01.12 | LTorgerson | Design User Facing GUI (JPL) | 90% | 156 d | Tue 1/22/19 | Tue 1/22/19 | Wed 9/25/19
0 | 248 | 02.01.12 | LTorgerson | Finalize and Publish SQL Schema (APL) | 100% | 1 d | Mon 4/1/19 | Mon 4/1/19 | Mon 4/1/19 | Mon 4/1/19
1 | 249 | 02.01.12 | LTorgerson | Produce Python Test Scripts (APL) to Test SQL DB Ops | 10% | 125 d | Tue 4/2/19 | Tue 4/2/19 | Fri 9/27/19
2 | 250 | 02.01.12 | LTorgerson | Prototype Python SQL Interface for GUI (JPL) | 0% | 43 d | Fri 9/27/19 |  | Tue 11/26/19
1 | 251 | 02.01.12 | LTorgerson | Prototype Initial GUI (JPL) | 25% | 87 d | Mon 4/29/19 | Mon 4/29/19 | Fri 8/30/19
1 | 252 | 02.01.12 | LTorgerson | Demo Initial GUI with Python SQL I/F (JPL/APL) | 0% | 1 d | Thu 9/26/19 |  | Thu 9/26/19
3 | 253 | 02.01.12 | LTorgerson | Develop User Facing Portion of GUI (JPL) | 50% | 61 d | Tue 8/20/19 | Tue 8/20/19 | Wed 11/13/19
3 | 254 | 02.01.12 | LTorgerson | Test GUI/Python/SQL/DTN-AMP MGR as a System (JPL/APL) | 0% | 26 d | Thu 11/14/19 |  | Mon 12/30/19
3 | 255 | 02.01.12 | LTorgerson | Demo of Basic GUI System for OPS (JPL/APL) | 0% | 0 d | Tue 12/31/19 |  | Tue 12/31/19
| 256 | 03.01.13 | SChien | Next Gen Plan & Seq | 83% | 224 d | Mon 10/1/18 | Mon 10/1/18 | Thu 9/26/19
0 | 257 | 03.01.13 | SChien | Build More Complex Test Domain | 100% | 92 d | Mon 10/1/18 | Mon 10/1/18 | Thu 2/28/19 | Thu 2/28/19
1 | 259 | 03.01.13 | SChien | Provide interface specifications for at least two timeline types supporting incremental modeling for inclusion into the Merlin architecture | 30% | 30 d | Mon 8/12/19 | Mon 8/12/19 | Thu 9/26/19
| 260 | 03.01.13 | SChien | Mission Analysis | 100% | 18 d | Mon 7/29/19 | Mon 7/29/19 | Fri 8/23/19 | Fri 8/23/19
0 | 261 | 03.01.13 | SChien | Complete preliminary design for coverage greedy search in CLASP coverage scheduler. Implement strawman non incremental greedy search algorithm | 100% | 18 d | Mon 7/29/19 | Mon 7/29/19 | Fri 8/23/19 | Fri 8/23/19
| 264 | 04.01.14 | JStuart | Interactive Data Vis | 89% | 272 d | Mon 10/1/18 | Mon 10/1/18 | Fri 12/13/19
0 | 265 | 04.01.14 | JStuart | Stabilize SunRISE Hololens Demo | 100% | 20 d | Mon 10/1/18 | Mon 10/1/18 | Tue 10/30/18 | Tue 10/30/18
0 | 266 | 04.01.14 | JStuart | Secure non-AMMOS funding of VR/AR Prototype for use as generalized design tool | 100% | 146 d | Mon 10/1/18 | Mon 10/1/18 | Thu 5/23/19 | Thu 5/23/19
| 268 | 04.01.14 | JStuart | Development of General Purpose VR/AR Tool | 97% | 151 d | Wed 1/2/19 | Wed 1/2/19 | Thu 8/29/19
1 | 269 | 04.01.14 | JStuart | Generalized AR Trajectory Viewer with Wed-Portal Interface | 97% | 151 d | Wed 1/2/19 | Wed 1/2/19 | Thu 8/29/19
| 271 | 04.01.14 | JStuart | Sustained Development of Orbit Determination Dashboard | 100% | 51 d | Wed 6/5/19 | Wed 6/5/19 | Fri 8/23/19 | Fri 8/23/19
0 | 272 | 04.01.14 | JStuart | Web Portal Access for MDNav user base | 100% | 36 d | Wed 6/5/19 | Wed 6/5/19 | Wed 7/31/19 | Wed 7/31/19
0 | 273 | 04.01.14 | JStuart | User interface (UX) interviews and feedback for HCI developers | 100% | 49 d | Mon 6/10/19 | Mon 6/10/19 | Fri 8/23/19 | Fri 8/23/19
0 | 274 | 04.01.14 | JStuart | Integration of UX feedback into Beta Prototype | 100% | 29 d | Thu 7/11/19 | Thu 7/11/19 | Fri 8/23/19 | Fri 8/23/19
| 275 | 04.01.14 | JStuart | Expansion of Monte Carlo Analysis Tool from missed thrust to other statistical analysis (planetary protection, conjunction analysis) | 40% | 205 d | Tue 1/22/19 | Tue 1/22/19 | Fri 12/13/19
0 | 276 | 04.01.14 | JStuart | Identification of Common Use Case (e.g. maneuver design) subject matter expert to provide data | 100% | 43 d | Tue 1/22/19 | Tue 1/22/19 | Thu 3/28/19 | Thu 3/28/19
2 | 277 | 04.01.14 | JStuart | Intern co-projects (one MDNav, one HCI) to prototype Monte Carlo dashboard | 0% | 65 d | Tue 9/3/19 |  | Fri 12/13/19
0 | 278 | 04.01.14 | JStuart | Identification and Initial Development of new prototype related to one of: broad search, optimization, maneuver planning | 100% | 58 d | Mon 4/1/19 | Mon 4/1/19 | Fri 6/28/19 | Fri 6/28/19
0 | 279 | 04.01.14 | JStuart | Presentation at Conference (SciPy, ASS, etc.) | 100% | 15 d | Thu 8/1/19 | Thu 8/1/19 | Fri 8/23/19 | Fri 8/23/19
| 280 | 04.01.15A | LTorgerson | AMES Deep Learning & Precursor Identification Task | 99% | 619 d | Fri 12/29/17 | Fri 12/29/17 | Fri 9/25/20
0 | 281 | 04.01.15A | LTorgerson | A Target Mission and End User Identified | 100% | 0 d | Fri 12/29/17 | Fri 12/29/17 | Fri 12/29/17 | Fri 12/29/17
0 | 282 | 04.01.15A | LTorgerson | Data Sources, Faults, SMEs Identified | 100% | 0 d | Fri 3/30/18 | Fri 3/30/18 | Fri 3/30/18 | Fri 3/30/18
0 | 283 | 04.01.15A | LTorgerson | Data Processed for Learning | 100% | 0 d | Fri 6/29/18 | Fri 6/29/18 | Fri 6/29/18 | Fri 6/29/18
0 | 284 | 04.01.15A | LTorgerson | Model Prototyped in Python | 100% | 0 d | Fri 9/28/18 | Fri 9/28/18 | Fri 9/28/18 | Fri 9/28/18
0 | 285 | 04.01.15A | LTorgerson | Validation Completed (offline data) | 100% | 56 d | Mon 11/19/18 | Mon 11/19/18 | Fri 2/22/19 | Fri 2/22/19
0 | 286 | 04.01.15A | LTorgerson | Explanation-visualization Developed | 100% | 65 d | Mon 2/25/19 | Mon 2/25/19 | Fri 5/24/19 | Fri 5/24/19
0 | 287 | 04.01.15A | LTorgerson | Model Extended for Streaming Data | 100% | 102 d | Mon 3/18/19 | Mon 3/18/19 | Fri 8/23/19 | Fri 8/23/19
1 | 288 | 04.01.15A | LTorgerson | "Operation Like" Playback Demo | 0% | 0 d | Fri 9/27/19 |  | Fri 9/27/19
3 | 289 | 04.01.15A | LTorgerson | Mission Data, Architecture, Hooks Identified | 0% | 0 d | Fri 12/27/19 |  | Fri 12/27/19
3 | 290 | 04.01.15A | LTorgerson | Model Attached to Hooks | 0% | 0 d | Fri 3/27/20 |  | Fri 3/27/20
3 | 291 | 04.01.15A | LTorgerson | Operational Concept Demo | 0% | 0 d | Fri 6/26/20 |  | Fri 6/26/20
3 | 292 | 04.01.15A | LTorgerson | Deliverables Submitted | 0% | 0 d | Fri 9/25/20 |  | Fri 9/25/20
| 293 | 05.01.13 | JLightholder | Data-Driven Explorer | 84% | 88 d | Wed 5/8/19 | Wed 5/8/19 | Wed 9/25/19
0 | 294 | 05.01.13 | JLightholder | Complete REDUX Port | 100% | 14 d | Wed 5/8/19 | Wed 5/8/19 | Thu 5/30/19 | Thu 5/30/19
0 | 295 | 05.01.13 | JLightholder | Basic User-Testing for Current Bug Scan | 100% | 15 d | Fri 5/31/19 | Fri 5/31/19 | Mon 6/24/19 | Mon 6/24/19
0 | 296 | 05.01.13 | JLightholder | Speed Optimization | 100% | 25 d | Tue 6/25/19 | Tue 6/25/19 | Thu 8/1/19 | Thu 8/1/19
1 | 297 | 05.01.13 | JLightholder | Encapsulate Regression/Curve Fitting/ Model Objects | 100% | 7 d | Thu 8/15/19 | Thu 8/15/19 | Mon 8/26/19 | 2019-08-26
1 | 298 | 05.01.13 | JLightholder | Demo Emphasizing Dataset Exploration/Bad Value Scan, Dimensionality Reduction, Logical Selections, Regression and Model Re-usage | 100% | 26 d | Thu 8/15/19 | Thu 8/15/19 | Wed 9/25/19 | 2019-09-20