## Slide 1
Instrument Data Processing
MMR May 2020
AMMOS Technology
Jack Lightholder

## Slide 2: Instrument Data Processing (CODEX)
Schedule
ID | WBS | CAM | Task Name | % Complete | Duration | Planned Start | Actual Start | Finished
375 | 05.01.13 | JLightholder | CODEX - Complex Data Explorer | 75% | 224 d | Tue 10/1/19 | Tue 10/1/19 | Fri 9/25/20
376 | 05.01.13 | JLightholder | Design and Implement "Data Quality Scan" User Interface | 100% | 62 d | Tue 10/1/19 | Tue 10/1/19 | 12/31/19
377 | 05.01.13 | JLightholder | Feature Bar Extension to Support Multiple Interaction Windows | 100% | 40 d | Thu 1/2/20 | 1/2/20 | 2/28/20
378 | 05.01.13 | JLightholder | Extend Server Data Reader Capabilities to for Additional Data Types | 100% | 33 d | Mon 3/2/20 | 3/1/20 | 4/15/20
379 | 05.01.13 | JLightholder | Extend Runtime Prediction Model to Support Features/Samples in Calculation | 100% | 22 d | Thu 4/16/20 | 3/1/20 | 3/15/20
380 | 05.01.13 | JLightholder | Design and Implement "Model Training" User Interface | 100% | 20 d | 3/15/20 | 3/15/20 | 4/1/20
381 | 05.01.13 | JLightholder | Enable Session Saving / Loading | 0% | 33 d | Tue 6/16/20 | NA | 
382 | 05.01.13 | JLightholder | Enable Data / Code / Selection / Feature Export | 0% | 17 d | Mon 8/3/20 | NA | 
383 | 05.01.13 | JLightholder | Advanced User Guidance Through Dynamic Error Reporting | 0% | 22 d | Wed 8/26/20 | NA | 

## Slide 3: CODEX
User Performance Improvements
Feedback from users of wanting to be able to load larger files
  Now supporting files up to 50MB
Improved responsiveness of plot interactions with large amounts of data
Researching dynamic downsampling (server) and point cloud reduction (client) strategies to make system more responsive.
Replace large file crashes with warnings and increased user guidance.

## Slide 4: CODEX
Infusion Status
Presented to VIPER mission team
  Considering CODEX for telemetry analysis and mission planning
  Reaching out to schedule follow-on meetings (Luke Dahl leading)
MAIA Mission Integration Conversations
  Initial meeting with science data systems and instrument data systems team leads.
  Provided access to CODEX for the team to explore
  Planning another demonstration of the tool for the larger team
Planning demonstration day with section 398 science data system and instrument data system groups to get user feedback.
  Workshop where users bring their own data to use in CODEX
  Design feedback for team on how users use the tool and features they desire.

## Slide 5: CODEX
Plans for Next Month
Performance improvements on larger data sets
Implement session saving/loading for multiple users and work states
User testing and future usability improvement documentation
SDDA testing with MSL data

## Slide 6: CODEX
Financial Status
Complex Data Explorer
  Actual YTD costs are $153K versus plan of $105K
    Slowing down while team committed to M2020 deliverables
    Could support additional funding with additional deliverables if available