## Sheet1
Status Date: 5/26/19
MGSS Status Indicator | Unique ID | #WBS | #CAM | Task Name | % Complete | Duration | Start | Act/Est Start | Finish | Act/Est Finish | Baseline Finish | Explanation of Change from Prior Month
0 | 1 | REF |  | Technology | 81% | 1439 days | Mon 6/30/14 | Mon 6/30/14 | Mon 11/16/20 |  | Fri 12/22/17
0 | 14 | REF |  | FY17 | 100% | 804 days | Mon 6/30/14 | Mon 6/30/14 | Fri 1/26/18 | Fri 1/26/18 | Fri 12/22/17
0 | 295 | REF |  | FY18 | 100% | 302 days | Mon 9/25/17 | Mon 9/25/17 | Tue 1/29/19 | Tue 1/29/19 | Fri 11/16/18
0 | 471 | REF |  | FY19 | 44% | 619 days | Fri 12/29/17 | Fri 12/29/17 | Fri 9/25/20 |  | Fri 9/25/20
0 | 493 | 106409-01.01.01.A | Randerson | Low Thrust Option | 34% | 256 days | Mon 10/1/18 | Mon 10/1/18 | Fri 11/15/19 |  | Fri 11/15/19
0 | 472 | 106409-01.01.01.A | RAnderson | Perform Comparison of low-thrust solutions to optimal impulsive low-energy solutions across design space | 100% | 110 days | Mon 10/1/18 | Mon 10/1/18 | Thu 3/28/19 | Thu 3/28/19 | Mon 10/29/18
1 | 473 | 106409-01.01.01.A | RAnderson | Computation of low-thrust/low-energy results for more complex multi-body orbits to synthesize for search methodologies | 55% | 140 days | Mon 10/1/18 | Mon 10/1/18 | Wed 5/15/19 |  | Tue 10/30/18
2 | 474 | 106409-01.01.01.A | RAnderson | Compute low-thrust solutions between complex combinations of three-body orbits using low-energy solutions | 25% | 169 days | Mon 10/1/18 | Mon 10/1/18 | Mon 7/1/19 |  | Mon 4/15/19
2 | 477 | 106409-01.01.01.A | RAnderson | Perform in-depth comparison of DV requirements of optimal low-energy vs. low-thrust trajectories | 5% | 128 days | Mon 3/4/19 | Mon 3/4/19 | Fri 9/20/19 |  | Fri 9/20/19
2 | 478 | 106409-01.01.01.A | RAnderson | Perform detailed DV topology comparison of optimal trajectories for libration orbits | 5% | 128 days | Mon 3/4/19 | Mon 3/4/19 | Fri 9/20/19 |  | Wed 5/15/19
3 | 480 | 106409-01.01.01.A | RAnderson | Draft of Conference Paper | 0% | 29 days | Mon 6/17/19 |  | Wed 7/31/19 |  | Wed 7/31/19
3 | 481 | 106409-01.01.01.A | RAnderson | Conference Paper (Summer 2019) | 0% | 1 day | Thu 8/1/19 |  | Thu 8/1/19 |  | Thu 8/1/19
3 | 482 | 106409-01.01.01.A | RAnderson | Annual Report | 0% | 1 day | Fri 11/15/19 |  | Fri 11/15/19 |  | Fri 11/15/19
0 | 571 | 106409-02.01.12 | LTorgerson | AMMOS DTN Pilot Implementation | 68% | 225 days | Mon 10/1/18 | Mon 10/1/18 | Mon 9/30/19 |  | Mon 9/30/19
0 | 572 | 106409-02.01.12 | LTorgerson | File Synch Software | 66% | 103 days | Tue 1/22/19 | Tue 1/22/19 | Tue 7/2/19 |  | Thu 12/27/18
0 | 573 | 106409-02.01.12 | LTorgerson | Deliver to MITRE & MSFC for Alpha Testing | 100% | 48 days | Tue 1/22/19 | Tue 1/22/19 | Fri 3/29/19 | Fri 3/29/19 | Mon 10/1/18
2 | 574 | 106409-02.01.12 | LTorgerson | JPL/MITRE/MSFC Alpha Testing | 25% | 40 days | Mon 4/1/19 | Mon 4/1/19 | Fri 5/31/19 |  | Thu 12/27/18
3 | 575 | 106409-02.01.12 | LTorgerson | Minor Bug Fixes | 0% | 0 days | Fri 5/31/19 |  | Fri 5/31/19 |  | Thu 12/27/18
3 | 576 | 106409-02.01.12 | LTorgerson | Consider Test Results and Plan Future Development | 0% | 0 days | Tue 7/2/19 |  | Tue 7/2/19 |  | Thu 12/27/18
0 | 577 | 106409-02.01.12 | LTorgerson | DTN-AMP GUI for NM&C | 68% | 225 days | Mon 10/1/18 | Mon 10/1/18 | Mon 9/30/19 |  | Mon 9/30/19
0 | 578 | 106409-02.01.12 | LTorgerson | Document Initial Set of GUI Requirements (APL) | 100% | 56 days | Mon 10/1/18 | Mon 10/1/18 | Fri 12/28/18 | Fri 12/28/18 | Thu 12/20/18
0 | 579 | 106409-02.01.12 | LTorgerson | Document Overall New GUI Design Approach (JPL) | 100% | 75 days | Mon 10/1/18 | Mon 10/1/18 | Thu 1/31/19 | Thu 1/31/19 | Thu 12/20/18
0 | 580 | 106409-02.01.12 | LTorgerson | Review and Document Data Model (APL with JPL Participation) | 100% | 100 days | Mon 11/5/18 | Mon 11/5/18 | Thu 4/18/19 | Thu 4/18/19 | Thu 12/20/18
3 | 581 | 106409-02.01.12 | LTorgerson | Data Model Published | 0% | 0 days | Thu 5/30/19 |  | Thu 5/30/19 |  | Thu 12/20/18
3 | 582 | 106409-02.01.12 | LTorgerson | Overall System Design Published | 0% | 0 days | Thu 5/30/19 |  | Thu 5/30/19 |  | Thu 12/20/18
1 | 583 | 106409-02.01.12 | LTorgerson | Design & Prototype Python Based SQL Interface for GUI (JPL) | 90% | 77 days | Tue 1/22/19 | Tue 1/22/19 | Tue 5/21/19 |  | Fri 2/22/19
1 | 584 | 106409-02.01.12 | LTorgerson | Design User Facing GUI (JPL) | 90% | 77 days | Tue 1/22/19 | Tue 1/22/19 | Tue 5/21/19 |  | Thu 3/28/19
0 | 585 | 106409-02.01.12 | LTorgerson | Finalize and Publish SQL Schema (APL) | 100% | 1 day | Mon 4/1/19 | Mon 4/1/19 | Mon 4/1/19 | Mon 4/1/19 | Mon 4/1/19
2 | 586 | 106409-02.01.12 | LTorgerson | Produce Python Test Scripts (APL) to Test SQL DB Ops | 10% | 48 days | Tue 4/2/19 | Tue 4/2/19 | Fri 6/7/19 |  | Fri 5/31/19
2 | 587 | 106409-02.01.12 | LTorgerson | Prototype Python SQL Interface for GUI (JPL) | 0% | 26 days | Mon 5/20/19 |  | Fri 6/28/19 |  | Fri 6/28/19
2 | 588 | 106409-02.01.12 | LTorgerson | Protoype Initial GUI (JPL) | 10% | 40 days | Mon 4/29/19 | Mon 4/29/19 | Fri 6/28/19 |  | Fri 6/28/19
3 | 589 | 106409-02.01.12 | LTorgerson | Demo Initial GUI with Python SQL I/F (JPL/APL) | 0% | 0 days | Mon 7/1/19 |  | Mon 7/1/19 |  | Mon 7/1/19
3 | 590 | 106409-02.01.12 | LTorgerson | Develop User Facing Portion of GUI (JPL) | 0% | 29 days | Tue 7/2/19 |  | Thu 8/15/19 |  | Thu 8/15/19
3 | 591 | 106409-02.01.12 | LTorgerson | Test GUI/Python/SQL/DTN-AMP MGR as a System (JPL/APL) | 0% | 26 days | Mon 8/19/19 |  | Thu 9/26/19 |  | Thu 9/26/19
3 | 592 | 106409-02.01.12 | LTorgerson | Demo of Basic GUI System for OPS (JPL/APL) | 0% | 0 days | Mon 9/30/19 |  | Mon 9/30/19 |  | Mon 9/30/19
0 | 593 | 106409-03.01.13 | SChien | Next Gen Plan & Seq | 67% | 225 days | Mon 10/1/18 | Mon 10/1/18 | Mon 9/30/19 |  | Wed 9/25/19
0 | 594 | 106409-03.01.13 | SChien | Build More Complex Test Domain | 100% | 92 days | Mon 10/1/18 | Mon 10/1/18 | Thu 2/28/19 | Thu 2/28/19 | Fri 12/28/18
2 | 597 | 106409-03.01.13 | SChien | Write Report on Recommendations - Target Publication at IWPSS | 50% | 180 days | Tue 12/11/18 | Tue 12/11/18 | Mon 9/30/19 |  | Wed 9/25/19
0 | 602 | 106409-04.01.14 | JStuart | Interactive Data Vis | 24% | 432 days | Mon 10/1/18 | Mon 10/1/18 | Thu 8/27/20 |  | Thu 9/26/19
0 | 603 | 106409-04.01.14 | JStuart | Stabilize SunRISE Hololens Demo | 100% | 20 days | Mon 10/1/18 | Mon 10/1/18 | Tue 10/30/18 | Tue 10/30/18 | Tue 10/30/18
1 | 604 | 106409-04.01.14 | JStuart | Secure non-AMMOS funding of VR/AR Prototype for use as generalized design tool | 50% | 146 days | Mon 10/1/18 | Mon 10/1/18 | Thu 5/23/19 |  | Fri 12/28/18
3 | 605 | 106409-04.01.14 | JStuart | Secure non-AMMOS funding for Orbit Determination Dashboard (OD-D) Development | 0% | 16 days | Thu 8/1/19 |  | Mon 8/26/19 |  | Thu 1/31/19
0 | 606 | 106409-04.01.14 | JStuart | Development of General Purpose VR/AR Tool | 21% | 376 days | Wed 1/2/19 | Wed 1/2/19 | Thu 8/27/20 |  | Thu 8/29/19
2 | 607 | 106409-04.01.14 | JStuart | Generalized AR Trajectory Viewer with Wed-Portal Interface | 50% | 151 days | Wed 1/2/19 | Wed 1/2/19 | Thu 8/29/19 |  | Wed 6/26/19
3 | 608 | 106409-04.01.14 | JStuart | Integrate VR Manipulation Prototype with Institutional Backend Solver (e.g. Monte) | 0% | 207 days | Tue 10/1/19 |  | Thu 8/27/20 |  | Thu 8/29/19
0 | 609 | 106409-04.01.14 | JStuart | Sustained Development of Orbit Determination Dashboard | 0% | 85 days | Wed 5/1/19 |  | Thu 9/12/19 |  | Thu 8/29/19
2 | 610 | 106409-04.01.14 | JStuart | Web Portal Access for MDNav user base | 0% | 36 days | Wed 5/1/19 |  | Wed 6/26/19 |  | Thu 2/28/19
2 | 611 | 106409-04.01.14 | JStuart | User interface (UX) interviews and feedback for HCI developers | 0% | 77 days | Wed 5/1/19 |  | Thu 8/29/19 |  | Tue 4/30/19
3 | 612 | 106409-04.01.14 | JStuart | Integration of UX feedback into Beta Prototype | 0% | 65 days | Mon 6/3/19 |  | Thu 9/12/19 |  | Thu 8/29/19
0 | 613 | 106409-04.01.14 | JStuart | Expansion of Monte Carlo Analysis Tool from missed thrust to other statistical analysis (planetary protection, conjunction analysis) | 36% | 140 days | Tue 1/22/19 | Tue 1/22/19 | Thu 8/29/19 |  | Thu 8/29/19
0 | 614 | 106409-04.01.14 | JStuart | Identification of Common Use Case (e.g. maneuver design) subject matter expert to provide data | 100% | 43 days | Tue 1/22/19 | Tue 1/22/19 | Thu 3/28/19 | Thu 3/28/19 | Tue 4/30/19
2 | 615 | 106409-04.01.14 | JStuart | Intern co-projects (one MDNav, one HCI) to prototype Monte Carlo dashboard | 0% | 77 days | Wed 5/1/19 |  | Thu 8/29/19 |  | Thu 8/29/19
2 | 616 | 106409-04.01.14 | JStuart | Indentification and Intial Development of new prototype related to one of: broad search, optimization, maneuver planning | 25% | 37 days | Mon 4/1/19 | Mon 4/1/19 | Tue 5/28/19 |  | Tue 5/28/19
3 | 617 | 106409-04.01.14 | JStuart | Presentation at Conference (SciPy, ASS, etc.) | 0% | 36 days | Thu 8/1/19 |  | Thu 9/26/19 |  | Thu 9/26/19
0 | 558 | 106409-04.01.15A | LTorgerson | AMES Deep Learning & Precursor Identification Task | 75% | 619 days | Fri 12/29/17 | Fri 12/29/17 | Fri 9/25/20 |  | Fri 9/25/20
0 | 559 | 106409-04.01.15A | LTorgerson | A Target Mission and End User Identified | 100% | 0 days | Fri 12/29/17 | Fri 12/29/17 | Fri 12/29/17 | Fri 12/29/17 | Fri 12/29/17
0 | 560 | 106409-04.01.15A | LTorgerson | Data Sources, Faults, SMEs Identified | 100% | 0 days | Fri 3/30/18 | Fri 3/30/18 | Fri 3/30/18 | Fri 3/30/18 | Fri 3/30/18
0 | 561 | 106409-04.01.15A | LTorgerson | Data Processed for Learning | 100% | 0 days | Fri 6/29/18 | Fri 6/29/18 | Fri 6/29/18 | Fri 6/29/18 | Fri 6/29/18
0 | 562 | 106409-04.01.15A | LTorgerson | Model Prototyped in Python | 100% | 0 days | Fri 9/28/18 | Fri 9/28/18 | Fri 9/28/18 | Fri 9/28/18 | Fri 9/28/18
0 | 563 | 106409-04.01.15A | LTorgerson | Validation Completed (offline data) | 100% | 56 days | Mon 11/19/18 | Mon 11/19/18 | Fri 2/22/19 | Fri 2/22/19 | Fri 12/28/18
2 | 564 | 106409-04.01.15A | LTorgerson | Explanation-visualization Developed | 80% | 62 days | Mon 2/25/19 | Mon 2/25/19 | Fri 5/31/19 |  | Fri 3/29/19
2 | 565 | 106409-04.01.15A | LTorgerson | Model Extended for Streaming Data | 50% | 67 days | Mon 3/18/19 | Mon 3/18/19 | Fri 6/28/19 |  | Fri 6/28/19
3 | 566 | 106409-04.01.15A | LTorgerson | "Operation Like" Playback Demo | 0% | 0 days | Fri 9/27/19 |  | Fri 9/27/19 |  | Fri 9/27/19
3 | 567 | 106409-04.01.15A | LTorgerson | Mission Data, Architecture, Hooks Identified | 0% | 0 days | Fri 12/27/19 |  | Fri 12/27/19 |  | Fri 12/27/19
3 | 568 | 106409-04.01.15A | LTorgerson | Model Attached to Hooks | 0% | 0 days | Fri 3/27/20 |  | Fri 3/27/20 |  | Fri 3/27/20
3 | 569 | 106409-04.01.15A | LTorgerson | Operational Concept Demo | 0% | 0 days | Fri 6/26/20 |  | Fri 6/26/20 |  | Fri 6/26/20
3 | 570 | 106409-04.01.15A | LTorgerson | Deliverables Submitted | 0% | 0 days | Fri 9/25/20 |  | Fri 9/25/20 |  | Fri 9/25/20
0 | 545 | 106409-05.01.13 | JLightholder | Data-Driven Explorer | 25% | 89 days | Wed 5/8/19 | Wed 5/8/19 | Thu 9/26/19 |  | Thu 9/26/19
2 | 546 | 106409-05.01.13 | JLightholder | Complete REDUX Port | 100% | 15 days | Wed 5/8/19 | Wed 5/8/19 | Fri 5/31/19 | Thurs 5/30/19 | Tue 4/30/19
3 | 547 | 106409-05.01.13 | JLightholder | Basic User-Testing for Current Bug Scan | 25% | 15 days | Mon 6/3/19 | Fri 6/1/19 | Tue 6/25/19 |  | Fri 5/31/19
3 | 598 | 106409-05.01.13 | JLightholder | Speed Optimization | 0% | 29 days | Wed 6/26/19 |  | Fri 8/9/19 |  | Wed 7/31/19
3 | 599 | 106409-05.01.13 | JLightholder | Encapsulate Regression/Curve Fitting/ Model Objects | 0% | 30 days | Mon 8/12/19 |  | Thu 9/26/19 |  | Thu 9/26/19
3 | 600 | 106409-05.01.13 | JLightholder | Demo Emphasizing Dataset Exploration/Bad Value Scan, Dimensionality Reduction, Logical Selections, Regression and Model Re-usage | 0% | 30 | Thu 9/26/19 |  | Thu 9/26/19 |  | Thu 9/26/19
0 | 503 | 106409-01.01.01.A | RAnderson | FY20 | 0% | 257 days | Mon 9/30/19 |  | Mon 11/16/20 |  | NA
3 | 504 | 106409-01.01.01.A | RAnderson | Implement low-thrust transfers directly using low-energy components including invariant manifolds & orbits | 0% | 225 days | Mon 9/30/19 |  | Thu 9/24/20 |  | NA
3 | 619 | 106409-01.01.01.A | RAnderson | Perform detailed DV topology comparison of optimal trajectories for complex trajectories | 0% | 81 days | Tue 10/1/19 |  | Tue 2/11/20 |  | Mon 9/23/19
3 | 505 | 106409-01.01.01.A | RAnderson | Draft of Conference Paper | 0% | 11 days | Wed 1/15/20 |  | Mon 2/3/20 |  | NA
3 | 506 | 106409-01.01.01.A | RAnderson | Conference Paper (Winter 2020) | 0% | 0 days | Mon 2/3/20 |  | Mon 2/3/20 |  | NA
3 | 507 | 106409-01.01.01.A | RAnderson | Draft of Conference Paper | 0% | 11 days | Wed 7/15/20 |  | Thu 7/30/20 |  | NA
3 | 508 | 106409-01.01.01.A | RAnderson | Conference Paper (Summer 2020) | 0% | 1 day | Mon 8/3/20 |  | Mon 8/3/20 |  | NA
3 | 509 | 106409-01.01.01.A | RAnderson | Complete search algorithms and algorithm document | 0% | 0 days | Thu 9/24/20 |  | Thu 9/24/20 |  | NA
3 | 510 | 106409-01.01.01.A | RAnderson | Final Report | 0% | 0 days | Mon 11/16/20 |  | Mon 11/16/20 |  | NA